## 2023
Name of Project: | Crown St Phase 2 Tower C4
Value of Project: | £74 Million
Duration of Project: | 3 Years
Date of Report:
Author:
Employment
Mechanisms of employment for local and appropriate individuals for the project. Ensuring that all individuals expressing interest are picked up by an employment initiative. Utilisation and development of local Sees.
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead
Apprentice's - Project Initiated |  |  | 8 |  | 8 |  | 8 |  | N/A
Apprentice's - Sustained |  |  | 10 |  | 10 |  | 10 |  | N/A
Apprentice Weeks |  |  | 234 |  | 234 |  | 234
Other Project Initiated Jobs
Project Specific Local Targets
This has a focus on the new workforce targets and the local agenda.
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead
Workforce comprising of permanent local residents
| % Manchester |  | 30 |  | 30 |  | 30 |  | 30
| % Greater Manchester |  | 50 |  | 50 |  | 50 |  | 50
| % North West |  | 15 |  | 15 |  | 15 |  | 15
| % Other |  | 5 |  | 5 |  | 5 |  | 5
Proportion of local subcontractors / supply chain | % Manchester |  | 5 |  | 5 |  | 5 |  | 5
| % Greater Manchester |  | 60 |  | 60 |  | 60 |  | 60
| North West |  | 20 |  | 20 |  | 20 |  | 20
| Other |  | 15 |  | 15 |  | 15 |  | 15
Employability & Learning
Activities and presentations to support individuals in the creation and development of skills deemed desirable to potential employers. Experience of real working environments and pressures and the need for communication skills. CV and interview skill development. Interventions to introduce contextual learning to secondary/ further and higher curriculum students to support functional skills and wider curriculum learning outcomes.
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead
Primary School Engagement
Enterprise Learning
Work Placement (Under 16 years)
Work Placement (Post 16 years)
Careers Package (Taster Days, Practice Interviews, Career Talks)
Site Tours
HE / FE Engagement / Research Projects
Professional Development Days (Teachers, Connexions, etc)
Volunteer / Pre-Employment Programmes
Development, Up skilling & Community Involvement
This has a focus on the existing workforce and site/project team and also local businesses and the community
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead
Vocational Courses / Short Courses
In-house development programmes: e.g. Graduate Management, Scholars, Supervisor training, Management development
CSCS Card Training
CSR / Time bank Days
Community Engagement Events
Meet the Buyer Events
SME Workshops H&S, Employment law, Bid Writing
Special Added Value Projects
The activities that may involve a number of the above elements and may be worthy of press coverage
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead

## 2022
Name of Project: | Crown St Phase 2 Development
Value of Project: | £155 Million
Duration of Project: | 3 Years
Date of Report:
Author:
Employment
Mechanisms of employment for local and appropriate individuals for the project. Ensuring that all individuals expressing interest are picked up by an employment initiative. Utilisation and development of local Sees.
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead
Apprentice's - Project Initiated |  | 4 | 6 |  | 6 |  | 8 |  | 8
Apprentice's - Sustained |  | 6 | 4 |  | 4 |  | 10 |  | 10
Apprentice Weeks |  | 130 | 120 |  | 120 |  | 234 |  | 234
Other Project Initiated Jobs
Project Specific Local Targets
This has a focus on the new workforce targets and the local agenda.
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead
Workforce comprising of permanent local residents
| % Manchester | 26 | 30 |  | 30 |  | 30 |  | 30
| % Greater Manchester | 50 | 50 |  | 50 |  | 50 |  | 50
| % North West | 17 | 15 |  | 15 |  | 15 |  | 15
| % Other | 7 | 5 |  | 5 |  | 5 |  | 5
Proportion of local subcontractors / supply chain | % Manchester | 4 | 5 |  | 5 |  | 5 |  | 5
| % Greater Manchester | 44 | 60 |  | 60 |  | 60 |  | 60
| % North West | 22 | 20 |  | 20 |  | 20 |  | 20
| % Other | 32 | 15 |  | 15 |  | 15 |  | 15 |  | Lifts (kone) Cladding (FOCCHI), Hoist (RECO)
Employability & Learning
Activities and presentations to support individuals in the creation and development of skills deemed desirable to potential employers. Experience of real working environments and pressures and the need for communication skills. CV and interview skill development. Interventions to introduce contextual learning to secondary/ further and higher curriculum students to support functional skills and wider curriculum learning outcomes.
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead
Primary School Engagement
Enterprise Learning
Work Placement (Under 16 years)
Work Placement (Post 16 years) |  | 2
Careers Package (Taster Days, Practice Interviews, Career Talks)
Site Tours
HE / FE Engagement / Research Projects
Professional Development Days (Teachers, Connexions, etc)
Volunteer / Pre-Employment Programmes
Development, Up skilling & Community Involvement
This has a focus on the existing workforce and site/project team and also local businesses and the community
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead
Vocational Courses / Short Courses |  | 14
In-house development programmes: e.g. Graduate Management, Scholars, Supervisor training, Management development |  | 15
CSCS Card Training |  | 1
CSR / Time bank Days
Community Engagement Events |  | 2
Meet the Buyer Events
SME Workshops H&S, Employment law, Bid Writing
Special Added Value Projects
The activities that may involve a number of the above elements and may be worthy of press coverage
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead

## 2021
Name of Project: | Crown St Phase 2 Tower C4
Value of Project: | £74 Million
Duration of Project: | 3 Years
Date of Report:
Author:
Employment
Mechanisms of employment for local and appropriate individuals for the project. Ensuring that all individuals expressing interest are picked up by an employment initiative. Utilisation and development of local Sees.
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead
Apprentice's - Project Initiated |  |  | 0 |  | 0 |  | 4 |  | 4
Apprentice's - Sustained |  |  | 2 |  | 3 |  | 3 |  | 3
Apprentice Weeks |  |  | 24 |  | 36 |  | 84 |  | 84
Other Project Initiated Jobs
Project Specific Local Targets
This has a focus on the new workforce targets and the local agenda.
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead
Workforce comprising of permanent local residents
| % Manchester |  | 30 |  | 30 |  | 30 |  | 30
| % Greater Manchester |  | 50 |  | 50 |  | 50 |  | 50
| % North West |  | 15 |  | 15 |  | 15 |  | 15
| % Other |  | 5 |  | 5 |  | 5 |  | 5
Proportion of local subcontractors / supply chain | % Manchester |  | 5 |  | 5 |  | 5 |  | 5
| % Greater Manchester |  | 60 |  | 60 |  | 60 |  | 60
| North West |  | 20 |  | 20 |  | 20 |  | 20
| Other |  | 15 |  | 15 |  | 15 |  | 15
Employability & Learning
Activities and presentations to support individuals in the creation and development of skills deemed desirable to potential employers. Experience of real working environments and pressures and the need for communication skills. CV and interview skill development. Interventions to introduce contextual learning to secondary/ further and higher curriculum students to support functional skills and wider curriculum learning outcomes.
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead
Primary School Engagement
Enterprise Learning
Work Placement (Under 16 years)
Work Placement (Post 16 years) |  |  | 2 | 2 | 2 | 2
Careers Package (Taster Days, Practice Interviews, Career Talks) | [7 empty] | 1
Site Tours
HE / FE Engagement / Research Projects
Professional Development Days (Teachers, Connexions, etc)
Volunteer / Pre-Employment Programmes
Development, Up skilling & Community Involvement
This has a focus on the existing workforce and site/project team and also local businesses and the community
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead
Vocational Courses / Short Courses |  |  |  | 16 |  | 16 |  | 16 |  | 16 | Included any instance where a member of staff from Crown 2 has attended recorded training including, internal training and external training
In-house development programmes: e.g. Graduate Management, Scholars, Supervisor training, Management development
CSCS Card Training
CSR / Time bank Days
Community Engagement Events
Meet the Buyer Events
SME Workshops H&S, Employment law, Bid Writing
Special Added Value Projects
The activities that may involve a number of the above elements and may be worthy of press coverage
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead
Following our adoption of Didsbury High School we visited and held a call with the school to support them with their entry to a school competition associated with COP28. We provided expert advice on desiging a sustainable building. | [5 empty] | 2

## 2020
Name of Project: | Crown St Phase 2 Tower C4
Value of Project: | £74 Million
Duration of Project: | 3 Years
Date of Report:
Author:
Employment
Mechanisms of employment for local and appropriate individuals for the project. Ensuring that all individuals expressing interest are picked up by an employment initiative. Utilisation and development of local Sees.
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead
Apprentice's - Project Initiated |  |  | N/A |  | N/A |  | N/A |  | 0
Apprentice's - Sustained |  |  | N/A |  | N/A |  | N/A |  | 0
Apprentice Weeks |  |  | N/A |  | N/A |  | N/A |  | 0
Other Project Initiated Jobs
Project Specific Local Targets
This has a focus on the new workforce targets and the local agenda.
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead
Workforce comprising of permanent local residents
| % Manchester | [7 empty] | 30
| % Greater Manchester | [7 empty] | 50
| % North West | [7 empty] | 15
| % Other | [7 empty] | 5
Proportion of local subcontractors / supply chain | % Manchester | [7 empty] | 5
| % Greater Manchester | [7 empty] | 60
| North West | [7 empty] | 20
| Other | [7 empty] | 15
Employability & Learning
Activities and presentations to support individuals in the creation and development of skills deemed desirable to potential employers. Experience of real working environments and pressures and the need for communication skills. CV and interview skill development. Interventions to introduce contextual learning to secondary/ further and higher curriculum students to support functional skills and wider curriculum learning outcomes.
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead
Primary School Engagement
Enterprise Learning
Work Placement (Under 16 years)
Work Placement (Post 16 years)
Careers Package (Taster Days, Practice Interviews, Career Talks)
Site Tours
HE / FE Engagement / Research Projects
Professional Development Days (Teachers, Connexions, etc)
Volunteer / Pre-Employment Programmes
Development, Up skilling & Community Involvement
This has a focus on the existing workforce and site/project team and also local businesses and the community
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead
Vocational Courses / Short Courses
In-house development programmes: e.g. Graduate Management, Scholars, Supervisor training, Management development
CSCS Card Training
CSR / Time bank Days
Community Engagement Events
Meet the Buyer Events
SME Workshops H&S, Employment law, Bid Writing
Special Added Value Projects
The activities that may involve a number of the above elements and may be worthy of press coverage
Activity | Target | Achieved to Date | Qtr 1 Forecast | Qtr1 Achieved | Qtr 2 Forecast | Qtr2 Achieved | Qtr 3 Forecast | Qtr3 Achieved | Qtr4 Forecast | Qtr4 Achieved | Update/Comments | Partners | Lead

## Guidance Notes
Added Value Report - Guidance Notes Please note Added Value Report is referred to as the 'Regeneration, Employment and Skills Plan' - RESP
ü
Primary School Engagement: These are specific activities that focus on primary schools. Activities may span a number of different subjects but carry a particular theme which is topical i.e.: heritage, sustainability, local history. Activities should be aimed at large audiences and may include: Art competitions, creative writing, drama etc. Engagement may be limited to schools local to the project, and the Local Authority can often assist with identifying and contacting schools.
ü
Enterprise Learning: These should not be a stand alone event - they should be linked in with the curriculum over the course of a school term and should culminate with an enterprise event. These primarily target secondary schools and there are several enterprise event templates in existence.
ü
Work Placement (Under 16 years): This may include any type of work placement, whether it is one day a week or a block period. All work placements should have planned outcomes and give some experience that is industry linked. An identified mentor should be put in place and organisations such as the National Careers Advice Service (Enterprise in Schools) can be used to facilitate the placements, as well as direct engagement with schools directly or the Local Authority. Only completed work placements should be counted.
ü
Work Placement (Post 16 years): As above except the sourcing of young people should be directed towards Local Authority (via the targeted youth support service using Career Connect), Job Centre Plus (JCP) or local colleges. Post 16 work placements sometimes link in with diploma course, or can target those individuals who are Not in Education, Employment or Training (NEET).
ü
Careers Package: This package involve anything that will help young people understand what a career in a specific industry might be like, and also includes those activities which may assist young people securing a job/further training. Activities include: taster days, mock interviews, ‘Master classes', ‘A Day in the life of…’ This package would also look at the various different roles within construction, trying to draw attention to the less well known trades.
ü
Site Tours: These are targeted at those in education and as with Enterprise learning, site tours where possible should not be stand alone. They should link in with another elements of the Regeneration, Employment and Skills Plan (RESP), whether this is a work placement or enterprise learning. Site tours that engage the local community can also be counted.
ü
HE Engagement / Research Projects: Involves a college/university student completing his/her research project on an element of the project. They will be provided with a mentor who will commit to 4 hours per month to assist the student. Subjects may also include those that may not seem directly relevant to construction, for example, photography, media, History etc.
ü
Professional Development Days: This applies to all those who may have influence over a young persons career choice/development such as teachers or Connexions reps. Sessions may include presentations from professionals within the industry that identify the industry trends and roles within the industry. This may also include teambuilding days and working with teaching professionals to develop activities within the Regeneration, Employment and Skills Plan (RESP).
ü
Volunteer / Pre-Employment Programmes: This target focuses on opportunities for the long-term unemployed, students or older community members. There may be less commitment with these opportunities and they should be aligned with some form of official accreditation. These people may require additional support.
ü
Apprentices – Project Initiated: This measures the number of new apprenticeships which have been initiated by the project.
ü
Apprentices – Sustained: This measure the number of apprentices that have come on to the project (maybe as part of the supply chain) but have not started their apprenticeship on this project. If possible, training hours of these individuals should be noted.
ü
Other Project Initiated Jobs: This includes all other project initiated jobs, that may target the long term unemployed in roles such as cleaner, general labouring, health & safety, IT. Where possible, these opportunities should be offered with training.
ü
Vocational Courses / Short Courses: Any course completed by the existing work force of any organisation engaged in the project.
ü
In-house development programmes: Include company specific training programmes which may not be accredited. There should be a Personal Development Plan (PDP) in place to provide evidence of this; Graduate Management, Scholars, Supervisor training, Management development etc.
ü
Construction Skills Certification Scheme: CSCS was set up to help the construction industry to improve quality and reduce accidents and cards are increasingly demanded as proof of occupational competence by contractors, public and private clients and others. They cover hundreds of occupations so whatever you do in construction there will be a card that is suitable. This target should capture information about those who have received a card for the first time, and those who have up-skilled to another card (i.e. heritage).
ü
CSR / Timebank Days: Time given by members of the project team and employees of all organisations involved to deliver some of the RESP commitments. This duties performed in this time must be outside of their daily job role. The number of people that take part in activities should be logged, and, if possible, so should the hours worked.
ü
Community Engagement Events: Events and activities that engage various communities with the project and link in with local activities, schools, residents associations etc.
ü
Meet the Buyer Events: The main contractor/s engage the local business community to offer information on the clients expectations and support where appropriate.
ü
SME Workshops, H&S, Bid Writing: This activity relates to the main contractor supporting the supply chain throughout the project. This includes holding workshops and setting up mechanisms/procedures to help them achieve added value requirements and to up-skill their own workforce.
ü
Special Added Value Projects: The activities that include one or a number of the above elements and may be worthy of press attention. These should be reported on a regular basis so they can be considered for the MCC, PR, Website and Newsletter. You may also wish to record Local Labour targets within this section.

## Apprentice Records
Apprentice Tracker
Project Name: | [11 empty] | 7
Author:
Apprentice Name | Postcode | Ward | Apprentice Trade | Apprentice Qualification | Training Provider | Employer | Start Date | End Date | New or Sustained? | GTA Apprentice | Previous job / placement | Progression
Fraser Wallace | M20 1HP | #N/A | Joiner | Level 2 Carpentry Apprenticeship | The Manchester College | AAA Joinery Ltd | 2014-01-01 | 2014-09-01 | New | Yes | Unempolyed | Full time Employment with AAA Joinery
Fraser Wallace | M44 6RF | #N/A | Engineer | Level 4 Site Engineer Technician | Salford City College | Renaker | 2021-09-01 | 2023-03-01 | New
George Constable | WA8 7BN | #N/A | Construction Manager | Level 4 Construction Site Supervisor | Salford City College | Renaker | 2021-09-01 | 2023-03-01 | New
Ben Lamb | OL3 6BX | #N/A | Engineer | Level 4 Site Engineer Technician | Salford City College | Renaker | 2021-09-01 | 2023-03-01 | New
Keane Swindells | M34 3FJ | #N/A | Quantity Surveyor | Construction Quantity Survey Technician | Salford City College | Renaker | 2021-09-01 | 2023-03-01 | New
Paige Couser | M27 4DY | #N/A | Construction Manager | Construction Project Managenent | Salford University | Renaker | 2021-09-01 | 2024-06-30 | Sustained
Joe Shearer | M38 9NR | #N/A | Construction Manager | Construction Project Managenent | Salford University | Renaker | 2021-09-01 | 2024-06-30 | Sustained
Shania Morris | M27 8GQ | #N/A | Construction Manager | Construction Project Managenent | Salford University | Renaker | 2021-09-01 | 2024-06-30 | Sustained
Jake Connell | WN6 0NB | #N/A | Plumbing Apprentice | Level 2 Plumbing | Wigan College | MWA | 2018-07-01 | 2022-06-30
Oliver Bassnett | M24 1QW | #N/A | Apprentice Eletrician |  | Oldham College | RNM | 2019-09-01 | 2023-06-30
Harrison Foulkes | BL2 3PQ | #N/A | Apprentice Eletrician |  | Bolton College | RNM | 2019-09-01 | 2023-06-30
Adam Walker | L15 8LU | #N/A | Apprentice Eletrician |  | Oldham College | RNM | 2019-09-01 | 2023-06-30
Omar Barnes | M24 5NU | #N/A | Apprentice Eletrician |  | Oldham College | RNM | 2019-09-01 | 2023-06-30
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A

## Local Labour
Local Labour Record
Project Name:
Author:
Tier | Area Definition | No. of Operatives | Percentage | Notes
1 | Local Ward Area (as identified within agreement) |  | #DIV/0!
2 | Manchester (all Manchester City Council wards not including the above) |  | #DIV/0!
3 | Greater Manchester (all GM residents not including Manchester) |  | #DIV/0!
4 | North West (all NW reidents not including GM) |  | #DIV/0!
5 | Other (all residents outside of the North West) |  | #DIV/0!
| Total Workforce | 0

## x
Postcode | OUTPUT AREA | LOWER SOA | 93 WARD | 04 WARD | Regen Area | CSTA? (Y/N) | CSTA Name | HMR? (Y/N) | HMR Name