## Sheet1
Inspection and Test Plan for T6676 Back Turner Street, Manchester
Project: | Back Turner Street |  | Project No. CSI | T6676 | ITP No. CSI-T6676
Compiled By: | S Bird /C BARNETT
Item No | Activity | Controlling Specifications | Inspection |  | Verifying Document/Reference | Inspection Authority | [6 empty] | Remarks
[6 empty] | CSI | Architect | Wicona | Dow Coning | CSI 3rd Party Engineer | Domis | EXTERNAL INSPECTION
|  |  | By Whom | Frequency
1 | Tender Drawings and Specification
| Compliance Check | Client / Engineers Specification | Estimating & Project Manager | All drawings and listed specifications | Drawings / Specifications | ü | ü | ü |  |  | ü
(Fully check Specs)
2 | Concept design
| Engineering checks - loadings and calcs | Client / Engineers Specification | CSI ENGINEER | All drawings and listed specifications | Drawings / Specifications |  | ü |  |  | ü | ü
| Drawings |  | ALL PARTIES |  |  | ü | ü | ü |  | ü | ü
3 | Final design
| Engineering/drawing/spec checks | Client / Engineers Specification | CSI | All drawings and listed specifications | Drawings / Specifications | ü | ü |  |  | ü | ü
Domis
4 | Samples and initial type tests
| HOLD POINT |  | Wicona and C.S.I. |  |  | ü |  | ü |  |  | ü |  | Record - Wicona / CSI quality records
| Samples for ITT manufactured by Wycona | Client/Engineers Specification |  |  | Drawings/Specifications
5 | Acoustic Assessment
| HOLD POINT |  | Wiconaand C.S.I. |  |  | ü |  | ü |  |  |  |  | Record -Wicona / CSI quality records
| Samples by Wicona | Client/Engineers Specification |  |  | Drawings/Specifications
6 | Material Procurement
| HOLD POINT |  | CSI Goods In/ISO9001 |  |  | ü | [6 empty] | Record - QSP010F2 Material Requisition register
| Drawings and requisitions | Client/Engineers Specification |  |  | Drawings/Specifications
7 | CE BsEn 1090 Testing
| HOLD POINT |  | RWC |  |  | ü
| Established that bracket is Strctural or non-structural and establish if CE marking required | Client/Engineers Specification | Magna?? |  | Certificate??
8 | Works orders
| HOLD POINT |  | Competent Works Order Controller | All works orders are checked before being issued to Production | Drawings / Specifications | ü
| Drawings & Specifications | Design Specifications | [10 empty] | Record- QSP010F5
| Check all WO machinings and details | Design Specifications/GA Drawings | [10 empty] | Record- QSP010F5a
Issue to production
9 | Goods Inwards
| HOLD POINT |  |  |  |  | ü | [6 empty] | WDCW001F29 & WDCW001F30 Record - Delivery notes / NCR records
| Quality/Quantity check | Design Spec/Order details | Stores Manager | All deliveries | Delivery Note / Purchase Orders
| Glass Inspection | Quality Control | Stores Manager | All deliveries | Delivery Note
10 | Wicona Manufacturing Supervision
| HOLD POINT |  | Dow Coning &Wicona |  |  |  |  | ü | ü |  |  | ü
Dow Corning Inspection & Sign Off
| Supervision over initial frame fabrication & Glazing | Wicona training and supervision |  | First frame | Wicona & Dow Coning quality standards | [7 empty] | Record- Wicona & Dow Coning to act as final QA signatory on WDCW005F1
11 | CWCT Sequence B Testing
HOLD POINT
| Water tightness test by Centre for Window and | CWCT parametres | CWCT | Test Sample Frame | CWCT standard guidelines |  |  | ü
| Cladding Technology | [11 empty] | CWCT certificate
12 | Manufacturing Inspections
HOLD POINT
| Benchmarking | Design/Project specifications | All parties | 1st off each unit |  | ü | ü | ü |  | ü | ü |  | Record - benchmark sign off records
| Check WO/Machining | W/O | WO Controller | All Works Orders | QC inline checks | ü | [6 empty] | Record - QSP010F5a WO Check
| 1st off check | Design Spec | Works Foreman | 1st off check | QC Final Checks | ü | [6 empty] | Record - Machining- WDCW001 F13/14/27. Unitised panels-WDCW005F1. Glass- WDCW001 F29/30
| 1-10 checks | System Manual | Works Foreman | 1-10 checks |  | ü | [6 empty] | Record- Machining- WDCW001 F13/14/27
| End of line QC | System manual and design spec | CSI Inspector | All complete frames | WDCW005F1 | ü | [6 empty] | Record - Initial WDCW005 F1 signed by Wycona. Remainder signed by Senior PM
13 | Pre Glaze Checks
HOLD POINT
| Check WO/Machining | W/O | WO Controller | All Works Orders | QC inline checks | ü | [6 empty] | Record - QSP010 F5a WO Check
| Glass Inspection | Design Spec | Works Foreman | 1st off check | QC Final Checks | ü | [6 empty] | Record - WDCW001F29/30 & WDCW005F1 Inspection
|  | System Manual |  | 1-10 checks |  | ü | [6 empty] | Record - WDCW001F13/14/27 & WDCW005F1 Inspection
|  | System Design Spec |  |  |  | ü | [6 empty] | Record - Wycona documents
14 | Wycona Final Inspections and Signoffs
| HOLD POINT |  | Wicona | [9 empty] | Record - WDCW005F1- initial frame to be signed off by Wycona
| Inspection of completed glazed units | Wicona training and supervision |  | All frames | Wicona quality standards |  |  | ü
15 | QC Documentation
| In process QC | W/O | WO Controller | All Works Orders | QC inline checks | ü | [6 empty] | Record - QSP010 F5/5a
| Glass Bonding QC & Testing | Sealent manufacturers specification | Glazing Manager | all units | Glazing/bonding test and check sheets | ü
| Weather Seal | Sealent manufacturers specification | Glazing Manager | all units | Glazing/bonding test and check sheets | ü
| Final QC | Design Spec/system manual | Works Foreman |  | QC Final Checks | ü | [6 empty] | Record - WDCW001F13/14/27/29/30 & WDCW005F1
| Photographic evidence | Quality Control | Foreman | All frames | QC Final Checks | ü | [6 empty] | Image Ref recorded on WDCW005F1 & stored on server.
16 | Loading and packaging
| Load stillages with correct protection | QSP012 Shipping and Logistics | Stores Manager | All dispatched deliveries | Dispatch Note | ü | [6 empty] | Record - Goods Dispatch Note
| Glass Inspection | Quality Control | Foreman | All dispatched deliveries | QC Final Checks | ü | [6 empty] | Record- WDCW001F29/30 & WDCW005F1
| Photographic evidence | Quality Control | Foreman | All dispatched deliveries | QC Final Checks | ü | [6 empty] | Image Ref recorded on WDCW005F1 & stored on server
17 | Site Delivery
| Dispatch Note |  | Csi Site | All deliveries | Dispatch Note-QSP012F5 | ü | [6 empty] | Record - Goods Dispatch Note QSP012F5
| QC Final Checks |  | Supervisor |  | Inspect Materials Received as per SP001 | ü | [6 empty] | Follow Procedure SP001
18 | Pre-start checks
| As per check sheet | Client / Engieers Specification | Csi PM | All Frames | Check sheet - Site001 F?? | ü | [6 empty] | Record - SITE001F15A/SITE001F36/SITE001F36A
| Wycona Supervision and Inspection | System Design Spec | Wycona Competent Pers. | Specified by Wycona | Wycona internal procedure | ü | [6 empty] | Record - Wycona documents
19 | Pre-installation checks
| As per check sheet | Wicona O&M | Csi PM | All Frames | Check sheet - Site001 F?? | ü | [6 empty] | Record - SITE001F15A/SITE001F36/SITE001F36A
| Wycona Supervision and Inspection | System Design Spec | Wycona Competent Pers. | Specified by Wycona | Wycona internal procedure | ü | [6 empty] | Record - Wycona documents
20 | Installation checks
| Inspection of all glazing | Wicona O&M | Csi PM | All Frames | Check sheet - Site001 F?? | ü |  | ü |  |  |  |  | Record - SITE001F15A/SITE001F36/SITE001F36A
| Wycona Supervision and Inspection | System Design Spec | Wycona Competent Pers. | Specified by Wycona | Wycona internal procedure | ü | [6 empty] | Record - Wycona documents
21 | Interface checks
| Inspection of all interfaces | Client / Engieers Specification | Csi PM | All Frames | Check sheet - Site001F?? | ü | [6 empty] | Record - SITE001F15A/SITE001F36/SITE001F36A
| Wycona Supervision and Inspection | System Design Spec | Wycona Competent Pers. | Specified by Wycona | Wycona internal procedure | ü | [6 empty] | Record - Wycona documents
22 | Handover checks
| Final inspection | Main Contractor Approval | Csi PM | All Frames | Check sheet - Site001 F15A/SITE001F35 Handover | ü |  | ü |  |  |  |  | Record - Handover Certificate SITE002F35
Main Contractor Finial Inspection
23 | Monitoring Non Conformance
| Csi Non Conformance/Improvement Procedure | Quality Plan/Quality System | Quality Manager | All NCRs | NCR Report & NCR Register (QSP008/QSP014) | ü | [6 empty] | Record - ISO9001 NCRs