## Sheet1
Planning Conditions - New Build
Date: 14/09/21
Condition | Type | Summary | Discharged | Discharge ref. | Resp. | Notes |  | Discharged | Partial | Submitted | Outstanding
1 | Compliance | 3 years expiry | N | Outstanding | MCC | No issues raised to date. MCC to confirm this can be closed |  |  |  |  | 1
2 | Compliance | In accordance with drwgs | N | Outstanding | MCC | No issues raised to date. MCC to confirm this can be closed |  |  |  |  | 1
3 | Pre-Commencement | Demolition | Y | Condition 3 | - | DISCHARGED |  | 1 |  | 1
4a | Pre-Commencement | Sample schedule | Y | Condition 4a, 8a, 12 | - | DISCHARGED |  | 1 |  | 1
4b | Pre-Commencement | Samples | Y | ufm7 | - | DISCHARGED (09/08/21)
5 | Pre-Commencement | CMP | Y | Condition 5, 6, 7, 16a | - | DISCHARGED |  | 1 |  | 1
6 | Pre-Commencement | Contractors wheels | Y | Condition 5, 6, 7, 16a | - | DISCHARGED |  | 1 |  | 1
7 | Pre-Commencement | Emergency telephone | Y | Condition 5, 6, 7, 16a | - | DISCHARGED |  | 1 |  | 1
8a | Post-Construction | Ground contamination | Y | Condition 4a, 8a, 12 | - | DISCHARGED |  | 1 |  | 1
8b |  | Ground contamination | Y | ufm7 | - | DISCHARGED (09/08/21)
9 | Post-Construction | Environmental standards | N | Outstanding | MA | Post construction review/certificate needed. Ongoing with Wallace Whittle - to be completed post PC as agreed with MCC |  |  |  |  | 1
10a Block C | Pre-Occupation |  | Y | Outstanding | - | DISCHARGED - PARTIAL |  |  | 1 | 1 | 1
10b Block E & F |  | SBD | N | Outstanding | MA | Final certificate issued via email 15/09/21. MCC to discharge
11 | Pre-Commencement | Surface water / foul | Y | Condition 11, 14, 15 | - | DISCHARGED |  | 1 |  | 1
12 | Pre-Commencement | Archaelogical works | Y | Condition 4a, 8a, 12 | - | DISCHARGED |  | 1 |  | 1
13 | Pre-Occupation | SUDS | N | Outstanding | MA/BH | CT issued additional info from BH on 28/01/21. Comments received from MCC (Flood Risk Management team) on 19/05/21. MA/BH responded on 03/08/21. MCC responded again on 09/08/21. MA/BH responded on 26/08/21. MCC responded again on 27/08/21. Additional information provided 13/09/21. Native to supply Maintenance Plan |  |  |  | 1 | 1
14 | Pre-Commencement | Surface water | Y | Condition 11, 14, 15 | - | DISCHARGED |  | 1 |  | 1
15 | Pre-Commencement | Local labour | Y | Condition 11, 14, 15 | - | DISCHARGED |  | 1 |  | 1
16a | Pre-Commencement | Materials | Y | Condition 5, 6, 7, 16a | - | DISCHARGED - PARTIAL |  |  | 1 | 1 | 1
16b |  | Footpaths | Y | Condition 16a, 16b, 16c | - | DISCHARGED - PARTIAL
16c |  | Tree species | Y | Condition 16a, 16b, 16c | - | DISCHARGED - PARTIAL
16d |  | Biodiversity | Y | Outstanding | MCC | Related to sign off of other conditions (16e blocker) MCC to discharge
16e |  | Street furniture | N | Outstanding | MCC | Information on proposed landscaping bins issued on 28/07/21. MCC to review/discharge
16f |  | Steps and handrails | Y | Outstanding | MCC | Related to sign off of other conditions (16e blocker) MCC to discharge
16g |  | - | - | - | - | Does not exist on original notice - mistake
16h |  | Signage strategy (wayfinding) | N | Outstanding | ASDL | ASDL to provide
16i |  | Street trees | N | Outstanding | MCC | Additional trial pit was dug 12/12/20. EA schematic drawings were issued to the planners 22/01/21. MA provided further details on 16/04/21 advising that there were no feasible locations where the trees could be planted. MCC have requested £21k contribution to plant trees elsewhere. ASDL have offered a £21k contribution. MCC to respond/discharge
16j |  | Canal edge | N | Outstanding | MCC | Information submitted. MCC to review/discharge
16k |  | Boating activity | N | Outstanding | MCC | Information submitted. MCC to review/discharge
17 | Pre-Occupation | Rochdale Canal | N | Outstanding | MCC | B+F provided additional test info on 17/12/20. CT submitted on 28/01/21. MCC to review/discharge |  |  |  | 1 | 1
18 | Pre-Occupation | Resi. Management Strategy | Y | Condition 18, 23 | - | DISCHARGED (23/04/21) |  | 1 |  | 1
19 | Pre-Occupation | Lighting Scheme | Y | Outstanding | MCC | Related to sign off of other conditions (13 and 17 blocker). MCC to discharge |  |  |  | 1 | 1
20 | Compliance | Glare | N | Outstanding | MCC | No issues raised to date. MCC to confirm this can be closed |  |  |  |  | 1
21 | Pre-Occupation | Travel Plan Framework | N | Outstanding | MCC | Revised Travel Plan has been provided by ASDL dated Feb 2021. CT issued 14/04/21. Chasing validation letter. MCC to review/discharge |  |  |  | 1 | 1
22a | Pre-Occupation | Acoustics - Resi | Y | Condition 22a | - | DISCHARGED - PARTIAL |  |  | 1 | 1 | 1
22b |  | Acoustic - Commercial | N | Outstanding | ASDL | ASDL / tenant to provide
23 | Pre-Occupation | Parking Management Strategy | Y | Condition 18, 23 | - | DISCHARGED (23/04/21) |  | 1 |  | 1
24a | Pre-Occupation | Acoustic insulation of plant - Resi | Y | Condition 24a | - | DISCHARGED - PARTIAL |  |  | 1 | 1 | 1
24b |  | Acoustic insulation of plant - Comm | N | Outstanding | ASDL | ASDL / tenant to provide
25a | Pre-Occupation | Fume extraction - Resi | Y | ufm7 | - | DISCHARGED - PARTIAL (09/08/21) |  |  | 1 | 1 | 1
25b |  | Fume extraction - Comm | N | Outstanding | ASDL | ASDL / tenant to provide
26 | Compliance | Use class | N | Outstanding | MCC | No issues raised to date. MCC to confirm this can be closed |  |  |  |  | 1
27a | Pre-Occupation | Signage Strategy | N | Outstanding | ASDL | CT to compile with ASDL input. ASDL to comment on draft document |  |  |  |  | 1
27b |  | Outside furniture | N | Outstanding | ASDL | ASDL to issue as part of Fit Out guide
28 | Compliance | Apartment use | N | Outstanding | MCC | No issues raised to date. MCC to confirm this can be closed |  |  |  |  | 1
29 | Pre-Occupation | Waste storage | N | Outstanding | ASDL | ASDL to provide |  |  |  |  | 1
30 | Compliance | TV reception | N | Outstanding | MCC | No issues raised to date. MCC to confirm this can be closed |  |  |  |  | 1
31a | Pre-Occupation | Servicing Management Strat. - Resi | N | Outstanding | ASDL | ASDL to provide |  |  |  |  | 1
31b |  | Servicing Management Strat. - Comm | N | Outstanding | ASDL | ASDL to provide
32 | Compliance | Deliverys etc | N | Outstanding | MCC | No issues raised to date. MCC to confirm this can be closed |  |  |  |  | 1
33 | Compliance | No mounted telecomms | N | Outstanding | MCC | No issues raised to date. MCC to confirm this can be closed |  |  |  |  | 1
34 | Compliance | No contaminated water | N | Outstanding | MCC | No issues raised to date. MCC to confirm this can be closed |  |  |  |  | 1
35 | Compliance | No amplified sound | N | Outstanding | MCC | No issues raised to date. MCC to confirm this can be closed |  |  |  |  | 1
36 | Compliance | Full disabled access | N | Outstanding | MCC | No issues raised to date. MCC to confirm this can be closed |  |  |  |  | 1
37 | Compliance | Bats | N | Outstanding | MCC | No issues raised to date. MCC to confirm this can be closed |  |  |  |  | 1
| Compliance Total | 12 |  |  |  | Total discharged: | 12
| Pre-Commencement Total | 10 |  |  |  | Total partial discharge: | 5
| Pre-Occupation Total | 13 |  |  |  | Total submitted: | 21
| Post-Construction Total | 2 |  |  |  | Total outstanding: | 25
| Overall Total | 37 |  |  |  | Overall: | 37 | (should be 37)