## Sheet1
SCHEDULE OF WORKS-MITIGATION MEASURES |  |  |  | FOURTH FLOOR 18 HILTON STREET
Indicating the effect of the proposals on the existing historic surfaces and elements, methods to be adopted and mitigation measures to be undetaken
Element of original fabric affected | Proposals affecting the element | Methods to be used for the work required | Potential effect on the element | Mitigation methods
Existing original pitch pine trusses and truss members | Removal of existing non-original partitioning and doors/architraves | Remove architraves, doors and door casings. Remove existing non-original skirtings, remove plasterboard linings both sides. Remove all vertical and intermediate studs leaving head and base rails. Carefully unscrew base and head rails from existing surfaces. plug existing screw holes , lightly sand and redecorate to match existing paint finishes | Damage to existing timber members | Careful removal of partitioning in stages starting with facings and vertical supports and removing head and cill members in isolation as opposed to wholesale demolition of entire partitioning areas.
Existing original pitch pine trusses and truss members | Fixing of new partition and glazed partition head rails and appearance of new plasterboard junctions with existing members | Proposed use of timber black shadowgap battens screwed using narrow gauge no 6 screws to beam members | Damage to existing timber members | Use of narrow gauge screws reduces the damage to the existing timbers by only creating a small fillable puncture hole. The shadowgap allows the plasterboard and skim to stand away from the members and give a shadow effect to the junction
Existing non-original but historic plasterboard ceiling linings (sloping and flat) | Removal of existing non-original partitioning and doors/architraves | As for removal of partition works to existing trusses above | Fixing damage to existing ceilings. | As for removal of partition works to existing trusses above
Existing non-original but historic plasterboard ceiling linings (sloping and flat) | Introduction of new partitioning | Proposed use of timber or metal head members screwed using narrow gauge no 6 screws to rafters or ceiling joists behind | Damage to boarded ceilings | Use of minimal fixings to the existing fabric. If noggins need inserting- the minimal works necessary are described.
Existing non-original but historic plasterboard ceiling linings (sloping and flat) | Introduction of lighting and cabled services | Lighting and cable distribution to be via suspended containment and suspended lighting. Using Unistruty short lengths of channel ( eg 350mm) screwed using narrow gauge no 6 screws through plasterboard to existing ceiling joists/rafters above. If no rafters present and noggins need to be instruduced then a small posket of plasterboard to be removed and reoplaced after the noggin is fixed. Re-skimmed and filled, sanded to match existing. | Damage to boarded ceilings | Avoidance of cut outs in boarding for lighting and burying cables, all equipment suspended using minimal fixings to the existing fabric. If noggins need inserting- the minimal works necessary are described.
Existing floor boards | Removal of existing non-original partitioning and doors/architraves | As for existing trusses above | Fixing damage to existing floorboards | Careful removal of partitioning in stages as described above.
Existing floor boards | Removal of existing non-original stuck down floorcoverings | Carpet tile flooring with tackyfire adhesive. Peel carpet off and gently remove tackfire with flat floor blade scraper taking care not to damage the timber surface. | Damage to existing floorboards | Careful removal of adhesive as described.
Existing floor boards | Removal of existing non-original carpet tile floorcoverings stuck down onto hardboard layer | Laid on Tackifire adhesive on hardboarded layer on top of the existing floor boards. The carpet adhesive is glued to the hardboard layer. Carefully de-nail and remove the hardboard to expose the clean boards under. | Damage to existing floorboards | As above
Existing floor boards | Removal of existing non-original linoleum floorcoverings | Loose laid on hardboard backing, remove hardboard as above | Damage to existing floorboards | As above
Existing floor boards | Introduction of power and data cabling circuits | Carefully remove and store existing floorboard in the direction of cable feed towards the desk/island. Replace with same size ( 25x100 galvanised box floor trunking flush with floor. | Damage to existing floorboards | The galvanised trunking cn be removed and the floorboard replaced if necessary to preserve the original fabric.
Element of original fabric affected | Proposals affecting the element | Methods to be used for the work required | Potential effect on the element | Mitigation methods
Existing plastered walls | Repairs to existing addled plaster and areas where plaster has fallen off | Remove loose addled plaster and wire brush existing masonry taking care to protect any existing woodwork such as window surrounds/architraves etc. Where plasterwork abuts windows existing window architraves to be carefully removed and pinned and glued back after plaster replacement. Apply 2 coat lime based renovation plaster to build up to level finishing coat with surrounding plaster. Apply plaste seal and decorate to match existing walls. | None- provided operations carried out carefully | Existing fixings to timber architraves and surrounds to be carefully removed to avoid splitting the wood.
Existing external brickwork (rear yard elevation) | installation on new foul drainage connection externally | Core drill minimum diameter hole required to suit a 100 dia cast iron dicharge pipe. Hole to be as tight as possible to allow for a recessed brick match mastic seal to be introduced so as not to be visible externally. No mortar to be used. Install matching profile 100 dia cast iron drainage wares and connect to existing original cast iron soil vent pipe. Paint in Pugin Red to match existing drainage wares. | Potential damage to brickwork and aesthetic appearance of rear elevation/being out of context with the historic nature of the elevation. | Use of accurate core drill to remove the damage caused by drilling/chiselling. Matchig cast iron wares to existing to ensure a seamless appearance from the existing elevation.