## Cover Sheet
Highways PMO
Introduction
This document is based on Manchester City Council's PEP process and is designed to manage the establishment, development and approval of Highways schemes to ensure the identified objectives at inception are monitored through delivery and achieved at completion.
How to use this document:
The spreadsheet contains various tabs: PEP 1 - Agreed Brief - to provide sufficient information to enable the scheme to be progressed PEP 2 - Design and Delivery - to provide sufficient information to enable the scheme to be designed and delivered Customer Satisfaction - To be completed by the client at the handover of the project
Version Control
Author and comments |  | Version No. | Status | Date
Ben Walker - Final version |  | 2 | Issued
Document Control
The controlled copy of this document is maintained by the Project Manager and Highways PMO. Any copies of this document held outside that area, in whatever format (e.g. Email attachment, paper) are considered to have passed out of control and should be checked for currency and validity.

## PEP 1 - Agreed Brief
Project Management Plan - Stage 1
Minor Works Client Brief & Project Parameters
Client Team Officer | Emma Todd
SRO Name & Contact
Requestee name, address and contact details | Regina Khanum Senior Project Manager Housing and Residential Growth Growth and Development Directorate Mobile: 07966382267 Email: r.khanum@manchester.gov.uk
Project Name / Reference | Smallwood Street Parking Bays
SAP Code if identified
1. Commission Assessment
If this commission is for Feasibility please complete section 1A. If this commission if for Works please complete section 1B.
1A. Feasibility
Please identify any surveys needed to inform this feasibility assessment | Yes
1B. Works
Is a programme required for the works? | Yes
Is a cost plan required for the works? | Yes
2. Background
Background to project
This scheme is part of a project to bring back into use a long-term brownfield site to build residential houses and apartments. One of the planning conditions is to develop a car parking strategy for the nearby District Centre to ensure there is sufficient parking for shoppers. There will be 100% parking for all the houses and 50% parking for the apartments as approved by Planning. The current parking bays on Smallwood Street will be removed as a result of the development and the developer widening the footway to cover the existing parking. The existing parking is not part of the adopted highway so in essence although it is owned by the council, it is not owned by Highways. A S247 (stopping up of highway) has been made (see Appendix Two) A S278 agreement is also to be agreed and the scope of the works has not yet been agreed with Rowlinson Constructions Limited. 10.05.22: S278 scope of works now agreed - see S278 folder. Neither schemes should impact each other.
Objectives of or reasons for project
To provide disabled parking and loading bays for the shops on Smallwood Street and parking bays on the MCC owned piece of land
Project Scope and Exclusions
Design Team to design and carry out the delegated power reports necessary to implement 7 short stay parking bays consisting of 2 disabled parking bays and 5 loading bays for the shops on Smallwood Street and the associated TRO (see Appendix One) Also to design and carry out the delegated power reports necessary to implement parking bays on the highlighted piece of MCC owned land that runs parallel to Great Newton Street and behind Newton Heath Working Men's Club (on the sandy coloured section above and to the right of F7622 highlighted in yellow - see Appendix Three) Design to advise how many bays are achievable. Also to advise if introducing a one way system on Smallwood Street as per Appendix One would be necessary.
3. Project Parameters
Budget and how this is accessed | Internal capital funding -CP4 approved for the overall project. Costings are needed to understand if the contingency/ provisional sum will cover the works, or if a further request is required.
Specific benefits/ outcomes | As above.
Environmental targets (inc low Carbon) | NA
Social value targets (see Social Value process Map) | 1. Highways have made significant improvements with embedding social value into the service and ensuring that all active contracts now have social value commitments within them. 2. Social Value opportunities are to be identified via the Neighbourhood priority list and delivered once the supplier is appointed - Jess Conley in Highways can support with this. 3. Having a Social Value agreement in place is a formal requirement and it is up to the supplier to decide what activities they will endeavour to deliver, however they should adhere to the MCC and GMCA priorities listed below: · Provide the best employment you can · Keep the clean air in Manchester · Create the employment and skills opportunities that we need to build back better · Be part of a strong local community · Make your organisation greener · Develop a local GM based and resilient supply chain
4. Project Risks
RISKS | Commentary/ cost/ time/ mitigation/ project effect
The Client may ask the Contractor leading on the overall development to deliver the works Client wishes to understand costs to support with relase of Planning condition.
5. Reports
Confirm which approval reports will be required (white, green etc) | White Report Green Report Yellow Report (if applicable) TMU Report
6 Agreement of brief
Client Team Officer | Emma Todd
SRO Name & Contact | 0
Highways Team Leader
Project Name/ Reference | Smallwood Street Parking Bays
I agree that the above brief has been presented and agreed as appropriate for the development of this project.
Head of Network Management signature & date *Clare Palmer to approve schemes under £50k* | C. A. Palmer 16.05.22.

## PEP 2 -Design + Delivery
Project Management Plan - Stage 2
Minor Works Design and Delivery
Client Team Officer |  | Emma Todd
SRO Name & Contact |  | 0
Requestee name, address and contact details |  | 0
Project Name / Reference |  | Smallwood Street Parking Bays
SAP Code if identified |  | 0
Highways Project Manager
Cost Manager
Design Lead |  | Yogeshwari Patel
P6 Code
1. Strategy & Brief - (summary from agreed brief)
1.1 Background to project (imported from previous sheet)
This scheme is part of a project to bring back into use a long-term brownfield site to build residential houses and apartments. One of the planning conditions is to develop a car parking strategy for the nearby District Centre to ensure there is sufficient parking for shoppers. There will be 100% parking for all the houses and 50% parking for the apartments as approved by Planning. The current parking bays on Smallwood Street will be removed as a result of the development and the developer widening the footway to cover the existing parking. The existing parking is not part of the adopted highway so in essence although it is owned by the council, it is not owned by Highways. A S247 (stopping up of highway) has been made (see Appendix Two) A S278 agreement is also to be agreed and the scope of the works has not yet been agreed with Rowlinson Constructions Limited. 10.05.22: S278 scope of works now agreed - see S278 folder. Neither schemes should impact each other.
1.2 Site considerations
Description of site, any necessary plans, any site constraints etc
1.3 Project objectives (imported from previous sheet)
To provide disabled parking and loading bays for the shops on Smallwood Street and parking bays on the MCC owned piece of land
2. Financial Position
2.1 Project Budget
3. Schedule
Activity Name |  |  | Start Date | Finish Date |  |  | Keep (Y/N)
Initiate Project |  |  | 2022-04-04 | 2022-04-11 |  |  | Y
Outline Design / Design Check |  |  | 2022-06-03 | 2022-06-17 |  |  | Y
Checkpoint Business Case | [6 empty] | N
Checkpoint 1 and 2 | [6 empty] | N
White Report - Approval to Consult |  |  | 2022-06-06 | 2022-06-27 |  |  | Y
Consultations |  |  | 2022-06-09 | 2022-06-30 |  |  | Y
Detailed Design |  |  | 2022-07-03 | 2022-07-31 |  |  | Y
Green Report |  |  | 2022-07-03 | 2022-08-14 |  |  | Y
Checkpoint 4 | [6 empty] | N
Design Complete & Issued as Final / Design Approved |  |  |  | 2022-08-14 |  |  | Y
Legal |  |  | 2022-08-14 | 2022-10-13 |  |  | Y
Yellow Report - If Objections | [6 empty] | N
Purchase Order Raised / Contract Award | [6 empty] | N
Mobilisation | [6 empty] | N |  | Auto-populated by Contract Award and Start on Site dates.
Permit Application - 3 month | [6 empty] | N |  | Auto-populated by Start on Site date.
Permit Application - 10 days | [6 empty] | N |  | Auto-populated by Start on Site date.
Start On Site | [6 empty] | N
Construction / Surveys / Studies | [6 empty] | N |  | Auto-populated by Start on Site and Handover dates.
Handover and Completion |  |  | 2022-11-10 | 2022-12-08 |  |  | Y
Final Account |  |  | 2022-12-22 |  |  |  | Y
Snagging / Defects (12 months) |  |  | 2022-12-22 | 2023-12-22 |  |  | Y |  | Auto-populated by Handover date.
Project Complete |  |  | 2023-12-22 | 2023-12-22 |  |  | Y |  | Auto-populated by Handover date.
4. Resources | [8 empty] | New Design Team fee rates are (per hour): |  | Inception
Project Phase | Resource (by name) |  |  | No of Hours | Rate | Recharge Cost |  |  | Grade 10 (Team Leader)- £69 | 71 | Design
Inception | Design Review / Budget est. CS |  |  | 2 | 71 | 142 |  |  | Grade 9 - £67 | 71 | Construction
Inception | Scope Review Eng- YP |  |  | 3 | 71 | 213 |  |  | Grade 8 - £71 | 71 | Closure
Design | Outline Design - Understand scheme/TRO requirements, Outline Scheme Design/White Report/Letters/Responces - YP |  |  | 30 | 71 | 2130 |  |  | Grade 7 - £65 | 65
Design | Outline Design Checks - MS/AP |  |  | 2 | 71 | 142 |  |  | Grade 6 - £60 | 60
Design | Outline Design Approvals -CS |  |  | 2 | 71 | 142
Design | Detailed Design - TRO Schedules, Parkmap, drawings, sign/lines design, BoQ- RD/JY |  |  | 35 | 65 | 2275
Design | Detailed Design - Green Report, Raise PO, Responses/Liasion/Legal, drawing/document checks, PCI, GMRAPS - YP |  |  | 28 | 71 | 1988
Design | Detailed Design Approvals - CS |  |  | 4 | 71 | 284
Construction | Site Inspection - YP |  |  | 5 | 71 | 355
Closure | TRO admin/handover to parking, final account/scheme closure -YP |  |  | 4 | 71
Closure | Final account/scheme closure - CS |  |  | 2 | 71 | 142
0
Total |  |  |  | 117 |  | 7813 |  | 0
Inception - Spend to Date Reports Studies - Forecast
5. Costs
| Y/N | Value |  | If legal involvement - select below:
Mancon | Y | 4000 |  | S278 |  |  | Y
Appointed Contractor | N |  |  | S38 |  |  | N
Amey | N |  |  | Closures |  |  | N
UTC | N |  |  | Residents Parking |  |  | N
Stats (BT etc) | N |  |  | Land Acquisition |  |  | N
Legal - Fee | Y | 2000 |  | TRO (List below) |  |  | Y
Legal - Advert | Y | 4000
Other: | N
Risk - Construction | N | 400 | [6 empty] | A generic 10% risk has been applied - Please over-type if it is different
Risk - Fee | Y | 816.8 | [6 empty] | A generic 10% risk has been applied - Please over-type if it is different
Fee | Y | 8168 | [6 empty] | Fee value taken from further up the form in the Resources section.
Total | 19384.8
Budget (Feasibility) | 20000 |  |  | Is the project forecasting an overspend?
Comments | The legal and construction costs are based on estimates, revised costs will be confirmed during detailed design and any underspent will be fully recharged. Assumption is that MCC will carry out detailed TRO design for the elements mentioned in PEP 1 (NOTE: physical works/site supervision / contractor liasion / statutory undertakers searches are not included). Relevant alternation and revocation to existing TROs that relate to the Stop up of roads and within the development have not been included. Client to advise if those are required. Client to share AutoCAD Drawings for Smallwood Road and highlighted piece of MCC owned land that runs parallel to Great Newton Street to ensure design accuracy. | [7 empty] | Please use this box to specify any requirements regarding the cost breakdown.
6. CDM Regulations
6.1 CDM regulations
Do the CDM regs apply, if not on what grounds?
6.2 Discharge of responsibilities
How will the client discharge responsibilities under CDM? If CDM regs do not apply what process will be put in place to manage safely?
7. Agreement of Project
Client Organisation/ Dept |  | 0
SRO Name & Contact |  | 0
Highways Team Leader |  | Constantina Stylianou
Project Name/ Reference |  | 0
MCC Client approval of scope and costs |  | I agree that the above plan has been presented and agreed as appropriate for the development of this project to expend funds, once approved, under the checkpoint process.
MCC Client signature & date
Requestee approval of scope and costs |  | In signing this document I have reviewed and agree with the brief and estimated costs included within the document.
Requestee signature and date |  | Martin Oldfield
Formulas:
Finish Date = [Start Date]+7
Finish Date = [Start Date]
Start Date = [Start Date, row above]+60
Start Date = [Finish Date, row above]+3

## Customer Survey
Highways
Client Satisfaction Survey
We appreciate your time in giving feedback on how Highways have provided support to you as a client and implemented your project. Please could you give some simple feedback below on your recent project.
Project
Client contact name
Date of survey
Please rate on a scale of 0 to 5 - where 0 is POOR and 5 is EXCEPTIONAL - the service provided at different phases of the project.
Project delivery - how did Highways perform in the delivery of this project?
| N/a | 0 | 1 | 2 | 3 | 4 | 5
Please tick as appropriate
Positive feedback
Negative feedback
Handover and close - how well did the Highways manage the completion and handover to you?
| N/a | 0 | 1 | 2 | 3 | 4 | 5
Please tick as appropriate
Positive feedback
Negative feedback
Please provide any additional feedback below: