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1. Introduction
The purpose of this report is to respond to the Planning Decision Notice for Silk St in relation to the following planning condition:
No. 36 - Prior to any above ground works, details of a car parking management strategy to consider and provide additional car parking and management of district centre car parking demands shall be submitted for approval in writing by the City Council, as Local Planning Authority. The approved details shall be implemented prior to the first occupation of the development hereby approved. 
Reason - In the interest of ensuring that there is sufficient and available car parking and management arrangements in place to support the district centre pursuant to policies SP1, T2 and DM1 of the Manchester Core Strategy (2012).

2. Car Parking Management Strategy
Officers have considered options to provide additional car parking to meet the demands of the district centre, and identified the following proposed solutions:
1. Introduction of 7 short stay parking bays, including 2 disabled parking bays on Smallwood St. Please see Appendix One for indicative design layout.
2. Introduction of parking bays on MCC owned land adjacent to Brighter Days nursey off Great Newton St.
MCC Highways have been commissioned to design and deliver the above.  Please see Appendix Two which details the commission brief. Outline timescales are provided below, and it is anticipated an initial detailed design will be available end of July 2022.
	
	
	

	Activity Name
	Start Date
	Finish Date
	Keep (Y/N)

	Initiate Project
	4/4/2022
	11/04/2022
	Y

	Outline Design / Design Check
	3/6/2022
	17/6/2022
	Y

	Checkpoint Business Case
	
	
	N

	Checkpoint 1 and 2
	
	
	N

	White Report - Approval to Consult
	6/6/2022
	27/6/2022
	Y

	Consultations
	9/6/2022
	30/6/2022
	Y

	Detailed Design
	3/7/2022
	31/7/2022
	Y

	Green Report
	3/7/2022
	14/8/2022
	Y

	Checkpoint 4
	
	
	N

	Design Complete & Issued as Final / Design Approved
	
	14/8/2022
	Y

	Legal
	14/8/2022
	13/10/2022
	Y

	Yellow Report - If Objections
	
	
	N

	Purchase Order Raised / Contract Award
	
	
	N

	Mobilisation
	
	
	N

	Permit Application - 3 month
	
	
	N

	Permit Application - 10 days
	
	
	N

	Start On Site
	
	
	N

	Construction / Surveys / Studies
	
	
	N

	Handover and Completion
	10/11/2022
	8/12/2022
	Y

	Final Account
	22/12/2022
	
	Y

	Snagging / Defects (12 months)
	22/12/2022
	22/12/2023
	Y

	Project Complete
	22/12/2023
	22/12/2023
	Y





