To: Jen Atkins

From: Regina Khanum:

Subject: Silk St Planning Condition no.36 - Parking Strategy

Date: 26.05.2022

________________________________________________________________________________

- Introduction

The purpose of this report is to respond to the Planning Decision Notice for Silk St in relation to the following planning condition:

No. 36 - Prior to any above ground works, details of a car parking management strategy to consider and provide additional car parking and management of district centre car parking demands shall be submitted for approval in writing by the City Council, as Local Planning Authority. The approved details shall be implemented prior to the first occupation of the development hereby approved.

Reason - In the interest of ensuring that there is sufficient and available car parking and management arrangements in place to support the district centre pursuant to policies SP1, T2 and DM1 of the Manchester Core Strategy (2012).

- Car Parking Management Strategy

Officers have considered options to provide additional car parking to meet the demands of the district centre, and identified the following proposed solutions:

- Introduction of 7 short stay parking bays, including 2 disabled parking bays on Smallwood St. Please see Appendix One for indicative design layout.

- Introduction of parking bays on MCC owned land adjacent to Brighter Days nursey off Great Newton St.

MCC Highways have been commissioned to design and deliver the above.  Please see Appendix Two which details the commission brief. Outline timescales are provided below, and it is anticipated an initial detailed design will be available end of July 2022.

| Activity Name | Start Date | Finish Date |  | Keep (Y/N) |
| --- | --- | --- | --- | --- |
| Initiate Project | 4/4/2022 | 11/04/2022 |  | Y |
| Outline Design / Design Check | 3/6/2022 | 17/6/2022 |  | Y |
| Checkpoint Business Case |  |  |  | N |
| Checkpoint 1 and 2 |  |  |  | N |
| White Report - Approval to Consult | 6/6/2022 | 27/6/2022 |  | Y |
| Consultations | 9/6/2022 | 30/6/2022 |  | Y |
| Detailed Design | 3/7/2022 | 31/7/2022 |  | Y |
| Green Report | 3/7/2022 | 14/8/2022 |  | Y |
| Checkpoint 4 |  |  |  | N |
| Design Complete & Issued as Final / Design Approved |  | 14/8/2022 |  | Y |
| Legal | 14/8/2022 | 13/10/2022 |  | Y |
| Yellow Report - If Objections |  |  |  | N |
| Purchase Order Raised / Contract Award |  |  |  | N |
| Mobilisation |  |  |  | N |
| Permit Application - 3 month |  |  |  | N |
| Permit Application - 10 days |  |  |  | N |
| Start On Site |  |  |  | N |
| Construction / Surveys / Studies |  |  |  | N |
| Handover and Completion | 10/11/2022 | 8/12/2022 |  | Y |
| Final Account | 22/12/2022 |  |  | Y |
| Snagging / Defects (12 months) | 22/12/2022 | 22/12/2023 |  | Y |
| Project Complete | 22/12/2023 | 22/12/2023 |  | Y |