## Schdule Of Works
Schedule of Works
Bar and Theatre Entry Frames - Drawing no 700 Rev B
1 | Allow for bar entry frame manufactured, supplied and installed as per. Powder coated Ral no 7021.
2 | Allow for supply and installation of 2no I Beam steel work entry sections to accept new bar and theatre fronts. Powder coated finish Ral no 7021.
3 | Allow for full renovation of original timber door and frame, supplied with new ironmongery. Renovation includes door easing and adjustments any timber splicing or making good.
5 | Associated builders works in connection with Arch entry installations.
Lobby Arch Access Works
1 | Arch knock through's to lobby and lobby 1 to accept new entry system at a later date.
2 | Allow for lobby and lobby 1 Arch knock throughs to have temp partition works to segregate and divide areas, Temp partition to be metal frame and track system with ply backing and 1 hour fire board for security and fire prevention, cosmetic overclad finish TBC.
Mezzanine - Drawing no 0602 Rev A
Bar Area Only
1 | Mezzanine floor supply and installation inclusive of galvanised chequer plate floor decking as shown on plan drawing. Steel frame to be fixed to localised foundation works to accept steel support stations.
2 | First floor mezzanine partition to segregate plant deck viewing in metal steel powder coated mesh detail proposal to allow aesthetic viewing appeal and aid air flow to plant deck machinery.
Flooring
1 | Allow for associated stone flagging repairs inclusive of uplift and relay where required to fall into sloping elevation levels. - Volunter?
Contingency for replacements stone flags - PC SUM
2 | Allow for central floor scabble or uplift between inlaid steel beams to accept new specialist concrete fibre finish, inclusive of full width finish to entry area below proposed mezzanine plant deck
Tanking works
1 | Allow for Arch bar area only to be tanked to front mezzanine and access location and to lower Arch WC area.
2 | Front entry area
3 | WC area
Redution for above needs to be discussed on site to extent of works for cost reduction.
Bar Drawings
1 | Allow for new front and back bar fittings supply and installation based on drawings with the following changes:
Note: Bar finish TBC to suit cost reduction
Bar spine front frame to be powder coated metal to accept cosmetic material cladding details.
Bar top tray t be formed in metal to accept concrete casting and brass coloured end trim.
Allow for possible timber sleeper to act as a plynth - foot rail
Cost inclusive of back bar above counter shelving and partitions to divide bar from keg /bin store and wash area location.
Unisex WC Area - Drawing no 2701 Rev A
1 | Allow for WC entry partition to a height of 2.7 FFL inclusive of 2no single doors with a vision panel in clear glass, door to be 2040 x 926 to allow for entry and disability access "WC door solid - no glazing"
2 | Open ceilings for aesthetic viewing of brick arches.
3 | Cubicles to be built to a height of circa 2.6FFL in timber framed carcass sat on DPM and walls constructed in moisture resistant MDF.
4 | Cubicle back walls to have IPS type void to accommodate soil pipes and cisterns etc, allowed full height with integrated access service panel- TBC
5 | Reed and bead board or similar to upper wall heights suggested in place of flat board finish due to moisture content in air.
6 | Full height doors and side frames.
WC Sundries
1 | Allow for mirrors and toilet roll holders, door hooks.
Mechanical & Electrical Works - See attached breakdown
Builders Works
Allow for builders works in connection with associated trades and possible internal Arch water ingress gutters to be localised area and below ground drainage for taking.

## Bar Elec
| Main Bar | £
Supply and install the following:
1 | Preliminaries | 2500
2 | Sub Main Distribution | 2770.9
1no. 24W TP&N distribution board (Located next to bar). 100A TP&N. SWA cabling switch fuse. Earthing
3 | Lighting - Applied cost reduction shown - On site lighting TBC to fit budgets - not as per drawings supplied. | 7000
20Mtrs of LED continuous strip lighting to bar counter
3no. 3mtr lighting tracks c/w 5no. LED directional track fittings to each track.
A £550.00 has been allowed for the cost of each of each track assembly.
24no. Decorative pendant lights
A £55.00 has been allowed for the cost of each pendant.
5no. Ceiling fittings
A £44.00 has been allowed for the cost of each fitting.
6no. Wall lights
A £55.00 has been allowed for the cost of each wall light.
14no. IP rated spot light fittings LED
24no. Emergency light fitting
All lighting to be switched from bar with exception of the lighting under the mezzanine
All lighting and cabling to be installed on / in galvanized tray / conduit
4 | Small Power | 5416.32
20no. 2 gang socket outlets (locations TBC)
1no. SP&N supply to Lossnay Unit
1no. SP&N supply to toilet extract
1no. TP&N supplies to A/C systems
1no. SP&N supply to fire detection and alarm system
5 | DDA Toilet Alarm Systen
| 2no. DDA toilet alarm kits | 822.8
| Total Cost | 18510.02

## Bar AC & Vent
£
Main Bar
Supply and install the following:
Heating, Cooling & Ventilation
1 | 1no. Lossnay LGH100 Heat recovery ventilation unit to provide fresh air via ducting | 6276.6
2 | 1no. Mitsubishi twin split cooling / heating comprising of 1no. 20KW condensing unit (located on the mezzanine in the Theatre) and 2no. 4 way fan coil units (cassettes) | 7596.6
3 | 1no. Toilet extract system | 3033.8
| Total Cost | 16907

## Bar Plumbing
£
Main Bar
Supply and install the following:
Plumbing Works
1 | 12no. Toilets with concealed cistern and soft close seat to each toilet cubicle
2 | 12no. Hand wash basin with mixer tap to each toilet cubicle
3 | 1no. DOC M pack to DDA toilet
4 | 3no. Sink units to the Bar
5 | Above ground waste and drainage
6 | Hot & Cold supplies (from new HW cylinder in theatre)
| Total Cost | 11522.5

## Fire Alarm
£
Main Bar
Supply and install the following:
Fire Detection & Alarm System
1 | 1no. Addressable control panel
2 | 12no. Smoke detector heads
3 | 6no. Sounder base
4 | 6no. Sounder / flashung base
5 | 5no. Call points
6 | 4no. Heat detectors
7 | 2no. Relay units
| Total Cost | 5335