## Sheet1
| PROJECT: | FLYING START | MMS044 |  | Today's Date | 26.04.2024
[5 empty] | Start on site date | 08.01.2024
Item | ACTION | DESCRIPTION | METHOD | RESPONSIBILITY | LINKS | DATE REQ BY | COMPLETE Y/N
1 | Contract Award LOI / Contract | Obtain LOI from client | Letter | Commercial Manager / Senior QS |  |  | Y
2 | Obtain Job Number from accounts in Brentwood | Obtain job number from Simon Bedford at Brentwood | Phone call | Commercial Manager / Senior QS |  |  | Y
3 | Tender handover meeting | Form ref EST006 | Meeting | Meeting | EST006 |  | N
4 | Appoint consultant team | Finalise appointments of consultant team | Issue standard agreements | Senior Surveyor |  |  | Y
5 | Confirm the scope of the appointment of a Fire Safety Consultant | Finalise appointment of consultant team | Issue standard agreements | Project Lead | EST001 |  | Y
6 | Place early subcontract orders | Place orders for early subcontractors such as demolition, piling etc | Subcontract order | QS |  |  | Y
7 | Bid Manager | If bid manager appointed, he/she to oversee consultant handover | Discussion | Director |  |  | N/A
8 | Full tender breakdown | Full build up information to all costs | Meeting QS / Estimator | Estimator |  |  | Y
9 | Tender scope and risk | Evaluation of further potential |  | Estimator / Bid Manager / QS / Project Manager |  |  | Y
10 | Create Work Test Inspection Plan & Work inspection sheets | Ensure inspection test plans and sheets are produced | QMS | Site Manager |  |  | Y
11 | Review project 'Building safety Case' | Ensure the project fire strategy and information required to substantiate the Building Safety Case is understood by project team. Ensure that appropriate compliance control measures and processes are identified & established for design, procurement, installation, validation, handover and McL digital record archive (Golden Thread) | Meetings, workshops , Operations ,QMS | Project Lead | MDM007a Pre Con design audit (Level 1) MDM007b Pre Con design audit (level 2) MDM007d Fire Strategy Audit (Res) MDM007e Fire Strategy Audit (None res) QMS029 Fire Protection Project Schedule QMS031 Building Safety Case Digital Record Checklist QMS032 Building Safety Case Final Compliance Audit | 2024-03-22 | Y
12 | Implement design management procedures & review existing design responsibility matrix | Refer to MMS & Simon Greaves | MMS 58, 59, 60, 61,,62 & 63 | Design Manager | MMS058 | 2024-05-01 | N
13 | Populate Staff responsibilities matrix |  | MMS002 | Site Manager | MMS002, SAF047 |  | Y
14 | Appoint site team |  | Discussion | Director/ Commercial Manager |  |  | Y
15 | Contact PR to set up meeting for site set up guidance / PR communications re project / marketing material | Order and set up press book | Download site set up / branding from portal | Secretary / Project Director / Site Manager |  |  | Y
16 | Internal Notification of Contract Award | Complete MMS 019 and email to all staff | Email | Site Manager | MMS019 |  | Y
17 | BioSite New Site Notification Form being completed and distributed | Complete SAF095 And distribute as required | Email | Project Lead | SAF095 |  | Y
18 | Review tender amendments | Evidence of tender amendments |  | Estimator |  |  | Y
19 | Existing Site Services Survey | Appoint IETG | Contact Engineering Dept | Site Manager |  |  | Y
20 | Level survey | Level survey layout to be agreed | Site Manager to contact Engineering Dept | Site Manager |  |  | Y
21 | Soils sampling testing | Check for any contamination etc | Appoint soils investigation consultant | Site Manager |  |  | Y
22 | Temporary works design | Define scope & appoint temporary works engineer |  | Site Manager |  |  | Y
23 | Order fencing / hoarding | Order site requirements | Requisition order | Site Manager |  |  | Y
24 | Site set up plan | Site logistics layout | Drawing / Sketch | Site Manager |  |  | Y
25 | Tree protection orders | Check if orders are present | Check planning conditions | Site Manager |  |  | Y
26 | Contact PR for site set up guidance press book & plasma images / marketing information | Order and set up press book | Download site set up / branding from portal | Secretary |  |  | Y
27 | Liaison meeting with utility for overhead power lines / underground / network rail / airports | Contact utility supplier if applicable | Phone and confirm by fax | Site Manager |  |  | Y
28 | Arrange site Utilities & connections such as ICT telephone, water, electricity & fire plan - obtain postcode & franking machine | Place orders , phone & broadband to be ordered via ICT | Standard ICT form & Letters | Site Manager |  |  | Y
29 | ICT & Photocopying requirements | Request for IT equipment | As –4.21 | Site Manager |  |  | Y
30 | Asbestos / Demolition Notification / application | Ensure both have been authorised / Notified | Phone call / letter | Site Manager |  |  | Y
31 | Programme, set up protocol & issue construction programme | Establish contract programme & checklist | Refer to MMS 055 | Site Manager | MMS055 |  | Y
32 | Information schedule | Review programme, specification and drawings | Standard form | Site Manager |  |  | Y
33 | Pre-commencement meeting | QA form ref SAF 01 |  | Site Manager | SAF - 01 |  | Y
34 | Party wall agreements | Set up agreements / notices for any party wall | Standard form / phone call | Site Manager |  |  | N/A
35 | Liaison with residents | Notify of commencement, period and contacts for job | Standard letter | Site Manager |  |  | Y
36 | Insurance & Bond | Check if client has requested adjoining owners insurance | Contact client | QS |  |  | Y
37 | Notify local authorities, Police, post office, hospital & Fire | Notify of commencement, period and contacts for job | Standard letter | Site Manager |  |  | Y
38 | Hoarding / scaffolding licence | Apply for if required | Standard letter | Site Manager |  |  | Y
39 | Arrange maintenance agreements | Have maintenance agreements been arranged for Landscaping, M&E and Lifts etc. Have the Commercial Department agreed stage payments for when each required maintenance visit has been carried out and agreed as procurement schedule |  | Project Manager / QS |  | 2025-01-01 | N
40 | SHEQ plan | Change site management plan to make it site specific | Standard form | Site Manager | SHEQ MMS046 |  | Y
41 | SHEQ Audits | Organise with SHEQ dept | Phone call / confirm by email | SHEQ Dept |  |  | Y
42 | Induction set up & Hospital Maps | Standard layout | Standard / non standard forms | Site Manager | SAF16/ SAF 18 / SAF53 |  | Y
43 | F10 | Ensure F10 is issued | Display on site notice board | Site Manager |  |  | Y
44 | Subcontractor & materials procurement schedule / arrange meetings | Set up procurement schedule for contract | Standard form | QS / Site Manager | MMS 011, MQS 7.1 |  | Y
45 | Obtain SHEQ start up pack | Issued at pre-start safety meeting | Phone call | SHEQ Dept |  |  | Y
46 | Pre-start client meeting | QA form | Meeting | Site Manager |  |  | Y
47 | Order defibrillator | Oder from Enfield Safety - Our Account Manager is Roger Munn: T 0845 683 2635 rmunn@enfieldsafety.co.uk | Email | Site Manager |  |  | Y
48 | Standardise Bill of Quantities | Standardise presentation format | To be actioned by QS | QS |  |  | Y
49 | Trade conditions | Sub-contractors trade conditions | To be actioned by QS | QS |  |  | Y
50 | Document management / 4 Projects | Drawing register QA form or set up 4 Projects | Standard form | Site Manager | MMS 003 |  | Y
51 | Notify environmental authority | Notify of commencement, period and contacts for job | Standard letter | Site Manager |  |  | Y
52 | Dilapidation survey | Full survey prior to start on site |  | Engineers |  |  | Y
53 | Planning 106 / 278 etc | Check requirements / assess including planning conditions | Check documents and clarify if necessary | Site Manager |  |  | Y
54 | Appoint BREEAM / SKA assessor & implement first review / meeting |  |  | Site Manager |  |  | Y
55 | Notify Building Control | [5 empty] | Y
56 | Emergency spill kit | Order emergency spill kit | Order | Site Manager |  |  | Y
57 | CCTV existing drainage | Check drainage including existing main connections if required | Subcontract order | Site Manager |  |  | Y
58 | Site signage | Order from relevant company – see site set-up manual | Order | Site Manager |  |  | Y
59 | Arrange labourers for set up | Arrange labourer through local papers for site | Phone call | Site Manager |  |  | Y
60 | Discharge license | Contact authority for foul and surface water licences | Utilities form | Site Manager |  |  | Y
61 | Pre start H&S meeting for early subcontractors |  | Standard form | Site Manager | SAF 03 |  | N
62 | Generator / fuel & Fuel store set up | Organise generator and fuel | Plant order | Site Manager |  |  | Y
63 | Organise skips / waste recycling | In accordance with SWMP | Order | Site Manager |  |  | Y
64 | Arrange first aider(s) | Statutory cover |  | Site Manager |  |  | Y
65 | Initial material order | Order initial materials | Requisition order | Site Manager |  |  | Y
66 | Order PPE | Order all necessary PPE from relevant company for visitors etc | Order from the standard schedule | Site Manager |  |  | Y
67 | Obtain standard forms from portal | download | Phone call / standard form | Site Manager |  |  | Y
68 | Appoint site secretary & order stationary | Appoint secretary & agree roles & responsibilities |  | Site Manager |  |  | Y
69 | Order site marketing merchandise | Standard pack | Obtain from PR | Site Manager |  |  | Y
70 | First aid | Order all necessary first aid equipment from relevant company | Standard materials | Site Manager |  |  | Y
71 | QA system / review audit schedule | Ensure that audits are in place | Standard forms | Site Manager | QMS Audit reports |  | Y
72 | Inspection rotas | Set up rotas | Standard form | Site Manager | WIS001 – 027/SAF 06 /30/33/42 |  | Y
73 | Traffic management plan |  | Marked up drawing | Site Manager |  |  | Y
74 | Tower Crane Notification | Refer to SHE001 – LOLE Procedure | Online / Post | Site Manager | SHE001 |  | Y
75 | Organise / establish site boundary, Verify survey stations / TBM set out controls | Survey for fencing / hoarding | Setting out |  |  |  | Y
76 | Progress photographs | Set up progress photograph sheet | Standard form |  |  |  | Y
77 | Standard letter head | Set up standard letter head containing address, phone / email etc | Computer |  |  |  | Y
78 | Site Master filing system & Emergency contact names | Adapt master filing system for job | Standard form | QS | MMS 034 |  | Y
79 | Drawing company | Appoint local drawing copying company | Order | QS |  |  | Y
80 | Crisis plan | Set up crisis plan for site and display | Standard form | Site Manager |  |  | Y
81 | Schedule design meetings - refer to MMS058 |  | Standard letter to consultants | Site Manager |  |  | Y
82 | Schedule staff meeting | Weekly / fortnightly |  | Site Manager |  |  | Y
83 | PAT testing and electrical safety certificate | By temporary contractor |  | Site Manager |  |  | Y
84 | Agree procedures for PO's & plant hire ( to be signed off by Director) | [5 empty] | Y
85 | Obtain design information for stats | Actioned by week 4 | Standard letter | Site Manager |  |  | Y
86 | Schedule subcontractor meeting |  | Standard letter to subcontractors | Site Manager |  |  | Y
87 | Petty cash | Organise petty cash with Accounts Dept at Brentwood Head Office | Phone call / standard form | Secretary |  |  | NA
88 | Signing in / out book | Set up signing in / out book for subcontractors on site | Order ring binder and set up sheets | Secretary |  |  | Y
89 | Weather notification board | Set up weather call on fax and display board | email | Secretary |  |  | Y
90 | Organise canteen company |  |  | Site Manager |  |  | N/A
91 | Frame Project Sheets | See site set up manual |  | Secretary |  |  | Y
92 | Saturday & Induction rota | Set up rotas |  | Site Manager |  |  | Y
93 | Four weekly Health and Safety meeting | Ensure first meeting has taken place |  | Site Manager | SAF-04 |  | Y
94 | Issue client satisfaction survey
95 | All items to be completed by first forecast meeting