## Sheet1
Condition | Information Requested | Response | Further Supporting Information
3 | The above information has been assessed and is considered insufficient to discharge this planning condition. This is on the basis that the applicant has failed to provide adequate details of: - A supporting method statement. - Details of replacement laths, type of wood, and measures for protection of existing plaster. - Animal hair is normally added to lime plasters particularly when plastering onto laths to help the plaster adhere onto the timber. Details of the mix and animal hair are required. The plaster and hair mix should match as closely as possible the existing plaster. | Please refer to the information that supplements this application
4 | Photographs of the existing slate and ridge tiles to gauge likeness. | Please see attached the photographic schedule that supplemts this application
7 | 'Room E25 Valley Beam Repair' appears to include a concrete padstone which is not a traditional repair. Justification for this is required. | One of the main load bearing beams supporting the rafters, rooflights and one of the central valleys has been completely rotted away at its end bearing and is at risk of complete failure. Due to the positioning of the beam and the amount of load it is supporting, replacement or splicing the beam is not possible and may lead to further complications. Therefore, the structural engineer has designed for a steel shoe to be bolted to the beam to support the end bearing. The concrete padstone has been introduced to provide a suitable bearing for the steel shoe, to allow the steel shoe to be securely installed and allow for the even distribution of the loads into the masonry. The padstone is to be concealed by lath and plaster and will not be visible. Please see photo adjacent of the condition of the beam end bearing.