## Sheet1
| PROJECT: | FLYING FINISH | MN1586 |  | Today's Date | 2025-07-28
[5 empty] | Completion date | 2025-06-18
F FNo. | ACTION | DESCRIPTION | METHOD | RESPONSIBILITY | LINKS | DATE REQ BY | COMPLETE Y/N
1 | PRE COMPLETION ITEMS
1.1 | Confirmation of services easements / Way leaves | Confirmation from Stats required | Letter confirming or requesting | Project / Site Manager |  |  | Y
1.2 | Electricity meters ordered via Shipper, date to be agreed when heads are installed | Place order with shippers | Letter | Commercial Manager / Senior QS
1.3 | Gas meters ordered via Shipper, date to be agreed when heads are installed | Place order with shippers | Letter | Commercial Manager / Senior QS
1.4 | Water meters ordered via Shipper, date to be agreed when heads are installed | Place order with shippers | Letter | Commercial Manager / Senior QS
1.5 | Ensure chlorination certificate is available for on site mains system prior to water authority connection. | Obtain certificate from M&E subcontractor | Discussion with subcontractor | Project / Site Manager
1.6 | Does water authority require on site plumbing inspection prior to final / meter connection | Arrange for inspection | Letter | Project / Site Manager
1.7 | Electricity supply capacities confirmed and connected | Confirm incoming supply meets requirements | Letter to M&E subcontractor & stat authorities | Project / Site Manager
1.8 | Pre commissioning of completed areas is available | Area partially completed can be pre commissioned | Discussion with subcontractor | Project / Site Manager
1.9 | Snagging system to be agreed / implemented and progressed | Assists in collating snags and producing reports | Contact David McDonnell | Project / Site Manager
1.10 | Preliminary Floor area measurement carried out and issued to client | Confirm areas as client required | Subcontract Order | Commercial Manager / Senior QS
1.11 | Final Floor area measurement carried out and issued to client | Confirm areas as client required | Subcontract Order | Commercial Manager / Senior QS
1.12 | External service duct layouts complete and marked up 'as built' | Form part of as built drawings | Marked up drawing | Site Engineer
1.13 | Drainage as built drawings | Form part of as built drawings | Marked up drawing | Site Engineer
1.14 | Confirmation that room data sheet requirements are met
1.15 | Confirmation of travel plans and finalisation
2 | TEST CERTIFICATES & COMMISSIONING
2.1 | Agree method to sign off witness testing | Agree with subcontractor | Discussion | Project / Site Manager
2.2 | Ensure BMS system set up and calibrated | Obtain witnessed tests & certificates | Letter requesting | Project / Site Manager
2.3 | Programme issued for testing & commissioning, comment on and agree indicating dates for witness testing | Request programme from subcontractor | Letter requesting | Project / Site Manager
2.4 | Commissioning and inspection of M&E services complete and reports compiled, detailing any minor outstanding actions. | Obtain witnessed tests & certificates | Letter requesting | Project / Site Manager
2.5 | Electrical system test certificates complete and available. | Obtain witnessed tests & certificates | Letter requesting | Project / Site Manager
2.6 | Fire alarm and detection system test certificates complete and available, witnessed by & issued / to Building Control | Obtain witnessed tests & certificates | Letter requesting & issue to Bld Ctrl | Project / Site Manager
2.7 | Smoke evacuation vents all operational, tested and certified, witnessed by & issued / to Building Control | Obtain witnessed tests & certificates | Letter requesting & issue to Bld Ctrl | Project / Site Manager
2.8 | Does Clients insurers / end user require sign off of sprinkler system | Query with client | Letter | Project / Site Manager
2.9 | Sprinkler system test and handover certificates complete and available | Obtain witnessed tests & certificates | Letter requesting | Project / Site Manager
2.10 | Water chlorination certificates complete and available | Obtain witnessed tests & certificates | Letter requesting | Project / Site Manager
2.11 | Lightning protection test certificates complete and available | Obtain witnessed tests & certificates | Letter requesting | Project / Site Manager
2.12 | Emergency lighting, tested and certificates available witnessed by & issued / to Building Control | Obtain witnessed tests & certificates | Letter requesting | Project / Site Manager
2.13 | CCTV Tested & certificates obtained | Obtain witnessed tests & certificates | Letter requesting | Project / Site Manager
2.14 | Security / access systems tested & certificates obtained | Obtain witnessed tests & certificates | Letter requesting | Project / Site Manager
2.15 | Dock levellers tested & certificates obtained | Obtain witnessed tests & certificates | Letter requesting | Project / Site Manager
2.16 | Overhead doors tested & certificates obtained | Obtain witnessed tests & certificates | Letter requesting | Project / Site Manager
2.17 | Lux levels internal & external light readings taken & agreed | Obtain report | Letter requesting | Project / Site Manager
2.18 | Passenger lift commissioning complete and certified, including BT lines. | Obtain witnessed tests & certificates | Letter requesting | Project / Site Manager
3 | OTHER CERTIFICATION
3.1 | Remediation strategy signed off by EA | Confirmation of sign off required | Letter requesting EA | Project / Site Manager
3.2 | Knottweed/Ragwort removal certificate issued | Confirmation of removal required | Letter requesting from subcontractor | Project / Site Manager
3.3 | Bomb survey certificate issued | Confirmation of clearance required | Letter requesting from subcontractor | Project / Site Manager
3.4 | Pollution Prevention and Control Surrender Notice Issued | Confirmation of clearance required | Letter requesting from subcontractor | Project / Site Manager
3.5 | Proof of consignment certifications for contaminated muck off site | Collection of transfer tickets |  | Project / Site Manager
3.6 | Collation of clean air certificates (asbestos removal) | Confirmation of clearance required | Letter requesting from subcontractor | Project / Site Manager
3.7 | Drainage system tested and inspected by Building Control with records & inspection certificates | Air Tests & Sign off required | Letter requesting from Bld Ctrl | Project / Site Manager
3.8 | Building Control Certificate of Completion for construction | Final building control sign off | Letter requesting from Bld Ctrl | Project / Site Manager
3.9 | Building Control plans approval certificate | Plan approval from Bld Control | Letter requesting from Bld Ctrl | Project / Site Manager
3.10 | Air leakage tests complete and compliant, issue to building control | Air Tests & Sign off required | Letter requesting from subcontractor | Project / Site Manager
3.11 | Thermo graphic survey complete and compliant ,issue to building control | Air Tests & Sign off required | Letter requesting from subcontractor | Project / Site Manager
3.12 | Local authority planning conditions, have been discharged noting prior to occupation items | Final discharge required | Letter requesting from planning liaison person | Project / Site Manager
3.13 | Confirmation of compliance with Legal Agreements -Section 106 etc. | Final discharge required | Letter requesting from planning liaison person | Project / Site Manager
3.14 | Confirmation of S278 sign off | Confirmation from LA required | Letter confirming or requesting | Project / Site Manager
3.15 | Confirmation of highways adoption | Confirmation from LA required | Letter confirming or requesting | Project / Site Manager
3.17 | BREEAM Certification issued, has desired rating been achieved | Confirmation from BREEAM Assessor required | Letter requesting | Project / Site Manager
3.18 | Roofing & cladding final inspection report sign off | Obtain report & certificates | Letter requesting | Project / Site Manager
3.19 | Roof flood test results | Obtain witnessed tests & certificates | Letter requesting | Project / Site Manager
3.20 | Has cladding manufacture issued Corus confidex certificate or equivalent | Obtain certificate | Letter requesting | Project / Site Manager
3.21 | Test Certification available for all 'mansafe' systems and equipment to be supplied available, (such as harnesses). | Obtain tests & certificates | Letter requesting | Project / Site Manager
3.22 | Mansafe end user sign off required | Query with client | Letter | Project / Site Manager
3.23 | Acoustic test finalise & certification |  |  | Project / Site Manager
3.24 | Smoke / thermographic survey |  |  | Project / Site Manager
3.25 | Syphonic drainage test certificates | Obtain tests & certificates | Letter requesting | Project / Site Manager
4 | CLIENT HANDOVER MATERIALS / PRODUCTS
4.1 | Door keys checked, tagged and marked up ready for signatures | Schedule produced and keys tagged | Letter of handover to client | Project / Site Manager
4.2 | Client / end user Operation and training regime agreed and planned | Schedule produced | Letter of handover to client | Project / Site Manager
4.3 | Independent floor surveys completed & issued, with any remedial works executed | Report produced | Letter of handover to client | Project / Site Manager
4.4 | CCTV survey completed of the full drainage system and all defects cleared. Has service provider been notified in writing of change of end user and new bill payer | Report produced | Letter of handover to client | Project / Site Manager
4.5 | Gas meter serial numbers and supply readings taken and recorded. Has service provider been notified in writing of change of end user and new bill payer | Reading taken & confirmed in writing | Letter to supplier & client | Project / Site Manager
4.6 | Water meter serial numbers and supply readings taken and recorded. Has service provider been notified in writing of change of end user and new bill payer | Reading taken & confirmed in writing | Letter to supplier & client | Project / Site Manager
4.7 | Electricity meter numbers and supply readings taken and recorded. Has service provider been notified in writing of change of end user and new bill payer | Reading taken & confirmed in writing | Letter to supplier & client | Project / Site Manager
4.8 | Complete as built drawings, refer to ER timescales stated in contract | Drawings required for O&M manual | Marked up drgs sent to consultants | Project / Site Manager
4.9 | Draft Health and safety file prepared and available | Prepared by CDMC | Liaison | Project / Site Manager
4.10 | Final Health and safety file complete and available | Prepared by CDMC | Letter of issue to client | Project / Site Manager
4.11 | Draft Operation and maintenance manuals available (to be prepared from day 1) | Prepared by CDMC | Liaison | Project / Site Manager
4.12 | Final Operation and maintenance manuals available (Chase comments on draft) | Prepared by CDMC | Letter of issue to client | Project / Site Manager
4.13 | Product guarantees and subcontractor warranties all executed | Information obtained form suppliers | Letters & tracking schedule | Commercial Manager / Senior QS
4.14 | All spares required for M&E system specified supplied and available, (e.g. filters, lamps, etc). | Obtain from subcontractors | Letter | Project / Site Manager
4.15 | Ancillary equipment required for lift complete and supplied, (e.g. pit ladders, barriers, drapes). | Obtain from subcontractors | Letter | Project / Site Manager
4.15 | Refer to schedule of agreed spares for building finishes | Obtain from subcontractors | Letter | Project / Site Manager
4.17 | Other equipment i.e. harnesses and contract specific items | Obtain from subcontractors | Letter | Project / Site Manager
4.18 | Consultant sign off letters confirming works in accordance with design specification | Letter confirming from consultants | Letter | Project / Site Manager
4.19 | Send Customer Satisfaction Questionnaire for completion and return. | Completion of MMS016 | MMS016 | Project / Site Manager
5 | CONTRACT ISSUES
5.1 | Cancel Insurances | If additional insurances taken for project | Phone call to Maurice Archer | Commercial Manager / Senior QS
5.2 | Relinquish bond if up to PC | If bond is to PC only | Phone call to Maurice Archer | Commercial Manager / Senior QS
5.2 | Relinquish PCG if up to PC | If PCG is to PC only | Phone call to Maurice Archer | Commercial Manager / Senior QS
5.3 | Archive site documents | Collate & archive | Refer to MMP Procedures | Commercial Manager / Senior QS
5.5 | Put in place latent defects insurance (if required) | Insurance Specific to certain projects | Phone call to Maurice Archer | Commercial Manager / Senior QS
5.6 | Obtain Practical Completion Certificate | Agree PC with client | Meeting | Project / Site Manager
5.7 | Agree procedure for clearing snags noted on PC certificate |  | Letter | Project / Site Manager
5.8 | Statement on agreed timescale to clear snags & programme | Refer to final snagright report | Letter | Project / Site Manager
5.9 | Practical Completion snag sign off | Agree sign off with client | Meeting | Project / Site Manager
5.10 | Eco sign off | Agree sign off with client | Meeting | Project / Site Manager
6 | SITE DECANT
6.1 | Arrange for Defib collection from Enfield Safety | Our Account Manager is Roger Munn : T 0845 683 2635 rmunn@enfieldsafety.co.uk | Email | Site Manager
6.2 | Divert Site Mail to Head Office | Contact post office | Letter | Project / Site Manager
6.3 | Cancel & pay up for temporary electric & water supplies | Contact suppliers | Letter | Project / Site Manager
6.4 | Cancel Phone Lines (1 months notice required) | Contact BT / CTT | Letter | Project / Site Manager
6.5 | Ensure all plant / equipment is off hired or relocated | Request latest plant hire schedule for checking | Phone call | Project / Site Manager
6.6 | Arrange for IT to be removed from cabins and notify CTT for asset register | Contact BT / CTT | Phone call | Project / Site Manager
6.7 | Remove Telephone system | Contact BT / CTT | Phone call | Project / Site Manager
6.8 | Arrange for cabins to be removed | Contact supplier | Phone call | Project / Site Manager
6.9 | Remove photocopier | Contact supplier McLaren IT NOT Supplier | Phone call | Project / Site Manager
6.10 | Cabins to be snagged and rectified & agreed with supplier prior to removal | Arrange for works to be completed | Letter | Project / Site Manager
6.11 | Have maintenance agreements been arranged for Landscaping, M&E and Lifts etc. Have the Commercial Department agreed stage payments for when each required maintenance visit has been carried out and agreed | Confirm orders for maintenance | Letter | Project / Site Manager
6.12 | Removal local site signage (i.e. finger boards etc) | Site activity | - | Project / Site Manager
6.13 | Advise all parties the project has finished i.e. SHEQ / IT departments | Contact individuals | Phone Call | Project / Site Manager
6.14 | Arrange Post handover security if project has been completed early | Contact security | Letter | Project / Site Manager
6.15 | Project De-Brief Meeting | Internal meeting to fully consider all aspects of the project | Meeting | Project / Site Manager
6.16 | Customer Feedback Questionnaire to be issued | Send to customer | Post / email | Project Manager
6.17 | Site Waste Management Plan (SAF48) / Accident book & Near miss reports to be sent to Head office, F.A.O. SHEQ Department | Send to Head Office | Post/email | Project / Site Manager
6.18 | Complete subcontractor appraisal form & return to estimating | Complete within 4 weeks of PC | MMS042 | Project / Site Manager / QS
6.19 | Review post contract contra charges with QS | Complete within 4 weeks of PC | email | Project / Site Manager
6.2 | Set date for client final account meeting | Complete within 4 weeks of PC | email | Project / Site Manager
6.21 | Ensure complete O&M manual information received from subcontractors |  | email | Project / Site Manager
6.22 | Set date for finalisation of subcontractor final accounts | Complete within 12 weeks of PC | email | Project / Site Manager
6.23 | Arrange feedback / post project review meeting with Precon / Ops & Estimating | Complete within 12 weeks of PC | email | Project / Site Manager