## SAMPLE PANEL COMMMENTS
Sample Panel Review Process |  |  | Condition 07
ELEMENT DISCUSSED | PLANNING OFFICER COMMENTS 03/07/24 | OMI RESPONSE | FOLLOW UP REVIEW MEETING 25/07/24 | OMI RESPONSE | PLANNING OFFICER COMMENTS
Brickwork | Brickwork types acceptable | Noted as agreed
Mortar | Mortar colours and pointing acceptable, subject to further comments below | Noted as agreed
Window System | Window system finsih (RAL colour) acceptable | Noted as agreed
Pointing | Detail at reveal of raked section has partially flush mortar. Planners expressed that this looks messy and that the mortar should be angled to reduce the contrast to the inset pointing. | Detail at reveal has partially flush mortar to allow a neat mastic junction with the window while maintaining the recessed pointing around the reveal corner. As a response to the comment raised the flush pointintg will be taken to the face of reveal (up to the recess on brickwork face), to improve appearance but maintain a good mastic junction. This has now been amended on the sample panel and is ready to review. | Pointing to reveal was deemed acceptable. | Noted as agreed
Mastic | Mastic to the buff brick sample acceptable. | Noted as agreed
Mastic | Mastic to the red brick sample not acceptable as it neither matches the window system or the brick. | An alternative mastic, which more closely matches the mortar used on the sample panel, has now been installed and is ready to review. | Revised mastic colour, Mapesil Cement Gray 113 – was deemed as acceptable. Minor comment on joint width, explained this was due to us having to cover over previous mastic samples. Moving forward mastic joint sizes will be minimised. | Noted as agreed
Mastic | Mastic to the window cill, where the cill is recessed, should terminate on the top of the cill at the junction with the precast and not return down the face as currently installed. | This has now been addressed and is ready to review. | Cutting back of mastic to ends of cills deemed acceptable. | Noted as agreed
Window System - sightlines | Comment received via email - We are not supportive of the proposed windows - the frames are deeper than what was shown on the approval (and agreed sample panel dwgs) and the opening light on the sample without the balaustrade was particularly of concern as the approved dwgs show a much slimmer profile frame (similar to that of the main frame) to the opening light. Again you will have to look at alternative window products which reflect the slim frames we anticipated in the approved dwgs. | In response to this comment we are able to propose an alternative, inward opening casement window system. This provides slimmer frame profiles than the previously proposed outward opening system, with sightlines very similar to the planning approved drawing. Please see attached drawing A-2006 which demonstrates this. | Frame section sizes/sight lines were discussed and the revised drawings issued as part of the response document, including the option to move to an inward opening window, was reviewed. It was agreed that this is an improvement over the previously proposed system. To be reveiwed with Angela on her return. |  | Accepted via AL email 06/08/24
Window System - cill fixings | Visible fixings queried on the cill. | Mechanical fixings to cills are preferred as they provide a robust, long lasting fixing to cills which can also be maintained. Adhered or trapped cill flashings are less robust and at risk of moving, warping or worst case dropping from the building during maintenance or high wind. In our view these should remain as per the sample panel. | To be reviewed with Angela on her return. |  | Accepted via AL email 06/08/24
Window System - drainage holes | Drainage hole covers to base of window should be colour matched. | This has now been addressed and is ready to review. | Colour matched drain caps deemed acceptable. Minor comment on finish consistency. This is to be monitored on site as part of QA procedures to ensure a consistent finish. | Noted as agreed
Window System - trickle vents | Comment receievd via email - Having checked the approved dwgs and latest amendments to the approved dwgs 137464/NMC/2023 we cannot see anything shown to reflect the inclusion of this element for trickle ventilation and we have not seen this solution on any other schemes within the City Centre. We are not supportive of this change to the approval due to its visual impact and awkward appearance within the affected window openings and you will therefore need to reconsider this element and look at alternative less visually intrusive ways to achieve the required ventilation. | Trickle ventilation is an instrinsic part of the overall ventilation strategy for the building, which utilises a KERS (kinetic energy recovery system) strategy. This involves mechanical extract via heat recovery to recycle warm air from inside the property to produce hot water. With this system air intake is via trickle ventilation. This strategy forms the basis of the sustainability strategy for the building and was consented through discharge of condition 15a Operational Energy. The use of trickle ventilaiton has been specifically set out in various documents both pre and post planning approval: The Acoustic Strategy Report by E3P submitted for the original planning application references the use of acoustic trickle vents (section 2.3.1). The E3P report references MCC's, 'Planning and Noise Technical Guidance Document (2015)'. which suggests the use of trickle ventilation. The development has followed this guidance. Followeing planning approval, the Acoustic Planning Report by Lighthouse Acoustics was submitted to discharge condition 30. This sets out the use of acoustic window ventilators as the strategy for intake ventilation in section 6.7. This condition was discharged in September 2023. Trickle ventilation is now stated in the wording of the advisory condition 30 within 138242/NMC/2023. A change to mechanical intake ventilation at this stage would have planning related implications. Additional rooftop plant would be required (PV panels) requiring amendments to consented parapet heights and/or a handrail detail. The sustainability strategy would need to be amended, affecting the consented condition 15a, and the acousticv strategy would require amendment affecting condition 30. We therefore cannot offer an alternaitve to the proposed trickle ventilation system and request that, due to the reasoning above, the detail can be agreed. | Comments remain on size of acoustic trickle vents. The reasoning for this was explained. PM queried whether more of the vent could be colour matched. This has subsequently been reviewed with the supply chain and unfortunately is not possible. To be reviewed with Angela on her return. | Pressed aluminium window head detail introduced which conceals the trickle vents whilst still allowing them to function as required. This balances the aesthetic and technical requirements and we hope that this now satisfies your concerns. Further Amendments following officer feedback: Introduce pistol bricks to window heads, to allow lintels/masonry support angles to be set higher. This allows us to reduce the gap between brickwork and flashing to circa 2-3mm, minimising the visual appearance at the outer brickwork line. Set outer edge back from face of brickwork by 10mm. This is the maximum that can be achieved as we need the flashing to allow for some brickwork tolerance. This will ensure a consistent detail across the building. Set vertical upstand face back by circa 20mm. This is the maximum we can achieve without clashing with the vent behind. Set underside of flashing up to minimise overall depth of detail. | Accepted via AL email 13/09/24