## Sheet1
Local Benefits / Social Value KPI Tracker
Supplier: | Short Construction Ltd |  |  |  | 01/05/2024 V1
Project / Contract Name: | Victoria Park (Laindon Road)
Measure | Target | Target Completion Date | Achieved Date | Current Status | Quarterly Update / Next Steps | Additional Notes
More people into work
Sustained apprentices | 2 | 2026-03-01
Apprentice Training Weeks | 2 | 2026-03-01
Track Jobs created (through Short Construction Ltd or sub contractors) | 2 (only guidance - to be used as an ambition) | 2026-03-01
Track Traineeships (placements offered) | 2 (only guidance - to be used as an ambition) | 2026-03-01
Track Work Experience placements (placements offered) | 2 (only guidance - to be used as an ambition) | 2026-03-01
Thriving local businesses
Local supply chain spend (within 10 mile radius) | 50% | 2026-03-01
Use local social enterprises in supply chain | 2 social enterprises throughout the life of the project | 2026-03-01
Local workforce - paid fairly and positively supported
100% of 'eligible staff' (i.e. working on site for 2 hors or more per week, for 8 weeks or more) to be paid the 'Real' Living Wage of £12 per hour. | 100% | 2026-03-01
Effective and resilient third sector
commitment to supporting local VCSE groups - e.g. no. of volunteer days / prop-bono hours / materials / projects. | 10 Volunteering Days (7 every 12 months) | 2026-03-01
Reduction in poverty, health and education inequalities
School/University engagement - site visits for student groups | 2 visits | 2026-03-01
School Engage activities ( delivery of activates within schools to promote construction and the project) | 2 activities | 2026-03-01
Professional development - support teachers, college and university lecturers, connexions and other interested partners to visit site and learn about construction careers / new building processes and techniques. | 1 development day | 2026-03-01
Health and safety talks in primary schools | 1 | 2026-03-01
Protecting the physical environment
Commitments to reducing carbon / recycling / etc. E.g. % of waste recycled through Short Construction Ltd's new waste facility / any other initiatives which could be introduced on this project, | 80% | 2026-03-01
Other - Community Engagement
Community Initiatives - deliver credible, community initiatives that have an impact on local people and the local community area, this can include fun days, coffee mornings, meet the team. | 2 initiatives | 2026-03-01
Contract Launch - engage with community and local partners to offer an engagement session. | 1 | 2026-03-01
News - educate local parties on opportunities and progress to date. | 4 news letters per annum | 2026-03-01
Traffic Light System
Completed or on schedule
Slightly behind schedule. Action required
Significantly behind schedule. Immediate action required.