## External Finishes
MATERIALS & SAMPLE TRACKER
Sample approved
Sample arrived
Architect to confirm
Not needed anymore
Project |  |  |  | 17 Quay Street | [5 empty] | Project No | PO 1024
Report No |  |  |  | 1 | [5 empty] | Date | 2023-11-01
Sample Photo No. | Description | Product Location / Drawing Number | Product Specification |  | Architectural Queries? | Planning Condition (y/n) | Colour | Datasheet (y/n) | Supplier |  |  | Request for Materials | Materials Received | Material provided to architect for approval | Action by | Post review queries | Query Sign off | Sample Approved | Sample Approval Needed By
External Finishes
1 | Brick Tint PCF-166 | All External Brickwork |  |  | Complete | Yes | Anthracite - Mixed Tone | Yes | Remedial Repair |  |  | Complete | Yes, onesite | Yes, approved. | N/A | Complete | Yes |  | MCC
2 | New Curtain Walling GWS-101 | New Curtain Walling Quay Street & Byrom Street a As Drawings 31001, 31002, 31003, 31000 |  |  | Complete | Yes | RAL 7021 | Yes | Supplier: Technal Installer: Red Systems |  |  | Complete | Yes, onesite | Yes, approved. | N/A | Complete | Yes |  | MCC
3 | External Respray PCF-195 | Existing Curtain Walling (including caps, fixed panelling and cills). 4th & 5th Floor - All Elevations. Quay Street L.H Recess 2nd - 5th Byrrom Street Stair Core All Artillery Street Windows |  |  | Complete | Yes | RAL 7021 | Yes | Vanda Coatings |  |  | Complete | Yes, onesite | Yes, approved. | N/A | Complete | Yes |  | MCC
4 | Curtain Walling Spandrels | Existing Spandrels Retained Spandrels To New Window To Match |  |  | Complete | Yes | T.B.C | Yes | Red Systems |  |  | Complete | Yes, onesite | Yes, approved. | N/A | Complete | Yes |  | MCC
5 | Aluminium Capping AMS-106 | Roof and 4th Floor Parapet Edge Detail |  |  | Complete | Yes | RAL 7021 | Yes | Bespoke Fabrication |  |  | Complete | Yes, onesite | Yes, approved. | N/A | Complete | Yes |  | MCC
6 | Aluminium Cill AMS-101 | Wrap to Artillery Street Stone Cills Facing to Stone Detail Lower Section of 4th Floor Parapet |  |  | Complete | Yes | RAL 7021 | Yes | Bespoke Fabrication |  |  | Complete | Yes, onesite | Yes, approved. | N/A | Complete | Yes |  | MCC
7 | Standing Seam Cladding WCS-201 | Quay Street: Full Height Cladding to Projecting Section Of Structure and Recessed Return. (L.H.S Of Elevation) Byrom Street: Full Height Cladding to Projecting Section Of Structure. (L.H.Stair Core Curtain Walling) Detail to underside of 4th Floor Parapet Wall Capping. |  |  | Complete | Yes | RAL 7021 | Yes | Bespoke Fabrication |  |  | Complete | Yes, onesite | Yes, approved. | N/A | Complete | Yes |  | MCC
8 | Roof Plant Screen | Screen Detail To External Perimeter Of Artillery Street & Byrom Street | AL7510 Louver |  | Complete | Yes | RAL 7021 | Yes | ALPS Louvers |  |  | Complete | Yes, onesite | Yes, approved. | N/A | Complete | Yes |  | MCC
9 | Roof Decking | Proposed Decking Solution For Roof Terrace Area | Ryno Classic Composite Decking - Slate |  | Complete | Yes |  | Yes | Ryno |  |  | Complete | Yes, onesite | Yes, approved. | N/A | Complete | Yes |  | MCC
10 | Roof Paving | Proposed Paving Solution For Roof Terrace Area | Ryno Quadro Porcelain Paving - Argento |  | Complete | Yes |  | Yes | Ryno |  |  | Complete | Yes, onesite | Yes, approved. | N/A | Complete | Yes |  | MCC
11 |  |  |  |  | Complete | Yes | [5 empty] | Complete | Yes, onesite | Yes, approved. | N/A | Complete | Yes |  | MCC
Sample approved
Sample arrived
Architect to confirm
Not needed anymore

## Floor Finishes
MATERIALS & SAMPLE TRACKER
Sample approved
Sample arrived
Architect to confirm
Not needed anymore
Project |  |  |  | 17 Quay Street | [5 empty] | Project No | PO 1024
Report No |  |  |  | 1 | [5 empty] | Date | 2023-05-02
Sample Photo No. | Description | Product Location / Drawing Number | Product Specification |  | Architectural Queries? | Planning Condition (y/n) | Colour | Datasheet (y/n) | Supplier |  |  | Request for Materials | Materials Received | Material provided to architect for approval | Action by | Post review queries | Query Sign off | Sample Approved | Sample Approval Needed By
Floor Finishes
1 | Ceramic Tiling FFS-201 | G.F Entrance Tiles. | Domus Narvik DAFN 04 1200x600x9mm Natural Grip Rectified. |  |  |  | DAFN 04 |  | Domus
2 | Ceramic Tiling FFS-202 | W.C Floor Tiles. | Domus Narvik DAFN 03 1200x600x9mm Natural Grip Rectified. |  |  |  | DAFN 03 |  | Domus
3 | Ceramic Skirting | W.C Skirting Tiles. | Domus Narvik DAFN 03 600x900x9mm Natural Grip Rectified. |  |  |  | DAFN 03 |  | Domus
4 | Entrance Matting FSS-514 | Entrance | Forbo Nuway Tuftiguard HD, Plain Inset,17mm depth Aluminium Scraper Bar - Silver Wiper - Rubber Grey/black/Coloured? Colour Black PPC Alumnium Frame |  |  |  | Black/Aluminium |  | Forbo
5 | Vinyl FSS-611 | Staircases Lobbies Basement Drying Room | Forbo Marmoleum Real 3032 Mist Grey 2.5mm |  |  |  | Mist Grey |  | Forbo
6 | Stair Nosing FFE-801 | Staircases | Gradus Xtra Grip T.B.C |  |  |  | T.B.C |  | T.B.C
7 | Carpet F17 | Business Lounge Meeting Room As drawing - 40006 | Interface Dolomite Carpet Tile 500x500mm Ref - T.B.C |  |  |  | RAL 7021 | No
8 | Concrete Paint PCF-181 | Car Park | Two- Pack Epoxy Floor Paint - Mid Sheen - T.B.C
9 | Line Marking Paint PCF-186 | Car Park | Solvent Based Linemarking Paint - T.B.C
10
Sample approved
Sample arrived
Architect to confirm
Not needed anymore

## Wall Finishes
MATERIALS & SAMPLE TRACKER
Sample approved
Sample arrived
Architect to confirm
Not needed anymore
Project |  |  |  | 17 Quay Street | [5 empty] | Project No | PO 1024
Report No |  |  |  | 1 | [5 empty] | Date | 2023-05-02
Sample Photo No. | Description | Product Location / Drawing Number | Product Specification |  | Architectural Queries? | Planning Condition (y/n) | Colour | Datasheet (y/n) | Supplier |  |  | Request for Materials | Materials Received | Material provided to architect for approval | Action by | Post review queries | Query Sign off | Sample Approved | Sample Approval Needed By
Wall Finishes
1 | Ceramic Tiling ILS-402 | W.C Wall Tiles. | Domus Narvik DAFN 02 1200x600x9mm Natural Grip Rectified. |  |  |  | DAFN 02 |  | Domus
2 | Tile Trim | W.C Wall Tiles. | Genesis 10mm x 12mm Box Tile Trim |  |  |  | DAFN 02 |  | Genesis
3 | Paint Finish PFC-101 | General Wall Finishes | T.B.C | [5 empty] | T.B.C
4 | Paint Finish PFC-102 | General Wall Finishes | T.B.C | [5 empty] | T.B.C
5 | Paint Finish PFC-103 | General Wall Finishes | T.B.C | [5 empty] | T.B.C
6 | Skirting Finish PCF-111 | General Wall Finishes | Skirting Finish - Satinwood RAL 9005 - Jet Black |  |  |  | RAL 9005 |  | T.B.C
7 | Skirting Finish PCF-111 | General Wall Finishes | Skirting Finish - Satinwood RAL 9010 - Pure White |  |  |  | RAL 9010 |  | T.B.C
8
9
10
Sample approved
Sample arrived
Architect to confirm
Not needed anymore

## Ceiling Finishes
MATERIALS & SAMPLE TRACKER
Sample approved
Sample arrived
Architect to confirm
Not needed anymore
Project |  |  |  | 17 Quay Street | [5 empty] | Project No | PO 1024
Report No |  |  |  | 1 | [5 empty] | Date | 2023-05-02
Sample Photo No. | Description | Product Location / Drawing Number | Product Specification |  | Architectural Queries? | Planning Condition (y/n) | Colour | Datasheet (y/n) | Supplier |  |  | Request for Materials | Materials Received | Material provided to architect for approval | Action by | Post review queries | Query Sign off | Sample Approved | Sample Approval Needed By
Ceiling Finishes
1 | Ceiling Spray | Structural Soffit G.F- 5th | Structural Soffit Sprayed RAL 7046 (Telegrey 2) |  |  |  | RAL 7046 (Telegrey 2)
2 | Services Spray | Exposed Services G.F- 5th | Exposed Services - RAL 7046 (Telegrey 2) |  |  |  | RAL 7046 (Telegrey 2)
3 | MF Ceilings & Bulkheads | Floor Infills to Main Floor Plate G.F- 5th Perimeter Bulkheads G.F- 5th | MF Ceilings & Bulkheads - RAL 7046 (Telegrey 2) |  |  |  | RAL 7046 (Telegrey 2)
4 | MF Ceilings & Bulkheads | Staircores Basement - Roof | Staircore Ceiling Finish -
5 | MF Ceilings & Bulkheads | W.C, Showers, W.C Lobbies Basement - 5th | W.C, Showers, W.C Lobbies Finish -
6
7
8
9
10
Sample approved
Sample arrived
Architect to confirm
Not needed anymore

## Doors & Joinery
MATERIALS & SAMPLE TRACKER
Sample approved
Sample arrived
Architect to confirm
Not needed anymore
Project |  |  |  | 17 Quay Street | [5 empty] | Project No | PO 1024
Report No |  |  |  | 1 | [5 empty] | Date | 2023-05-02
Sample Photo No. | Description | Product Location / Drawing Number | Product Specification |  | Architectural Queries? | Planning Condition (y/n) | Colour | Datasheet (y/n) | Supplier |  |  | Request for Materials | Materials Received | Material provided to architect for approval | Action by | Post review queries | Query Sign off | Sample Approved | Sample Approval Needed By
Doors & Joinery
1 | Veneered Doors | W.C & Lobbies & Circulation All Floors | Door Leaf: Quater Cut, European Oak Veneer, Black, Clear Lacquer Finish (facings, edgings, beads) |  |  |  | Matt Black |  | CNM Joinery
2 | Painted Doors | Riser Doors All Floors | Door Leaf: Paint Grade Door Decorated Satinwood RAL 9010 - Pure White |  |  |  | RAL 9010 - Pure White |  | CNM Joinery
3 | Steel Doors | Comms & Bin Store Doors Basement | FD60 doors, powdercoated RAL 9005 Standard lever handle, Sash lock (keyed alike) with euro cylinder (key/key). Door closer to all leaves. Flush bolts to passive doors. |  |  |  | RAL 9006 |  | Latham
4 | Shower Lockers, Benches & Coat Rails | Basement Shower Area | Formica Classic Wenge F8851 LNW - 13mm Solid grade laminate Locker Facings, Bench Seat, Coat Rail Frame: Tubular steel support legs Powdercoated RAL 9005 |  |  |  | Classic Wenge F8851 |  | T.B.S Amwell
5 | Drying Room Benches & Coat Rails | Basement Drying Room | Formica Fog F7961 MAT - 13mm Solid grade laminate Bench Seat, Coat Rail Bench Frame: Tubular steel support legs Powdercoated RAL 9005 Hooks: Hat and coat hook Powdercoated RAL 9005 |  |  |  | Fog F7961 MAT |  | T.B.S Amwell
6
7
8
9
10
Sample approved
Sample arrived
Architect to confirm
Not needed anymore

## Sanitaryware
MATERIALS & SAMPLE TRACKER
Sample approved
Sample arrived
Architect to confirm
Not needed anymore
Project |  |  |  | 17 Quay Street | [5 empty] | Project No | PO 1024
Report No |  |  |  | 1 | [5 empty] | Date | 2023-05-02
Sample Photo No. | Description | Product Location / Drawing Number | Product Specification |  | Architectural Queries? | Planning Condition (y/n) | Colour | Datasheet (y/n) | Supplier |  |  | Request for Materials | Materials Received | Material provided to architect for approval | Action by | Post review queries | Query Sign off | Sample Approved | Sample Approval Needed By
W/C Saniatary Ware
1 | Toilet Seat & Cover | Standard WC Ambulant WC Shower WC | Duravit - 2577090000 Toilet WM 540 mm D-Neo white washdown rimless Durafix incl. Duravit - 0021690000 Seat and cover D-Neo removable white sst-hinges with SoftClosure |  |  |  | White | yes | Neville Lumb
2 | WC Pan Support Frame | Standard WC Ambulant WC Shower WC | TD Dudley - 325685 Illusion A Height Adj Wall hung Wc pan Support Frame |  |  |  | N/A | yes | Neville Lumb
3 | Flush Plate | Standard WC Ambulant WC Shower WC | Tyde - 330264 WAVE S3 Electronic Flush Plate |  |  |  | Black | yes | Neville Lumb
4 | Toilet Brush | Standard WC Ambulant WC Shower WC | Crosswater - PRO025M MPro Wall Toilet Brush Matt Black |  |  |  | Matt Black |  | Neville Lumb
5 | Robe Hok | Standard WC Abulant WC Shower WC Shower Room | Crosswater - PRO021M MPro Single Robe Hook Matt Black |  |  |  | Matt Black | yes | Neville Lumb
6 | Toilet Roll Holder | Standard WC Abulant WC Shower WC | Crosswater - PRO029M MPro Toilet Roll Holder Matt Black |  |  |  | Matt Black | yes | Neville Lumb
7 | Tap | Standard WC Abulant WC Shower WC Shower Room | Tyde - 327969 Electroflo Horizon Touch-Free Tap Wall Mounted Mains Op Matt Black Finish |  |  |  | Matt Black | yes | Neville Lumb
8 | Soap Dispenser | Standard WC Abulant WC Shower WC Shower Room | Crosswater PRO011C Mpro Soap Dispenser Wall Mounted Matt Black (Bespoke) |  |  |  | Matt Black | yes | Neville Lumb
9 | Bottle Trap | Standard WC Abulant WC Shower WC | Tyde - 368291 1 1/4" x 3" seal modern style black brass bottle trap with 35mm x 400mm extension tube & modern style wall flange |  |  |  | Black Brass | Yes | Neville Lumb
10 | Hand Dryer | Standard WC Abulant WC Shower WC | Velair - VAF4003 F4 Eco Hand Dryer Matte Black |  |  |  | Matt Black | Yes | Neville Lumb
11 | Grab Rail | Ambulant WC | Nymas - 311462/MB Luxury grab rail straight stainless steel concealed fixings 620mm matt black (RAL 9011) |  |  |  | Matt Black | Yes | Neville Lumb
12 | Shower | Shower WC Shower Room | Crosswater - GTLPRO1510M Gtl/One Box One Box Showering - MPro Bundle 1510 Matt Black |  |  |  | Matt Black | Yes | Neville Lumb
13 | Shower Tray | Shower WC Shower Room | BetteUltra - 1680 AS 120x80x3.5 BetteUltra - B50-3049 Foot-System For Shower Tray 1200x800mm BetteUltra - B523-000 AX Shower Waste Bettesolid 50?, 0.6l/s white GB |  |  |  | Matt or Gloss? White ? | Yes | Neville Lumb
14 | Shower Enclosure | Shower WC | Roxor - SQHD80BP Hinged Door 800x1850mnm - Matt Black |  |  |  | Matt Black | Yes | Neville Lumb
15 | Doc M Pack | Disabled WC | Nymas - NY03-DM-13202-MB Premium Rimless Right Handed Luxury close coupled Doc M toilet pack TMV3 tap matt black |  |  |  | Matt Black Fitiings? | Yes | Neville Lumb
16 | Shower Enclosure | Shower Room | AHI14MB - Merlyn Arysto Sleek Hinge Door & Inline Panel - Matt Black |  |  |  | Matt Black | Yes | Neville Lumb
17 | Wall Mounted Basin | Standard WC Abulant WC Shower WC | T.B.C
18 | Basin Waste | Standard WC Abulant WC Shower WC | T.B.C
18 | W.C Cistern Shelf | Standard WC Abulant WC Shower WC | Bespoke Solid Surface Cistern Shelf Durasein PM206 Nocturn |  |  |  | PM206 Nocturn Black | Yes | Qubicle
18 | Vanity Tops | Basement Shower Area | Bespoke Solid Surface Vanity Durasein PAW 022 Meteor shower |  |  |  | PAW 022 Meteor shower | Yes | Qubicle
18 | Hair Dryer Tops | Basement Shower Area | Bespoke Solid Surface Hair Dryer Tops Durasein PAW 022 Meteor shower |  |  |  | PAW 022 Meteor shower | Yes | Qubicle
Sample approved
Sample arrived
Architect to confirm
Not needed anymore