## Sheet 1
Ref | Feature | Description | Removed / Retained | Methodology | Sample Date
GENERAL ITEMS
G1 | Columns & beam shoes | Painted cast iron columns and varying types of primary beam support shoes | Retained | Existing paint to be lightly removed and new intumescent paint finish to be applied | 2023-11-24
G2 | Primary beams | Painted 400 x 200mm timber beams spanning full width | Retained & fully revealed | Existing paint to be lightly removed and new clear intumescent coating to be applied. Beam ends to be replaced where rotten to be confirmed following strip out works | 2023-11-24
G3 | Joists | 175 x 65mm timber joists at 400mm centres spanning between primary beams | Retained & exposed | Joists to be lightly sanded and new clear intumescent coating to be applied | 2023-11-24
G4 | Timber board soffits | Two layers of timber planks spanning across joists forming floor deck above | Retained & exposed | Boards to be lightly sanded and new clear intumescent coating to be applied | 2023-11-24
G6 | Internal face of external walls | Exposed brickwork with paint finish with small areas of plasterboard dry lining | Retained & cleaned of paint | Existing paint finish to be lightly removed and brickwork left uncoated and exposed. Internal face of east gable to be dry lined. | 2023-11-24
G11 | North east stair | Painted brickwork walls to stair enclosure with stair construction of timber joists overlaid with timber board flooring and vinyl covering. Underside of boards form soffit. | Retained & cleaned of paint | Existing paint finish to be lightly removed and brickwork left uncoated and exposed. Vinyl floor covering to be removed and replaced. Boards and joists to be lightly cleaned of paint and fully exposed. | 2023-11-24
G12 | North west stair | Painted brickwork walls to stair enclosure with stair construction of concrete flights with paint finish to exposed concrete soffits. | Retained & cleaned of paint | Existing paint finish to be lightly removed and brickwork left uncoated and exposed. Concrete elements to be cleaned of paint and coated with clear dust sealer. | 2023-11-24
GROUND FLOOR
05 | External doors to west gable | Large, painted timber doors with inset personnel door and steel sheet overlay to external face | Retained, cleaned & exposed | Steel overlay sheeting to be removed externally. doors to be stripped of paint, sanded and coated with clear preservative treatment. ironmongery retained and repainted | 2023-11-24
07 | Floor slab | Concrete ground floor slab | Retained and left exposed | Existing slab to be diamond polished in reception area and coated with clear dust dealer. Extent of works to remaining ground floor to be confirmed. | 2023-11-24
08 | Brickwork jambs to external doors on Baird Street | Poorly formed brickwork jambs to door openings following prior alterations. Original openings infilled with flush timber doors and timber/brick over panels. | Brickwork retained and made good. Infills removed | Brick jambs at low level to be reformed to match existing profile above using bricks reclaimed from alteration. Non original infills to overall openings to be removed. | 2023-11-24
FIRST FLOOR
13 | Floor | Asphalt topping to timber boards | Retained and covered | Existing asphalt to be filled and levelled and new micro cement topping applied over. | 2023-11-24
SECOND FLOOR
THIRD FLOOR
34 | Sliding door to east gable | Steel framed door and overhead track | Retained | Door and running gear to be stripped and repainted. | 2023-11-24
FOURTH FLOOR
41 | Roof trusses | Primary timber trusses with hanging rods | Retained & cleaned | Existing paint to be lightly removed and new clear intumescent coating to be applied. | 2023-11-24
42 | Purlins | 100 x 225mm timber purlins | Generally retained. Upper purlin to south roof slope to be removed | Purlins to be lightly cleaned of paint | 2023-11-24
44 | Ceiling lining | Painted timber strip ceiling fixed to underside of rafters | Retained | Boards to be cleaned in situ, removed & then reinstated over new insulation fixed to underside of rafters | 2023-11-24
ROOF