## Calculation Cover Sheet
Calculation Cover Sheet
Project Title | [7 empty] | Project Number
Project Olympus | [7 empty] | 1036095
Calculation Section/ System | [7 empty] | Calculation Group/ System
123456789ABC
Quality Control
Cover sheet applicable to calculations sheets:
Sheet numbers |  | By | Date | Calculation Section/ System
Calculation Synopsis/ Objective
Key Assumptions, Criteria & References. |  |  |  |  | Applicable Eurocodes/ British Standards/ Codes of Practice
1 |  |  |  |  | Ref
2 |  |  |  |  | Ref
3 |  |  |  |  | Ref
4 |  |  |  |  | Ref
5 |  |  |  |  | Ref
6 |  |  |  |  | Ref
7 |  |  |  |  | Ref
8 |  |  |  |  | Ref
9 |  |  |  |  | Ref
10
Drawings - list all drawings that the calculations are based on
Drawing No. |  | Drawing Title |  |  | Drawing No | Drawing Title
Revision History
Revision | By | Date | Revision Description

## How-to Guide
When the file is opened the first thing you should see is a collapsed version of the 4 risk hazards. Once you have 'Enabled Editing' you should see the + signs (highlighted in green) that would allow you to expand these hazards and its risk descriptions. We would like the design team to provide comments for all 4 sections.
The design team should input their comments of the risk description in Column S (highlighted in green and with yellow arrow). Column R presents example mitigation options that could potentially be implemented into the current design - a brainstorm point if you don't know what mitigation measures for that risk description should look like.
Column E-H will show the respective risk descriptions each design discipline should respond to - however, as some are intersected, would be worth to check all rows to see if anything related to your discipline can be added.

## REQUIRE DESIGN TEAM INPUT
# | Climate Change Impact | Project Component | Design Discipline |  |  |  | Risk Description |  | First Risk Rating | [5 empty] | Example Mitigation Options | Migitation Measures |  | Second Risk Rating | [5 empty] | Future Mitigation Options (2050+) | Status |  | Risk Rating | [5 empty] | Residual Risk to Project
|  |  | Architecture/ Structures | Building Services | Civils & Infrastructure | Landscape & Ecology |  | Score |  |  | Consequence |  |  |  | This lists out the mitigation options that the design team could currently implement. | Design Team to confirm the current mitigation measures incorporated in the project. | Score |  |  | Consequence |  |  |  | This includes the mitigation options that Cundall has considered and reviewed, which are recommended to the design team. | Design Team / Cundall to confirm the reviewed mitigation options. | Score |  |  | Consequence
[11 empty] | 1 | 2 | 3 | 4 | [5 empty] | 1 | 2 | 3 | 4 | [5 empty] | 1 | 2 | 3 | 4
Increasing Average / Maximum Temperatures
1 | Increasing average / maximum temperatures | Public Realm | [X] |  |  | [X] | • Overheating of public spaces making them uncomfortable for users • Overheating and humidity of outdoor furniture (i.e. benches) and fixtures (handrails, bike racks) making them unable to be used for their intended purposes • Urban heat island impacts causing increase in temperatures and day-time temperatures | 6 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Incorporation of green infrastructure at the site providing localised shading for public realm users • Cool roofs and green roofs being considered on the project | Extensive tree planting and ornamental planting throughout public realm will lower air temperatures, helping to combat the 'urban heat island' effect and provide areas of shade in hot weather. Seating and benches to have timber tops to maintain comfortable seating temperatures in hot weather. Handrails and bike racks to be stainless steel specification as per BS 8300 recommendations. | 3 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Consideration of additional shade structures at the site. These can be both permanent and/or temporary structures which can be implemented when required. • Design mitigation - Installation of water fountains |  | 3 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
2 |  |  |  | [X] |  |  | • Regional power outages resulting in temporary disruption to street lighting. | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Consider installing solar powered emergency lighting at access points into and out of the site | Emergency lighting for the building will be standard battery backed emergency lighting with 3 hours duration. There are currently no plans to provide solar powered emergency Street lighting. | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project. |  | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
3 |  |  |  |  | [X] |  | • Access roads and surfaces such as asphalt can become susceptible to permanent deformation | 6 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Designing hardscaping based on industry standards and taking account of future weatherfiles and predicted increases in surface temperatures • Incorporating tree planting which will shade areas of hard landscaping and reduce heating | Subbase to be detailed for proposed finished, use, and loading in accordance with all relevant standards and codes. | 3 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Research around which materials would work best at future forecasted temperatures is recommended. • Soft landscaping and natural materials can be used to help mitigate increasing temperatures. • Routine inspection and maintenance of surfacing and proactive repairs |  | 3 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Confident that risks are managed through appropriate designing and ongoing operational management. • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
4 | [5 empty] | [X] | • Water shortages could lead to landscape vegetation loss and die back • Extended drought to the soils may impede their availability to absorb any flash flood or rainfall events leading to flooding following summer storms • Non native planting susceptible to predators and pests • New pests and diseases in wake of higher temperatures and migration • Increase in native drought-tolerant species • Increased dry winds may impact/cause damage to species coming in | 9 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Ecological assessment to inform landscaping strategy and the prioritisation of native vs drought tolerant planting • On-site attenuation to capture water during flash flooding and high rainfall events | Ecological input to inform landscaping strategy and the prioritisation of native vs drought tolerant planting Tree and ornamental planting to incorporate variety of native species alongside non native varieties. Proposals avoid large planting areas with monoculture of speices. All planting types to include range of varieties to limit the impact and spread of diseases. Planting selection to take into account both periods of drought and wet weather conditions to ensure suitable establishment and longevity. A hybrid drainage strategy incuding suds features and attenuation tanks is proposed to limit any risk from flash flooding. Raingardens incorporated as part of a sustainable drainage system. These will provide on-site attenuation in the case of high rainfall events or flash flooding. Planting to include species capable of withstanding periods of drought as well as periods of flooding. | 9 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Consider installation of a secondary irrigation system for landscaped areas to be used during high temperature events and any resulting drought periods |  | 9 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
5 |  | Building | [X] |  |  |  | • Thermal expansion of building materials • Decreased service life of building components and accelerated deterioration of the façade through UV exposure • Increased UV exposure may result in deterioration of flexible elements (e.g. sealants) | 6 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Material specification should consider future increased in mean and maximum temperatures • The building should incorporate both internal and externals shading structures which will protect materials and occupants from UV exposure • Overheating assessments to be done differently according to building type: Plot 10a will align with commercial building regulations and Plot 10b will align with residential building regulations. • Ventilation strategies to be done differently: consideration of passive cooling/ventilation, openable windows | Material specification will consider climate change risks. The design has been progressed with the aid of daylighting assessment tools to ensure optimal lighting levels and as well as minimising overheating. provide sufficient movement joints in materials susceptible to thermal expansion building blocks are mostly brick with exception of curtain walling internal and external shading horizontally and verticlaly to protect from UV exposure openable windows on all floors In detailed design, requirements for movement joints to accomodate thermal expansion in the primary structure with be reviewed. | 3 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project. |  | 3 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
6 |  |  |  | [X] |  |  | • Extended periods of hot weather can lead to regional disruptions to electrical distribution and results in power outages for buildings onsite • HVAC systems running at maximum capacity for longer resulting in additional wear and tear and increasing the likelihood of mechanical failure and maintenance works. • Overheating of elevator controllers / main distribution transformer • Future utility costs increasing • Comfort cooling system may not have sufficient capacity to maintain comfort conditions and cause heat stress for occupants • Additional cooling capacity to meet increasing temperatures contribute to increased demand on buildings electrical infrastructure LIFE SCIENCES AREA High temperatures resulting in temperature controlled areas operating outside of required temperature thresholds Chemicals being stored outside of their optimum storage temperature resulting in wastage Temperature, humidity and pressure sensitive equipment operating outside of thresholds resulting in inaccuracies in results, premature degradation and replacement of equipment. | 6 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Consideration that electrical infrastructure has sufficient capacity to accommodate the higher peak cooling loads. • Promote passive cooling techniques in the building design to reduce heat gains and load on systems. • DfP modelling to optimise efficiency of operation: natural ventilation, passive cooling techniques, openable windows and thermal fabric. • Ensure both thermal and energy analysis of the building considers the impact of climate change on the analysis. BCO recommends designs consider medium emissions scenario (RCP4.5) as a minimum. • Over typical 15-20 year service life of cooling system (Max temperature of 1-1.5°C above historic levels) • Install sufficient backup generation to accommodate critical lab operations | Transformers are sized with 20% spare capacity over the current maximum demand calculation. There is 20% additional capacity in the HVAC systems/ASHP beyond the current estimated requirements. The building energy strategy takes a fabric first approack to reduce energy usage. All, thermal and energy modelling is being carried out is using the latest CIBSE Climate data. - with current and future weather scenarios being use as required by BREEAM NC V6, HEA04, ENE 01 and ENE05 Credits. As a minimum the following weather information for Manchester is to be used for all Weather under a climate change scenario (DSY 2020 Emissions Scenario: High (A1F1), 50th percentile DSY2 and DSY 3). Back-up generation for client operations forms part of the client fit out. Spatial allowance has been made at roof level for client generators. | 4 | Likelihood | 1 | 1 | 2 | 3 | 4 | Consider the implementation of demand response measures to minimise stress on local infrastructure: • Smart controls • Natural ventilation • PV and storage capacity Consider space allowance for larger capacity cooling system: • 2.6°C higher (RCP8.5, 2050, Central) • 5.0°C higher (RCP8.5, 2080, Central) |  | 4 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Protect against future utility cost changes with energy efficiency measures and onsite energy systems
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
7 |  |  |  |  | [X] |  | N/A |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
8 | [5 empty] | [X] | • Roof top and green wall vegetation may brown and die, leading to increased irrigation costs and/or replacement. | 9 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Ecological assessment to inform landscaping strategy and the prioritisation of native vs drought tolerant planting • On-site attenuation to capture water during flash flooding and high rainfall events | Planting to roof terrace to incorporate species tolerant to periods of drought. No green walls currently proposed as part of the scheme. | 9 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Consider installation of a secondary irrigation system for landscaped areas to be used during high temperature events and any resulting drought periods |  | 9 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
Intense Rainfall Events
9 | Intense rainfall events | Public Realm | [X] |  |  |  | • Overwhelming of building guttering and drainage system could result in water falling into access routes and public realm spaces. | 6 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Onsite drainage and guttering to be designed using future weather files or with adequate space to easily upsize system should it be required in the future • Consideration of blue-roof to hold a greater volume of water before discharging | Below ground drainage design will be undertaken in accordance with policy for the area indicates that surface water runoff should be restricted to match the greenfield rate (Qbar) of 2.5 l/s. Attenuation requirements to restrict the run off to the public network will be calculated using the required storm rate with the required allowance for climate change. SUDs measures to be included, including permeable paving. | 4 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Guttering on site should be regularly checked and maintained to avoid blockages and water backups |  | 4 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
10 |  |  |  | [X] |  |  | N/A |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
11 |  |  |  |  | [X] |  | • Changes in peak rainfall events could increase the volume of surface water runoff leading to water overflowing into access roads | 4 | Likelihood | 1 | 1 | 2 | 3 | 4 | • High water table at the site makes large scale infiltration unfeasible • On-site rain gardens will be attenuation features with slow water release into a piped drainage system. • Surface water runoff from the Project should be managed in line with national and local policy requirements through the implementation of the surface water drainage strategy which would utilise SUDS features and ensure no detrimental effects on site or to neighbouring land. | Below ground drainage design will be undertaken in accordance with policy for the area indicates that surface water runoff should be restricted to match the greenfield rate (Qbar) of 2.5 l/s. Attenuation requirements to restrict the run off to the public network will be calculated using the required storm rate with the required allowance for climate change. SUDs measures to be included, including permeable paving. | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Emergency management procedure will need to be developed for the site and included in a Operation and Maintenance manual produced for the scheme. |  | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
12 | [5 empty] | [X] | • Changes in peak rainfall events could increase the volume of surface water runoff leading to water overflowing into areas of landscaping and waterlogging of soils resulting in damage to planting onsite. | 3 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Drainage strategy design to incorporate both infiltration and attenuation. • On-site rain gardens will be attenuation features with slow water release into a piped drainage system and reducing the risk of waterlogging of soils. | Raingardens to attenuate surface water run-off Incorporation of planted raingardens as part of a sustainable drainage system to function as part of the site's overall drainage strategy. These will provide on-site attenuation in the case of high rainfall events or flash flooding. Planting to include species capable of withstanding periods of drought as well as periods of flooding. Soil specification to include free draining sub soils and a layer of attenuation to ensure surface water is allowed to permeate through and doesn't saturate the topsoil layer. | 3 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project. |  | 3 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
13 |  | Building | [X] |  |  |  | • Drainage and guttering overwhelmed by intense rainfall events resulting in water ingress into building envelope | 6 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Onsite drainage and guttering to be designed using future weather files or with adequate space to easily upsize system should it be required in the future | Below ground drainage design will be undertaken in accordance with policy for the area indicates that surface water runoff should be restricted to match the greenfield rate (Qbar) of 2.5 l/s. Attenuation requirements to restrict the run off to the public network will be calculated using the required storm rate with the required allowance for climate change. SUDs measures to be included, including permeable paving. | 4 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Guttering on site should be regularly checked and maintained to avoid blockages and water backups • Flood detection system to be installed in business critical areas of the buildings |  | 4 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
14 |  |  |  | [X] |  |  | • Roof top equipment damaged by heavy rainfall events or ponding of water on rooftop • Heavy rainfall and regional flooding could result in ingress into ground floor and basement areas resulting in damage to mechanical / electrical equipment, floors, finishes and furniture | 8 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Onsite drainage and guttering to be designed using future weather files or with adequate space to easily upsize system should it be required in the future • Specification of ground floor and basement equipment which is resilient to water ingress or can be easily repaired and replaced if damaged by flooding. | Falls on roofs to be detail by architect to avoid ponding of water. Site is in Flood Zone 2 and flood risk assessment is being undertaken and measures to control flooding incorporated into scheme (none anticipated to be required over normal building measures). | 6 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Guttering on site should be regularly checked and maintained to avoid blockages and water backups • Flood detection system to be installed in business critical areas of the buildings |  | 6 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
15 |  |  |  |  | [X] |  | • Overwhelming of building guttering and drainage system could result in water falling into access routes and public realm spaces overwhelming local drainage systems. | 4 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Onsite drainage and guttering to be designed using future weather files or with adequate space to easily upsize system should it be required in the future • Roof gardens for better rainwater harvesting | Below ground drainage design will be undertaken in accordance with policy for the area indicates that surface water runoff should be restricted to match the greenfield rate (Qbar) of 2.5 l/s. Attenuation requirements to restrict the run off to the public network will be calculated using the required storm rate with the required allowance for climate change. SUDs measures to be included, including permeable paving. | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Guttering on site should be regularly checked and maintained to avoid blockages and water backups |  | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
16 | [5 empty] | [X] | • Waterlogging of landscaped areas on the rooftop. | 4 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Onsite landscaping should be designed to be climate appropriate and have sufficient drainage to accommodate high rainfall events | Ornamental planting to roof terrace to utilise lightweight, free draining soils to minimise waterlogging. Drainage board and egg crate systems used to store limited amounts of rainwater but allow excessive amounts to freely discharge. | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project. |  | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
Flooding
17 | Flooding | Public Realm | [X] |  |  |  | N/A |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
18 |  |  |  | [X] |  |  | N/A |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
19 |  |  |  |  | [X] |  | • Flooding and onsite water ponding resulting in manholes and service trenches being unable to be accessed. | 3 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Depths of service trenches and power supply routes to consider current and future ground water levels and accessibility during flooding events. • Consider that surrounding buildings use rainwater storage or community rainwater storage to reduce surface water runoff. The public realm can use SUDS and soft landscaping where possible, and ideally involve local stakeholders to generate ownership of this community area. | Below ground drainage design will be undertaken in accordance with policy for the area indicates that surface water runoff should be restricted to match the greenfield rate (Qbar) of 2.5 l/s. Attenuation requirements to restrict the run off to the public network will be calculated using the required storm rate with the required allowance for climate change. SUDs measures to be included, including permeable paving. | 3 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project. |  | 3 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
20 | [5 empty] | [X] | • Waterlogging and surface ponding of landscaped areas. | 3 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Current design includes onsite water attenuation, landscaping and SUDS. | Current design includes onsite water attenuation, landscaping and SUDS. Incorporation of planted raingardens as part of a sustainable drainage system to function as part of the site's overall drainage strategy. These will provide on-site attenuation in the case of high rainfall events or flash flooding. Planting to include species capable of withstanding periods of drought as well as periods of flooding. | 3 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Specify planting to be climate tolerant and able to withstand long hot summers and wet winters with periodic high volume precipitation events |  | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
21 |  | Building | [X] |  |  | x | • Accessibility into the building may be restricted and routes to the science park disrupted during flooding | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Provide alternative transport routes to the site and emergency exit routes | External levels strategy and design directs surface water flows away from entrances and the immediate building curtilage, allowing safe access and egress from the building entrances. | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Flooding may occur rapidly and warning systems of local conditions need to be reported to occupiers |  | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
22 |  |  |  | [X] |  |  | • Heavy rainfall and regional flooding could result in ingress into ground floor and basement areas resulting in damage to mechanical / electrical equipment, floors, finishes and furniture | 3 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Onsite drainage and guttering to be designed using future weather files or with adequate space to easily upsize system should it be required in the future • Specification of ground floor and basement equipment which is resilient to water ingress or can be easily repaired and replaced if damaged by flooding. | We are awaiting the flood risk assessment, but our understanding is that the building is above the 100 year flood level. Electrical equipment will be on plinths at ground floor level or on plant supports on the roof to raise them ahove slab and roof levels. | 3 | Likelihood | 1 | 1 | 2 | 3 | 4 | • OM - Guttering on site should be regularly checked and maintained to avoid blockages and water backups • Flood detection system to be installed in business critical areas of the buildings s |  | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
23 |  |  |  |  | [X] |  | • Foundations and substructure not designed to accommodate changing weather and groundwater conditions | 4 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Substructure design to model water table using future weather files and upsize foundation and pile design accordingly | Pile design to be optimised to accommodate for groundwater conditions Substructure design to be undertaken based on site investigations and confirmation of groundwater levels. Assessment of potential climate change implications to be reviewed as part of detailed design. | 4 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Structural integrity of foundations to be reviewed for changes in soil conditions from dry to saturation. |  | 4 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Residual risk within acceptable risk threshold for the project.
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
24 | [5 empty] | [X] | N/A |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
Wind
1 | Increasing average / maximum temperatures | Public Realm | [X] |  |  | [X] | • Strong wind in public spaces making them uncomfortable for users. • Non-stationary furniture (chairs, umbrella stands, etc.) blown away by strong wind. | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Wind shelters or screens to protect public realm users • Storage areas to keep furniture indoors safe from wind • Specification for stationary furniture | Extensive tree planting is proposed throughout the public realm offering buffering to prevailing winds. Tree planting positions are staggered to avoid any channelling of winds. All street furniture will be fixed down. | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 |  |  | 1 | Likelihood | 1 | 1 | 2 | 3 | 4
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
2 |  |  |  | [X] |  |  | N/A | 4 | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  | 4 | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  | 4 | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
3 |  |  |  |  | [X] |  | • Regional power outages/shut downs resulting in temporary disruption to street lighting. | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Consider installing wind-powered emergency lighting at access points into and out of the site • UPS installation for emergency lighting in case of power grid outages |  | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 |  |  | 2 | Likelihood | 1 | 1 | 2 | 3 | 4
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
4 | [5 empty] | [X] | • Fallen trees may pose as a safety hazard for passers-by and building users. • Roosting habitats and planting species around site may be harmed by wind or fallen trees as a result of wind. |  | Likelihood | 1 | 1 | 2 | 3 | 4 | • Shelter to be provided for users around buildings • Landscape specification in line with expected wind conditions in lieu of installing equipment in public realm | Detailed management regime will ensure operatives will check tree guying whist roots are establishing a regular intervals and after strong winds. Any damages to planting or habitats will be identifed as part of the management and maintenance of the site. This will be undertaken regularly and will be identified as part of a detailed management and maintenance strategy. |  | Likelihood | 1 | 1 | 2 | 3 | 4 |  |  |  | Likelihood | 1 | 1 | 2 | 3 | 4
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
5 |  | Building | [X] |  |  |  | • Building material resistance to wind resulting in swaying through building, external facade features that may produce nuisance noises due to strong wind, and other features that may affect internal comfort. • Nearby debris (roof shingles, unsecured furniture, branches from fallen trees) picked up by wind may be projected against building envelope and roof equipment (if MEP). Higher likelihood of wear and tear of building materials. | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Shelter to be provided to equipment at roof level • Assessing impacts on internal comfort from wind. | The façade, and specially the elements intended for shading, are fixed and there is a low risk of them being affected by strong wind. MEP equipment at roof (plant area) is to be protected by a screen Stability of the building is provided through the reinforced concrete cores and the detailed structural design will be undertaken to limit sway of the building to acceptable limits in accordance with current structural codes. Wind load calculations will be undertaken to account for potential climate change. | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 |  |  | 2 | Likelihood | 1 | 1 | 2 | 3 | 4
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
6 |  |  |  | [X] |  |  | • Extended periods of wind events can lead to regional disruptions to electrical distribution and results in power outages for buildings onsite • Regional power outages/shutdowns resulting in loss of electrical heating in building. • Roof-mounted equipment to be damaged by strong wind. | 6 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Install sufficient backup generation to accommodate critical operations • UPS installation for emergency lighting in case of power grid outages • Shelter for roof-mounted equipment • Sensitive equipment to be moved down to basement or indoor areas of the building | Backup generation is provided for life safety services. No critical services have been identified by the client. Tenants will be responsible for backup generation to their critical services; spatial allowance has been allowed for this. Emergency llighting is provided by integrated 3 hour battery packs, this will provide the same level of resilience as a central 3 hour battery/UPS system. No sensitive equipment has been located on the roofs. | 6 | Likelihood | 1 | 1 | 2 | 3 | 4 |  |  | 6 | Likelihood | 1 | 1 | 2 | 3 | 4
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
7 |  |  |  |  | [X] |  | N/A |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
8 | [5 empty] | [X] | N/A |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
Snowing / Snowstorms
1 | Increasing average / maximum temperatures | Public Realm | [X] |  |  | [X] | • Snowing in public spaces making them uncomfortable for users • Snow on outdoor furniture (i.e. benches) and fixtures (handrails, bike racks) making them unable to be used for their intended purposes | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Shelter for fixtures • Mats to be placed inside entrance door | Detailed management regime will ensure on site operatives will check surfacing and furniture throughout winter months ensuring they are clear of snow and fit for purpose. Seating to be provided under building canopies to provide areas of sheltered seating. Handrails and bike racks to be stainless steel specification as per BS 8300 recommendations with several under building canopies to ensure year round use. | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 |  |  | 1 | Likelihood | 1 | 1 | 2 | 3 | 4
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
2 |  |  |  | [X] |  |  | • Regional power outages/shut downs resulting in temporary disruption to street lighting. | 4 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Consider installing solar powered emergency lighting at access points into and out of the site | Emergency lighting for the building will be standard battery backed emergency lighting with 3 hours duration. There are currently no plans to provide solar powered emergency Street lighting. | 4 | Likelihood | 1 | 1 | 2 | 3 | 4 |  |  | 4 | Likelihood | 1 | 1 | 2 | 3 | 4
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
3 |  |  |  |  | [X] |  | • Restricted accessibility of transport. • Surface run off around public realm. | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Designing hardscaping based on industry standards and taking account of future weather files and predicted increases in surface temperatures |  | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 |  |  | 2 | Likelihood | 1 | 1 | 2 | 3 | 4
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
4 | [5 empty] | [X] | N/A |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
5 |  | Building | [X] |  |  |  | • MEP equipment at roof level - accessibility of equipment | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Shelter to be provided to equipment at roof level • Backup generation to be placed inside building to cover for inaccessibility | MEP equipment at roof (plant area) is to be protected by a screen. Access and maintenance strategy is designed with specialist | 2 | Likelihood | 1 | 1 | 2 | 3 | 4 |  |  | 2 | Likelihood | 1 | 1 | 2 | 3 | 4
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
6 |  |  |  | [X] |  |  | • Extended periods of snowfall/storm events can lead to regional disruptions to electrical distribution and results in power outages for buildings onsite • Additional heating capacity to meet increased frequency of cold days contribute to increased demand on building/'s electrical infrastructure. Heating systems running at maximum capacity for longer resulting in additional wear and tear and increasing the likelihood of mechanical failure and maintenance works. • Future utility costs increasing • Comfort heating system may not have sufficient capacity to maintain comfort conditions and cause heat/ventilation stress for occupants • Regional power outages/shutdowns resulting in loss of electrical heating in building. | 6 | Likelihood | 1 | 1 | 2 | 3 | 4 | • Consideration that electrical infrastructure has sufficient capacity to accommodate the higher peak heating loads. • Ensure both thermal and energy analysis of the building considers the impact of climate change on the analysis. BCO recommends designs consider medium emissions scenario (RCP4.5) as a minimum. • Install sufficient backup generation to accommodate critical lab operations | Transformers are sized with 20% spare capacity over the current maximum demand calculation. There is 20% additional capacity in the HVAC systems/ASHP beyond the current estimated requirements. The building energy strategy takes a fabric first approack to reduce energy usage. All, thermal and energy modelling is being carried out is using the latest CIBSE Climate data. - with current and future weather scenarios being use as required by BREEAM NC V6, HEA04, ENE 01 and ENE05 Credits. As a minimum the following weather information for Manchester is to be used for all Weather under a climate change scenario (DSY 2020 Emissions Scenario: High (A1F1), 50th percentile DSY2 and DSY 3). Back-up generation for client operations forms part of the client fit out. Spatial allowance has been made at roof level for client generators. | 6 | Likelihood | 1 | 1 | 2 | 3 | 4 |  |  | 6 | Likelihood | 1 | 1 | 2 | 3 | 4
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
7 |  |  |  |  | [X] |  | N/A |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
8 | [5 empty] | [X] | N/A |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A |  |  | Likelihood | 1 | 1 | 2 | 3 | 4 | N/A
[10 empty] | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8 |  |  |  |  | 2 | 2 | 4 | 6 | 8
[10 empty] | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12 |  |  |  |  | 3 | 3 | 6 | 9 | 12
[10 empty] | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16 |  |  |  |  | 4 | 4 | 8 | 12 | 16
Design team comments here:
Risk Assessment 2
  Secondary Assessment based on Recommendations from Initial Assessment.
Residual Actions
  Final Assessment based on All Recommendations from Cundall and Design Team.
Note on Z39: Yeung, Arwen: no changes

## (data) (hidden)
Risk Reference | Climate Change Impact |  | Responsibl eparty (Civils, land) | Project component (site wide, landscape, off ect) | Consequence
[5 empty] | 1 | Current Mitigation options | Future Mitigation options- 2050+ | Principal Responsibility | 2 | Current Mitigation options | Future Mitigation options- 2050+ | Principal Responsibility | 3
|  |  | Architecture/Structures | Public Realm
|  | [X] | Building Services | Building
Civils & Infrastructure
Landscape & Ecology