## Social Value Plan (TOMs)
Social Value - Client Charter
Project Name Islington Wharf 4
Project Turnover (£M) 21.1
| Social Value Bank ROI |  | 50% | 10571116.47
|  | KPI | IW4 Tender | Actual to date
Workforce |  | Total number of people will be / were working on the development | 500 | 765
|  | Of that total, how many will be / were City of Manchester residents | 150 | 206
|  | Of that total, how many will be / were newly created jobs | 10 | 55
|  | Of those newly created jobs, how many will be / were taken up by City of Manchester residents | 8 | 55
Apprenticeships |  | Total number of apprentices will be / were working on the development | 10 | 26
|  | Total number of weeks these apprentices will be / were working on the development | 140 | 271
|  | Of the total number of apprentices, how many will be / were City of Manchester residents | 5 | 6
|  | Of the total number of apprentices how many will be / were new roles | 1 | 3
|  | Total number of weeks these new apprentices will be / were working on the development | 30 | 63
|  | Of these new apprenticeship roles, how many will be / were taken up by City of Manchester residents | 1 | 2
Subcontractors and suppliers |  | Total number of sub-contactors/suppliers will be / were working on the development | 46 | 63
|  | Of that total, how many will be / were from the City of Manchester | 9 | 5
|  | Number of Meet The Buyer events will be / were held | 1 | Planned | Date to be agreed | Neil Carson
Learning and Employability |  | Number of careers activities that will be/were held in City of Manchester schools | 10 | 10
|  | Number of careers activities will be / were held on site or office for City of Manchester schools | 10 | 5 | 3No planned events have been cancelled by stakeholders
|  | Number of work experience/placements for under 18s City of Manchester residents | 12 | 11
|  | Number of sector insight talks / events / company visits will be / were held for teaching staff of City of Manchester schools | 5 | 4
|  | Number of strategic releationships will be / were developed with a City of Manchester secondary school to help improve curriculum and careers education and advice | 3 | 3
|  | Number of student projects will be / were held with City of Manchester FE College and Universities | 4 | 4
|  | Number of work experience / placements will be / were offered to over 18s City of Manchester residents | 12 | 8
|  | Number of volunteer opportunities for City of Manchester job seekers will be / were offered | 10 | 19
|  | Number of work trials for City of Manchester job seekers will be / were offered | 2 | 2
Working with community organisations |  | Number of community projects will be / were delivered that had skills and employability outcomes for residents | 4 | 2
|  | Number of other community projects will be / were delivered | 6 | 5
Morgan Sindall Added Value |  | Promotional (good news stories) | 10
|  | Local spend (City of Manchester) | 20%
|  | LM3 | 1.85 | 1.97
|  | Job Vacancies Advertised | 20
|  | Inclusion plan in place | Yes
|  | Mental Health First Aiders | 1
|  | CCS Score | 42 | 42
|  | Environmental TBT's | 18
|  | Responsible Timber procured | 100% | 100%
|  | Air Quality Improvement Plan | Gold
|  | Biodiversity Legacy | Silver
|  | Carbon Emissions | TBC
|  | Water Reduction Plan | Gold

## Social Value Plan (hidden)
Social Value - Client Charter
| Project Name |  | Gorton Community Centre
| Performance To Date |  | June 22
| Project Turnover (£M) |  | 19.4
| Social Value Bank ROI |  | 12972033.69 | 67% | Gorton Tender | Actual to date
| Social Value Portal |  | 15898847 | 82%
KPI
North West Construction Hub Targets | Employment & Opportunities | Apprentice Weeks |  | Number | 217 | 150
|  | Training - Work Experience |  | Number | 10 | 41
|  | Training weeks |  | Weeks | 52 | 23
|  | Employment Support | Individuals | Number | 33 | 98
| Environment | Construction Waste Recycled | Diverted from landfill | % | 96% | 99.8%
|  | Construction Waste Intensity | Removed from site | Skips | 100 | 71
| Local Economy and Community | Educational Activities | STEM | Number | 19 | 16
|  |  | Non-STEM | Number | 7 | 0
|  | Community | Beneficiaries | Number | 54 | #REF!
|  |  | Events | Number | 10 | #REF!
|  | Local Workforce | Tier 1 - Gorton | % | 90 | 34%
|  |  | Tier 2 - GM | % |  | 21%
|  |  | Tier 3 - Other | % | 10 | 45%
Morgan Sindall Added Value | Local Economy and Community | Local Spend (To date) | Tier 1 - Gorton | % | 85 | 8%
|  |  | Tier 2 - GM | % |  | 59%
|  |  | Tier 3 - Other | % | 10 | 33%
|  | Promotional (good news stories) |  | Number | 14 | 21
|  | Meet the Buyer |  | Events | 2 | 2
|  | Supply chain school training |  | Sessions | 1
|  | Supply chain | Large | Number | Monitor
|  |  | SME | Number
|  |  | Micro Enterprise | Number
|  | Spend with SME's (To date) |  | % | Monitor
|  | Spend with Micro Enterprises (To date) |  | % | Monitor
|  | LM3 |  |  | 1.85 | 1.99
| Employment & Opportunities | Work Placement (Paid) |  | Number | 1 | 1
|  | Job Vacancies Advertised |  | Number | 20 | 22
|  | Workless job starts |  | Number | 20 | 2
|  | Mentoring | External | Number | 20 | 0
|  |  | Internal | Number | 2 | 0
|  | Inclusion plan in place |  | Yes/No | Yes | Yes
| Safety, Health & Environment | Mental Health First Aiders |  | No. | 1 | 1
|  | CCS Score | Score out of 50 | No. | 42 | 45
|  | SHEQ TBT's |  | No. | 21 | 24
|  | External Environmental Training |  | Person Days | 1 | 1
|  | Responsible Timber procured |  | % | 100% | 100%
|  | Air Quality Improvement Plan |  | Level | Gold | Silver
|  | Biodiversity Legacy |  | Level | Silver | Silver
|  | Carbon Emissions |  | CO2/£100K | TBC | TBC
|  | Water Reduction Plan |  | Level | Gold | Silver

## SV Training opportunties
Employer | Programme | Trade | Level | Experience | Age Group | Gender | Ethnicity | Ward/Tier | Person Weeks | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01
Titan Interior Solutions Ltd | Apprenticeship | PROQUAL Construction Contracting Operations | 6 | Sustained | 25-49 |  |  | GM | 4 | 14 | 2 | 0 | 0 | 0 | 0
Cara Brickwork | Apprenticeship | Bricklayer | 2 |  | 16-24 |  |  | Manchester | 6 | 6 | 18 | 0 | 0 | 0 | 0
Lancashire Tiling | Apprenticeship | Tiling | 2 |  | 16-24 |  |  | Manchester | 12.5 | 12 | 0 | 6 | 8 | 24 | 0
Ameon | Apprenticeship | Electrician | 3 |  | 16-24 |  |  | Manchester | 4 | 2 | 9 | 0 | 0 | 5 | 0
Titan Interior Solutions Ltd | Apprenticeship | Dryliner | 2 |  | 16-24 |  |  | Manchester | 20.75 | 79 | 0 | 4 | 0 | 0 | 0
Ameon | Apprenticeship | Electrician | [5 empty] | UK | 13.75 | 0 | 0 | 0 | 23 | 20 | 12
Ameon | Apprenticeship | [6 empty] | UK | 1.75 | 0 | 0 | 0 | 7 | 0 | 0
Allied Access | Apprenticeship | Scaffolding | 2 |  | 16-24 |  |  | Manchester | 5.25 | 15 | 6 | 0 | 0 | 0 | 0
Axiom Group | Apprenticeship | PROQUAL Construction Management | 6 |  | 25-49 |  |  | GM | 0.75 | 1 | 2 | 0 | 0 | 0 | 0
Heyrods | Apprenticeship | Steel fixing | 2 |  | 25-49 |  |  | GM | 10.25 | 41 | 0 | 0 | 0 | 0 | 0
Wyse Power | Apprenticeship | Electrician | 3 |  | 25-49 |  |  | NW | 0.75 | 3 | 0 | 0 | 0 | 0 | 0
Titan Interiors Solutions Ltd | Apprenticeship |  |  |  | 16-24 |  |  | Manchester | 13.75 | 0 | 0 | 0 | 8 | 28 | 19
Ameon | Apprenticeship | Electrician | 3 |  | 16-24 |  |  | NW | 6 | 24 | 0 | 0 | 0 | 0 | 0
Ameon | Apprenticeship | Electrician | 3 |  | 16-24 |  |  | NW | 34 | 4 | 46 | 13 | 22 | 29 | 22
Ameon | Apprenticeship | Sprinkler | 3 |  | 16-24 |  |  | GM | 5 | 1 | 11 | 3 | 4 | 0 | 1
Cara Brickwork | Apprenticeship | [6 empty] | GM | 9.75 | 0 | 0 | 0 | 20 | 19 | 0
Metclad | Apprenticeship |  |  |  | 25-49 |  |  | GM | 24.75 | 0 | 0 | 0 | 37 | 34 | 28
Titan Interior Solutions Ltd | Apprenticeship | Dryliner | 2 |  | 25-49 |  |  | GM | 11.75 | 5 | 42 | 0 | 0 | 0 | 0
Morgan Sindall | Apprenticeship | Engineer | 6 |  | 16-24 |  |  | NW | 0.75 | 2 | 0 | 0 | 1 | 0 | 0
Ameon | Apprenticeship | Building service engineering | 3 |  | 16-24 |  |  | NW | 0.75 | 1 | 2 | 0 | 0 | 0 | 0
EWS Façade | Apprenticeship | Occupational work supervision | 3 |  | 16-24 |  |  | UK | 1 | 1 | 3 | 0 | 0 | 0 | 0
Allied Access | Apprenticeship | Scaffolding | 2 |  | 16-24 |  |  | GM | 3.5 | 1 | 13 | 0 | 0 | 0 | 0
RW Joinery | Apprenticeship | Joinery |  |  | 16-24 | F | White British | GM | 27.75 | 0 | 56 | 10 | 0 | 24 | 21
Cara Brickwork | Apprenticeship | Bricklayer | 2 |  | 25-49 |  |  | GM | 11.75 | 47 | 0 | 0 | 0 | 0 | 0
Ameon | Apprenticeship | Plumber | 3 |  | 16-24 |  |  | GM | 36.75 | 12 | 83 | 10 | 18 | 22 | 2
Ameon | Apprenticeship | Electrician | 3 |  | 16-24 |  |  | NW | 3.75 | 3 | 12 | 0 | 0 | 0 | 0
Titan | Job start | Dryliner |  | Previously Not in Eduction Employment or Training (NEET) | 16-24 | M | White British | Manchester | 9.75 | 0 | 0 | 0 | 0 | 5 | 34
Bennett Architectural Alumium Solutions Ltd | Paid work placement | [6 empty] | UK | 52.25 | 0 | 0 | 0 | 160 | 28 | 21
Titan Interiors Solutions Ltd | Paid work placement | [6 empty] | GM | 37.25 | 0 | 0 | 0 | 144 | 5 | 0
Titan Interiors Solutions Ltd | Paid work placement | [6 empty] | GM | 39.25 | 0 | 0 | 0 | 152 | 5 | 0
Morgan Sindall | Paid work placement | [6 empty] | Manchester | 12.25 | 0 | 0 | 0 | 49 | 0 | 0
Ameon | Paid work placement | [6 empty] | GM | 5.5 | 0 | 0 | 0 | 22 | 0 | 0
Morgan Sindall | T Level | DSP | [5 empty] | Manchester | 5.25 | 21 | 0 | 0 | 0 | 0 | 0
Morgan Sindall | T Level | DSP | [5 empty] | Manchester | 0.5 | 0 | 0 | 0 | 0 | 2 | 0
Morgan Sindall | T Level | DSP | [5 empty] | Manchester | 1.5 | 2 | 4 | 0 | 0 | 0 | 0
Morgan Sindall | T Level | DSP | [5 empty] | GM | 2.5 | 0 | 0 | 0 | 10 | 0 | 0
Morgan Sindall | T Level | DSP | [5 empty] | Manchester | 1.5 | 0 | 0 | 0 | 6 | 0 | 0
Morgan Sindall | T Level | DSP | [5 empty] | Manchester | 4 | 16 | 0 | 0 | 0 | 0 | 0
Titan | Traineeship | Dryliner |  | Previously Not in Eduction Employment or Training (NEET) | 16-24 | M |  | GM | 3.75 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0
Titan | Traineeship | Dryliner |  | Previously Not in Eduction Employment or Training (NEET) | 16-24 | M | White British | Manchester | 3.75 | 0 | 0 | 0 | 0 | 15 | 0
Metclad | Work Experience | [6 empty] | GM | 17.25 | 0 | 0 | 0 | 14 | 30 | 25
Morgan Sindall | Traineeship | Brick |  | Previously Not in Eduction Employment or Training (NEET) | 16-24 | M | White/British | GM | 3.75 | 0 | 0 | 0 | 0 | 0 | 15
Morgan Sindall | Traineeship | Brick |  | Previously Not in Eduction Employment or Training (NEET) | 16-24 | M | British/African | GM | 3.75 | 0 | 0 | 0 | 0 | 0 | 15
Morgan Sindall | Traineeship | Brick |  | Previously Not in Eduction Employment or Training (NEET) | 16-24 | M | British/African | GM | 3.75 | 0 | 0 | 0 | 0 | 0 | 15
Morgan Sindall | Traineeship | Plasterer |  | Previously Not in Eduction Employment or Training (NEET) | 16-24 | F | British/Asian | GM | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 15
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Apprenticeship |  | 1 | Unemployed for a year or longer | 16-24 | M | White British
| Graduate |  | 2 | Armed forces veterans | 25-49 | F | Asian, Black and other ethnically diverse people
| NVQ |  | 3 | Homeless | 50+ | Prefer Not To Say
| Work Experience |  | 4 | Mothers returning to work
| Kickstart |  | 5 | Survivors of modern slavery
| ILM |  | 6 | Previously Not in Eduction Employment or Training (NEET)
| Job start |  | 7 | 16-25 y.o. care leavers
| Traineeship |  | N/A | 18+ ex offenders
| BTEC |  |  | 18-24 rehabilitating young offenders
| City and Guilds |  |  | Disabled
| HNC |  |  | Armed forces veterans
| HND |  |  | In Education
| T Level |  |  | Sustained
| Paid work placement |  |  | Previously employed with others

## Local stats
Employer | Name | New to the project | Advertised | Trade | Gender | Ethnicity | Ward/Tier | Days on site
Bennett Architectural Aluminium Solutions Ltd | Aaron Tucker | [5 empty] | Manchester
Titan Interior | Adam Dermody | Yes |  |  |  |  | Manchester
Allied Scaffolding | Adam Allcock | [5 empty] | Manchester
Heyrod | adrian skiba | [5 empty] | Manchester
Heyrod | ahmet doci | [5 empty] | Manchester
Heyrod | Alan Hedgecock | [5 empty] | Manchester
Allied Scaffolding | Alan Dunwoody | [5 empty] | Manchester
Titan Interior | Alan McGreavey | Yes |  |  |  |  | Manchester
Titan Interior | Aleksandar Georgiev Hotov | Yes |  |  |  |  | Manchester
EWS Façade | Aleksej Babuskin | [5 empty] | Manchester
EWS Façade | Alex ene | [5 empty] | Manchester
Titan Interior | Alfie Gunnar Henson | No |  |  |  |  | Manchester
Titan Interior | Alhassan Karim Mumumi | Yes |  |  |  |  | Manchester
Heyrod | alokik singla | [5 empty] | Manchester
Titan Interior | Amadeusz Brozyna | Yes |  |  |  |  | Manchester
Heyrod | Amritpal Singh Sidhu | [5 empty] | Manchester
Heyrod | Andrei loan | [5 empty] | Manchester
Titan Interior | Anteo Agalliu | Yes |  |  |  |  | Manchester
Titan Interior | Anton Dimitrov | No |  |  |  |  | Manchester
Morgan Sinall | Aqib Iqbal | Yes |  |  |  |  | Manchester
Cara Brickwork | Arron Oreilly | [5 empty] | Manchester
Heyrod | Basel Zalghana | [5 empty] | Manchester
Allied Scaffolding | Ben Marshall | [5 empty] | Manchester
Morgan Sinall | benji arthur | Yes |  |  |  |  | Manchester
Titan Interior | Bobeica Sergiu | [5 empty] | Manchester
Ameon | Boby Emmanuel | [5 empty] | Manchester
Heyrod | Bogdan Kapera | [5 empty] | Manchester
Allied Scaffolding | Bradley Mansbridge | [5 empty] | Manchester
Titan Interior | Bradley Pearl | Yes |  |  |  |  | Manchester
Ameon | Brandon Ryan | [5 empty] | Manchester
Bennett Architectural Aluminium Solutions Ltd | callum davies | [5 empty] | Manchester
Chartrange | Callum Cook | [5 empty] | Manchester
Titan Interior | Callum McKenna | Yes |  |  |  |  | Manchester
Allied Scaffolding | Callum Stirrup | [5 empty] | Manchester
Titan Interior | Camron Woodhouse | Yes |  |  |  |  | Manchester
Heyrod | Carlton Jordan | [5 empty] | Manchester
Ambrose Ellis | Chris Greyson | No |  |  |  |  | Manchester
Titan Interior | Chris Talbot | No |  |  |  |  | Manchester
Heyrod | Colleen Carthy | [5 empty] | Manchester
Titan Interior | Corey Palmer | No |  |  |  |  | Manchester
Titan Interior | Damian Palka | No |  |  |  |  | Manchester
Titan Interior | Damian Sus | Yes |  |  |  |  | Manchester
Titan Interior | Daniel Powell | Yes |  |  |  |  | Manchester
Titan Interior | Daniel Appiagyei | [5 empty] | Manchester
Allied Scaffolding | Daniel Condron | [5 empty] | Manchester
Titan Interior | Daniel Crawley | Yes |  |  |  |  | Manchester
Titan Interior | Daniel Heaton | Yes |  |  |  |  | Manchester
Titan Interior | Daniel Powell | Yes |  |  |  |  | Manchester
Titan Interior | Daniel Pupeza | No |  |  |  |  | Manchester
Titan Interior | Daniil Komisarenko | Yes |  |  |  |  | Manchester
Heyrod | Dariusz Katra | [5 empty] | Manchester
Heyrod | Dariusz Nowicki | [5 empty] | Manchester
Chartrange | Darren Pearson | [5 empty] | Manchester
Allied Scaffolding | Dave Moran | [5 empty] | Manchester
RW Joinery | David Connor | Yes |  |  |  |  | Manchester
Morgan Sinall | David Dementjev | Yes |  |  |  |  | Manchester
Titan Interior | David Glover | No |  |  |  |  | Manchester
Allied Scaffolding | David Griffin | [5 empty] | Manchester
Heyrod | David Laughton | [5 empty] | Manchester
Bennett Architectural Aluminium Solutions Ltd | David Teehan | [5 empty] | Manchester
Titan Interior | Declan Lovelace | Yes |  |  |  |  | Manchester
Heyrod | Declan Murphy | [5 empty] | Manchester
Titan Interior | Derek Stevenson | Yes |  |  |  |  | Manchester
Titan Interior | Devon Mannion | [5 empty] | Manchester
Bennett Architectural Aluminium Solutions Ltd | Dominic Jordan | [5 empty] | Manchester
EWS Façade | Dumitru Burcea | [5 empty] | Manchester
Cara Brickwork | Dylan walker | [5 empty] | Manchester
Heyrod | Edward Barnes | [5 empty] | Manchester
Titan Interior | Emmanuel Bempong | Yes |  |  |  |  | Manchester
Morgan Sinall | fabian simpson | Yes |  |  |  |  | Manchester
Ameon | fergus black | [5 empty] | Manchester
Morgan Sinall | Folahan Ogunjobi | Yes |  |  |  |  | Manchester
Titan Interior | Gary Jones | Yes |  |  |  |  | Manchester
Max Installations | Georgi Bibishkov | [5 empty] | Manchester
Heyrod | Gurpreet Singh | [5 empty] | Manchester
Morgan Sinall | Harrison Smart | Yes |  |  |  |  | Manchester
Titan Interior | Helm Davies | No |  |  |  |  | Manchester
Bennet Architectural Aluminium | Ian Miller | [5 empty] | Manchester
Titan Interior | Isaac Addo | Yes |  |  |  |  | Manchester
Titan Interior | Ivan Pupeza | Yes |  |  |  |  | Manchester
Allied Scaffolding | Jacek Matusz | [5 empty] | Manchester
Heyrod | Jakub Swidurski | [5 empty] | Manchester
Allied Scaffolding | James Carty | [5 empty] | Manchester
Allied Scaffolding | James Elliott | [5 empty] | Manchester
Heyrod | James Woolfe | [5 empty] | Manchester
Titan Interior | Jaroslaw Rutkowski | No |  |  |  |  | Manchester
Heyrod | Jasbir Jasbir | [5 empty] | Manchester
Bennett Architectural Aluminium Solutions Ltd | Jason Finley | [5 empty] | Manchester
Chartrange | Jason Woodward | [5 empty] | Manchester
Titan Interior | Jay Cunliffe | Yes |  |  |  |  | Manchester
Metclad | Jimmy Briggs | [5 empty] | Manchester
Bennett Architectural Aluminium Solutions Ltd | John Patton | [5 empty] | Manchester
Morgan Sinall | John Allwood | Yes |  |  |  |  | Manchester
Morgan Sinall | John Harness | Yes |  |  |  |  | Manchester
Heyrod | John Keeley | [5 empty] | Manchester
Allied Scaffolding | John Storr | [5 empty] | Manchester
Morgan Sinall | Jonathan Heller | Yes |  |  |  |  | Manchester
Lyndon SGB | Jordan Coleman | [5 empty] | Manchester
Heyrod | jordan keeling | [5 empty] | Manchester
Cara Brickwork | JORDAN LEVINSON | [5 empty] | Manchester
Allied Scaffolding | Jordan Nelson | [5 empty] | Manchester
Ameon | Josh Moffatt | [5 empty] | Manchester
Morgan Sinall | Joshua Durcan | Yes |  |  |  |  | Manchester
Titan Interior | Junior Nolan | Yes |  |  |  |  | Manchester
Titan Interior | Kai Gorji | Yes |  |  |  |  | Manchester
Manchester City Council | Kamal Beckles | [5 empty] | Manchester
Heyrod | kamaljeet singh | [5 empty] | Manchester
EWS Façade | kamil Glazer | [5 empty] | Manchester
Bennett Architectural Aluminium Solutions Ltd | keith williams | [5 empty] | Manchester
Bennett Architectural Aluminium Solutions Ltd | Kevin Williams | [5 empty] | Manchester
Chartrange | Kieran Walls | [5 empty] | Manchester
EWS Façade | Krzysztof Dyk | [5 empty] | Manchester
Ameon | Kyle Lowe | [5 empty] | Manchester
RW Joinery | Lance Collins | [5 empty] | Manchester
Morgan Sinall | Lateefat Seidu-Lateef | Yes |  |  |  |  | Manchester
Titan Interior | Lee Mason | Yes |  |  |  |  | Manchester
Ameon | Lewis Buckley | [5 empty] | Manchester
Titan Interior | Lewis Taylor | No |  |  |  |  | Manchester
Muse Developments | Liam Davis | [5 empty] | Manchester
Titan Interior | Liam Cartner | [5 empty] | Manchester
Titan Interior | Lukasz Poleszczuk | No |  |  |  |  | Manchester
Titan Interior | Luke Grimley | No |  |  |  |  | Manchester
Titan Interior | Luke Mason | Yes |  |  |  |  | Manchester
Allied Scaffolding | Luke Moran | [5 empty] | Manchester
Titan Interior | Luke Raistrick | Yes |  |  |  |  | Manchester
Titan Interior | Maksym Pashko | [5 empty] | Manchester
Heyrod | Manjinder Singh | [5 empty] | Manchester
Heyrod | Marek Nosal | [5 empty] | Manchester
Hardhat Logistics Limited | Mariam Gbolagun | [5 empty] | Manchester
Heyrod | Mariusz Sikora | [5 empty] | Manchester
Ameon | Mark Dempsey | [5 empty] | Manchester
Hays | Mark Finerty | [5 empty] | Manchester
Bretton Architectural | Mark Golden | [5 empty] | Manchester
Morgan Sinall | Mark Hunt | Yes |  |  |  |  | Manchester
Titan Interior | Mark Scott | Yes |  |  |  |  | Manchester
Cara Brickwork | Matthew Byrne | [5 empty] | Manchester
Titan Interior | Matthew Glover | Yes |  |  |  |  | Manchester
Ambrose Ellis | Matthew Hill | No |  |  |  |  | Manchester
Titan Interior | Matthew Onyemem | Yes |  |  |  |  | Manchester
Allied Scaffolding | Matthew Sanchez | [5 empty] | Manchester
Titan Interior | Methode Nguimby | Yes |  |  |  |  | Manchester
Heyrod | Michael Heard | [5 empty] | Manchester
Heyrod | Mieczyslaw kruk | [5 empty] | Manchester
Bennet Architectural Aluminium | Mike Ryan | [5 empty] | Manchester
Heyrod | mirza baig | [5 empty] | Manchester
Cara Brickwork | mitchell thomson | [5 empty] | Manchester
EWS Façade | Muhammad Qaiser | [5 empty] | Manchester
Latimer | Nabeel Baig | [5 empty] | Manchester
Bennett Architectural Aluminium Solutions Ltd | Nathan McEwan | [5 empty] | Manchester
Titan Interior | Niall Pollitt | [5 empty] | Manchester
EWS Façade | Norbert ziober | [5 empty] | Manchester
Ameon | Onesmus Kivilia | [5 empty] | Manchester
Titan Interior | Pana Sergiu | No |  |  |  |  | Manchester
Heyrod | parvinder singh | [5 empty] | Manchester
Titan Interior | Patrick Rose | No |  |  |  |  | Manchester
EWS Façade | Patryk Ciekanski | [5 empty] | Manchester
Heyrod | Paul Broadhurst | [5 empty] | Manchester
Cara Brickwork | Paul Campbell | [5 empty] | Manchester
Heyrod | paul cawley | [5 empty] | Manchester
Titan Interior | Pawel Litwinczuk | No |  |  |  |  | Manchester
Titan Interior | Pawel Michalowski | No |  |  |  |  | Manchester
Max Installations | Petar Yankov | [5 empty] | Manchester
John Sutch | Pete wilson | [5 empty] | Manchester
Heyrod | Ramanpreet singh | [5 empty] | Manchester
Heyrod | Ranjodh Brar | [5 empty] | Manchester
Allied Scaffolding | Ray Wilkey | [5 empty] | Manchester
Allied Scaffolding | Reece Johnson | [5 empty] | Manchester
Heyrod | Richard Mcneilly | [5 empty] | Manchester
Heyrod | Robert McNeily | [5 empty] | Manchester
Ameon | Robert Parker | [5 empty] | Manchester
Heyrod | Roman Kosut | [5 empty] | Manchester
Morgan Sinall | Roman Splawski | Yes |  |  |  |  | Manchester
Allied Scaffolding | Ryan Marley | [5 empty] | Manchester
Heyrod | sahil jaswal | [5 empty] | Manchester
Morgan Sinall | Sara Pregnolato | Yes |  |  |  |  | Manchester
Heyrod | Satnam Singh | [5 empty] | Manchester
GGR | Sean Mealey | [5 empty] | Manchester
Morgan Sinall | Segun Bello | Yes |  |  |  |  | Manchester
Heyrod | Sergiu Tverdohleb | [5 empty] | Manchester
Heyrod | sima getachew | [5 empty] | Manchester
Titan Interior | Simon Chamberlain | No |  |  |  |  | Manchester
Titan Interior | Simon Cutler | Yes |  |  |  |  | Manchester
Allied Scaffolding | Simon Wood | [5 empty] | Manchester
Heyrod | stephen kenny | [5 empty] | Manchester
Allied Scaffolding | Stephen Woods | [5 empty] | Manchester
Wysepower | Steven McManus | [5 empty] | Manchester
Titan Interior | Sylwester Wegiera | No |  |  |  |  | Manchester
Max Installations | Teodor Stoyanov | [5 empty] | Manchester
Titan Interior | Thomas Ross | Yes |  |  |  |  | Manchester
Titan Interior | Tom Jackson | [5 empty] | Manchester
Morgan Sinall | Tomasz Skibinski | Yes |  |  |  |  | Manchester
Heyrod | Varinder Singh | [5 empty] | Manchester
Titan Interior | Vasil Shimbov | Yes |  |  |  |  | Manchester
Titan Interior | Vasile Pinzari | Yes |  |  |  |  | Manchester
Titan Interior | Warren Todd | No |  |  |  |  | Manchester
Allied Scaffolding | Wayne Lyons | [5 empty] | Manchester
Allied Scaffolding | wesley dalton | [5 empty] | Manchester
Morgan Sinall | William Jones | Yes |  |  |  |  | Manchester
Titan Interior | Wojciech Zajaczkowski | No |  |  |  |  | Manchester
Titan Interior | Xhulian Hyria | No |  |  |  |  | Manchester
Titan Interior | Yahuza Awudu | [5 empty] | Manchester
Titan Interior | Yasen Mihaylov | Yes |  |  |  |  | Manchester
Heyrod | yilli Cara | [5 empty] | Manchester
Titan Interior | Yordan lliev | Yes |  |  |  |  | Manchester
EWS Façade | Zbigniew Chetnik | [5 empty] | Manchester
Chartrange | Zydrunas Jabubsevicius | [5 empty] | Manchester

## Education Employment Community
Open field (free text) | Please select from Dropdown |  |  | Open field - detail what support you offered on this occasion | Open field (free text) | [5 empty] | Self calculating | Open field (free text) | Please select from Dropdown | Estimate percentage split of group if this wasn’t recorded
Employer | Measure (Specific KPI met) |  |  | What did you do | Where (Location) | Date | Who did you support? | Number of Volunteers | Total Volunteering hours | Beneficiaries (number in attendance) | TOMs people*hrs | Charitable spend (£) | Beneficiary age range | Gender % |  | Ethnicity %
|  |  | Case study | [10 empty] | Male | Female | WB | BME | Notes | Evidence
Morgan Sindall | Educational Engagement | Sector insight talks / events / company visits for teaching staff of City of Manchester schools |  | Multi Disciplinary Project - talk topics including Cost & Risk Registers: Collaborative working using the NEC and subcontractors, Collateral Warranties/ bonds, Management of subcontractors. | University of Salford | 2022-02-17 | University of Salford - MDP | 1 | 4 | 30 | 4 |  | 16-25
Morgan Sindall | Educational Engagement | Sector insight talks / events / company visits for teaching staff of City of Manchester schools |  | Multi Disciplinary Project - talk topics including session on Social Value and Sub-Contractors | University of Salford | 2022-02-24 | University of Salford - MDP | 1 | 4 | 30 | 4 |  | 16-25
| Educational Engagement | Student projects with City of Manchester FE College and Universities |  | T Levels Project day - Low carbon primary school challenge | Manchester College | 2022-09-21 | Full cohort of first year students. | 10 | 9 | 25 | 90 |  | YR 10-12 | 17 | 8 | 25 | 75
Morgan Sindall | Support young people into work | Careers activities in City of Manchester schools |  | Mock Interviews | Our Ladys RC High School, Higher Blackley | 2021-11-30 |  |  |  |  | 0
Morgan Sindall | Educational Engagement | Careers activities on site or office for City of Manchester schools |  | Site tour | Manchester College | 2022-04-01 | Level 1 students who due to COVID havent had any site visits | 2 | 2 | 12 | 4 |  | YR 10-12
Morgan Sindall | Support young people into work | Careers activities in City of Manchester schools |  | Career carousel | The East Manchester Academy | 2022-09-15 |  |  |  | 30 | 0
| Support young people into work | Careers activities in City of Manchester schools |  | Mentoring & team building session | The East Manchester Academy | 2022-11-01 |  | 9 | 3 | 30 | 27
| Educational Engagement | Careers activities on site or office for City of Manchester schools |  | Site tour | The East Manchester Academy | 2022-11-08 | Year 9 students | 2 | 2 | 15 | 4 |  | YR 7-9
| Support young people into work | Careers activities in City of Manchester schools |  | Mock Interviews | Bury C of E High School |  | Year 11 students | 1 | 3 | 15 | 3
| Support young people into work | Careers activities in City of Manchester schools |  | Mock Interviews | Connell Co-Op College |  | Year 13 students | 1 | 3 | 15 | 3
| Support young people into work | Careers activities in City of Manchester schools |  | Mock Interviews for year 12 students | Connell Co-Op College
Morgan Sindall | Initiatives to be taken to tackle homelessness | Community project |  | Volunteering | Bread & Butter Thing | 2021-10-29 |  | 2 | 12 |  | 24
Morgan Sindall | Initatives taken or supported aimed at supporting young parents and children | Community project | Yes | Donation of presents | Wood Street Mission | 2021-12-01 | Helped support families who are struggling across Manchester and Salford, providing new toys and gifts for children aged 0-14 years old |  |  |  | 0 | 650
Morgan Sindall | Initatives taken or supported aimed at supporting young parents and children | Community project |  | Xmas volunteering wraping presents | Manchester Youth Zone | 2021-12-13 |  | 2 | 12 |  | 24
| Initiatives taken or supported to engage people in health interventions or wellbeing initiatives in the community | Community project | 2022-12-01 | Collection of hygiene products for donation to a local charity | Hygiene Bank
| Initatives taken or supported aimed at supporting young parents and children | Community project | 2022-12-01 | Collection of food products for donation to a local charity | Foodbank
Morgan Sindall | Supporting unemployed people into work | Community projects will be / were delivered that had skills and employability outcomes for residents |  | Informaitive session on various roles withtin construction, CV and interview tips | Mancehster Adult Education (MAES) | 2022-06-29
| Educational Engagement | Student projects with City of Manchester FE College and Universities |  | VWEX | Manchester College |  |  |  |  | 30 | 0 |  | YR 10-12
| Educational Engagement | Careers activities in City of Manchester schools |  | Whats My Job Role | Ashbury Meadow Primary | 2021-11-24 | Morgan Sindall attended and took part in a session with the Pupils, the pupils had to ask as many questions as they could in attempt to find out what our day Jobs were. | 1 | 2 | 60 | 2 |  | YR 1-6
| Educational Engagement | Careers activities in City of Manchester schools |  | Mixed Bag Event | Manchester Youth Zone | 2021-12-13 | Young people at Manchester Youth Zone | 2 | 4 |  | 8 |  | YR 1-6
| Educational Engagement | Careers activities in City of Manchester schools |  | Whats My Job Role | Ravensbury Community Primary School |  | Morgan Sindall attended and took part in a session with the Pupils, the pupils had to ask as many questions as they could in attempt to find out what our day Jobs were. | 1 | 2 | 60 | 2 |  | YR 1-6
| Educational Engagement | Student projects with City of Manchester FE College and Universities |  | VWEX |  | 2022-07-04 |  |  |  |  | 0
Morgan Sindall | Supporting unemployed people into work | Volunteer opportunities for City of Manchester job seekers |  | Have a Go event - plastering activity | HMP Styal Prison | 2022-10-13 |  | 2 | 6 | 19 | 12
Morgan Sindall | Initiatives aimed at reducing crime |  | Yes | Supported Styal Womens Prison with career advice & Mock Interviews | Styal ladies prison | 2022-02-12 | Styal Womens Prison | 2 | 10 | 7 | 20
Morgan Sindall | Mentoring External |  |  | Site for MCC and Muse Developments apprentices | [6 empty] | 0
Morgan Sindall | Support young people into work | Careers activities in City of Manchester schools |  | Manchester College Trades Day | Manchester College | 2023-03-23 |  | 3 | 12 | 650 | 36
Morgan Sindall |  | Sector insight talks / events / company visits for teaching staff of City of Manchester schools |  | Digital Sandpit workshop to Manchester College teaching staff and students | Manchester College |  |  | 2 | 6 | 12 | 12
| Educational Engagement | MAnchester College Electrical students site visit |  | Induction and site tour | M/cr college | 19-04-23 |  |  |  |  | 3 |  | 16-25
| Educational Engagement | MAnchester College Electrical students site visit |  | Induction and site tour | M/cr college | 2023-10-05 |  |  |  |  | 3 |  | 16-25
| Educational Engagement | CPD session |  | Newton Heath Job centre site visit |  | 2023-10-05 |  |  |  |  | 3 |  | 16-25
|  | Martin Wilcock CPd with PAul Guil & AMeon | [8 empty] | 0
| Support young people into work | [11 empty] | YR 1-6
| Supporting unemployed people into work | [11 empty] | YR 7-9
| Mentoring External | [11 empty] | YR 10-12
| Mentoring Internal | [11 empty] | 16-25
| Educational Engagement | [11 empty] | 26-49
Total amount (£) spent with VCSEs within your supply chain
Provision of expert business advice to VCSEs and SMEs (e.g. financial advice / legal / HR/HSE)
Staff wellbeing initiatives
Diversity training
Initiatives aimed at reducing crime
Initiatives to be taken to tackle homelessness
Initiatives to be taken to support older people to build stronger community networks
Initiatives to be taken to support disabled and vulnerable people to build stronger community networks
Initiatives taken or supported to engage people in health interventions or wellbeing initiatives in the community
Initatives taken or supported aimed at supporting young parents and children

## SV Economic
Update each month
|  |  | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01
Morgan Sindall Added Value | Promotional (good news stories) | 10
| Local spend (City of Manchester) | 20%
| LM3 | 1.85
| Job Vacancies Advertised | 20
| Inclusion plan in place | Yes
| Mental Health First Aiders | 1
| CCS Score | 42
| Environmental TBT's | 18
| Responsible Timber procured | 100%
| Air Quality Improvement Plan | Gold
| Biodiversity Legacy | Silver
| Carbon Emissions | TBC
| Water Reduction Plan | Gold

## SC List (hidden)
Morgan Sindall Construction
13W009 Gorton Community Hub |  |  |  | PCSA WORKS / NOT APPLICABLE | AW
BK
Sub-Contractor List
COINS ORDER REF |  | PROCUREMENT SCHEDULE REF | SUB-CONTRACTOR | WORKS PACKAGE | QS | Current Order Value | Postcode | Tier 1 | Tier 2 | Tier 3 | SMEs
S/13W009/ | 1 | 1 | Curtins Consulting Engineers | Site Investigations & transport planning | N/A | 46146 | M1 5WG |  | 46146 |  | 46146
S/13W009/ | 2 | 2 | SEP (Site Engineering Personnel) Ltd | Topo Surveys & Drainage Survey | AW | 120504 | WN8 8EF |  |  | 120504
S/13W009/ | 3 | 3 | Ramboll | Acoustic Consultant S2-4 | AW | 17330 | M3 2LF |  | 17330
S/13W009/ | 4 | 4 | Omega Fire Engineering Ltd | Fire Consultant | AW | 37943 | M3 4LZ |  | 37943 |  | 37943
S/13W009/ | 5 | 5 | GWP Projects Services Ltd | Breeam Services | N/A | 15225 | M3 2BH |  | 15225 |  | 15225
S/13W009/ | 6 | 6 | IBI Group (UK) Ltd | Architect & Landscape Fees to Stage 3 Design | AW | 577714 | M4 2AL |  | 577714
S/13W009/ | 7 | 7 | Quartzelec Ltd | M&E Consultant Stage 2-4 Design | AW | 3158125 | M50 2GT | 60000 | 3098125
S/13W009/ | 8 | 8 | Curtins Consulting Ltd | Civil & Structural Engineers to Stage 4 | AW | 176163 | M1 5WG |  | 176163 |  | 176163
S/13W009/ | 9 | 9 | Baker Hicks Ltd | Principle Designer | N/A | 5060 | M50 3YW |  | 5060
S/13W009/ | 10 | 21 | Hardhat Logistics Ltd | Security & Welfare Cleaning | AW | 76541 | L3 7BL | 7500 |  | 69041 |  | Site Cleaner
S/13W009/ | 11 | 10 | R&H Site Services Ltd | Hoarding & Gates | N/A | 35495 | L5 9UU |  |  | 35495
S/13W009/ | 12 |  | MSES Ltd | Temporary Works Consultants | N/A | 0 | M50 3YW | 0
S/13W009/ | 13 | 14 | Socotec Asbestos Ltd | Asbestos Survey | N/A | 8185 | SK5 6PH |  | 8185 |  | 8185
S/13W009/ | 14 | 13 | Wysepower Ltd | Temporary Electrics | AW | 41310 | M17 1EH | 5000 | 36310 |  | 36310 | Local hire depots etc.
S/13W009/ | 15 | 11 | PP O'Connor Ltd | Demolition | N/A | 160500 | M17 1NB | 8000 | 152500 |  | 152500 | Local hire depots etc.
S/13W009/ | 16 | 23 | Gleeds Advisory Ltd | Breeam Life Cycle Costing | N/A | 5000 | M2 3LW |  | 5000 |  | 5000
S/13W009/ | 17 |  | United Utilities Water PLC | Sewer Closure Application | N/A | 174 | WA5 3LP |  | 174
S/13W009/ | 18 | 12 | LAR Ltd | Asbestos Removal | N/A | 3539 | SK4 5BF |  | 3539 |  | 3539
S/13W009/ | 19 | 24 | Stroma Built Environment Ltd | Air Quality Assessment & Air Test | BK | 4900 | WF5 9TJ |  |  | 4900
S/13W009/ | 20 | 20 | Nolan Associates | Temporary Works | N/A | 2850 | B16 8PE |  |  | 2850
S/13W009/ | 21 | 19 | Baker Hicks Ltd | BIM Information Manager | N/A | 21000 | M50 3YW |  | 21000
S/13W009/ | 22 | 25 | IBI Group (UK) Ltd | Architect Fees Stages 5-7 | N/A | 0 | -
S/13W009/ | 23 | 26 | Curtins Consulting Ltd | Civil & Structural Engineers Stages 5-7 | N/A | 0 | -
S/13W009/ | 24 |  | Baker Hicks Ltd | Principle Designer Stage 5 | AW | 5200 | M50 3YW |  | 5200
S/13W009/ | 25 |  | Baker Hicks Ltd | BIM Information Manager Stages 5-6 | AW | 21950 | M50 3YW |  | 21950
S/13W009/ | 26 |  | Omega Fire Engineering Ltd | Fire Consultant Stage 5 | N/A | 0 | -
S/13W009/ | 27 |  | Footprint Freelance | Freelance QS | N/A | 15000 | M20 2YY |  | 15000 |  | 15000
S/13W009/ | 28 | 28 | All Foundations (UK) Ltd novated to Founda Ltd | Piling | AW | 88665 |  | 7500 |  | 81165 |  | Local hire depots etc.
|  |  | Cemex Concrete |  |  | 35000 | M18 8DB | 35000
S/13W009/ | 29 | 27 | Chartrange Ltd | Groundworks | AW | 1449138 | SK16 4NJ | 420000 | 1029138 |  | 1029138
S/13W009/ | 30 |  | MSES Ltd | Temporary Works | AW | 5000 | M50 3YW |  | 5000
S/13W009/ | 31 | 29 | Border Steelwork Structures Ltd | Structural Steelwork | AW | 1145898 | CA3 0BQ | 20000 | 50000 | 1075898
S/13W009/ | 32 | 31 | KONE plc | Lifts | BK | 237982 | WA3 7QN |  |  | 237982
S/13W009/ | 33 |  | Ramboll | Acoustic Consultant S5-7 | N/A | 0 | -
S/13W009/ | 34 |  | UBU Envrionmental Ltd | Roadsweeper | AW | 21600 | M28 3LY |  | 21600 |  | 21600
S/13W009/ | 35 |  | Knowsley Surfacing Ltd | Tarmac | AW | 98160 | L3 3BN |  | 40000 | 58160 |  | £40k Aggregate industries M50 1DG
S/13W009/ | 36 |  | Hoard-It Ltd | Hoarding to Tesco Access Road | AW | 7200 | S73 8HR |  |  | 7200
S/13W009/ | 37 |  | Altrad NSG Ltd | Scaffolding | BK | 203095 | DE55 5GZ |  |  | 203095
S/13W009/ | 38 |  | Beech Landscape Developments Ltd | Maintenance to Library Car Park | AW | 2500 | M31 4AD |  | 2500 |  | 2500
S/13W009/ | 39 |  | Red Systems Ltd | Windows & Curtain Walling | BK | 402837 | CH64 3RU | 28000 | 90000 | 284837
S/13W009/ | 40 |  | PLF Ltd | Brickwork | BK | 823630 | PR4 3HJ | 40000 | 187000 | 596630
S/13W009/ | 41 |  | L&R Roadlines | Temp Road Markings | AW | 838 | CH65 4EL |  |  | 838
S/13W009/ | 42 |  | Firesafe Installations | Intumescent Paint | AW | 77860 | L34 9HP | 15000 | 25000 | 37860 |  | Pant hire / Sherwin Williams BL2
S/13W009/ | 43 |  | AMEY LG Ltd | Street Lighting Disconnection & removal | AW | 2778 | M17 1DZ |  | 2778 |  | 2778
S/13W009/ | 44 |  | SCS Building Solutions Ltd | SFS | BK | 435794 | WF3 4AL | 22000 | 50000 | 363794
S/13W009/ | 45 |  | Clive Plant & Associates | PPC Inspections | AW | 756 | OX15 5NA |  |  | 756
S/13W009/ | 46 |  | Metro Rod Ltd | Drainage CCTV Survey | AW | 925 | SK10 4NL |  |  | 925
S/13W009/ | 47 |  | Edocuments Ltd | O&M Manuals | BK | 5000 | CM1 2QE |  |  | 5000
S/13W009/ | 48 |  | Primeseal Roofing Ltd | Roofing & Cappings | AW | 404285 | OL9 9HD | 25000 | 379285 |  | 379285
S/13W009/ | 49 |  | WPL (UK) Ltd | Plant Screen Louvres | BK | 17061 | BL3 2RB |  | 17061 |  | 17061
S/13W009/ | 50 |  | Met-Clad Contracts Ltd | Cladding | AW | 149878 | NG15 0DQ | 7500 | 40000 | 102378 |  | Local plant hire, fixings / sundries Tier 2
S/13W009/ | 51 |  | Concrete Drilling Services Ltd | Builderswork | BK | 7487 | BL2 2HH |  | 7487 |  | 7487
S/13W009/ | 52 |  | Accordial Ltd | Folding Partitions | BK | 12447 | LE11 5JH |  |  | 12447
S/13W009/ | 53 |  | Steven A Hunt & Associates Ltd | MEP Technical Advisor | BK | 8110 | L24 8RN |  |  | 8110
S/13W009/ | 54 |  | Rotec Security Solutions Ltd | External Steel Doors | BK | 26350 | SK7 2LD |  | 26350 |  | 26350
S/13W009/ | 55 |  | SCS Building Solutions Ltd | Internal Partitions & Ceilings | BK | 978065 | WF3 4AL | 50000 | 360000 | 568065
S/13W009/ | 56 |  | Axiom Group Limited | Soft Flooring | BK | 145963 | WA4 6HL | 20000 | 45000 | 80963
S/13W009/ | 57 |  | Ambose Ellis | Decoration | BK | 68734 | WA7 4UX | 10000 | 15000 | 43734
S/13W009/ | 58 |  | Metallic Fabrications | Balustrades | AW | 61493 | LS23 | 3000 | 10000 | 48493
S/13W009/ | 59 |  | Planet Contracting Limited | Glazed Partitions | AW | 107074 | LS12 6HH | 5500 | 16000 | 85574
S/13W009/ | 60 |  | Inscape Interiors Limited | IPS & Cubicles | BK | 148668 | PR6 9AR | 7500 | 22000 | 119168
S/13W009/ | 61 |  | TMJ Contractors Limited | Joinery | BK | 275790 | OL6 7SW | 40000 | 235790 |  | 235790
S/13W009/ | 62 |  | Bathgate Flooring Limited | Raised Access Floor | AW | 22256 | HR2 6JT |  |  | 22256
S/13W009/ | 63 |  | B&K Systems | Screeding | BK | 9889 | LS27 7WF |  |  | 9889
S/13W009/ | 64 |  | Fastglobe Mastics Ltd | Mastic Sealant | BK | 9943 | PR6 9AR |  | 5000 | 4943
S/13W009/ | 65 |  | Langley Design | Cycle Shelter Installation | BK | 21500 | SN6 6HE |  |  | 21500
S/13W009/ | 66 |  | Advancing Hygienic Contracting Ltd | Hygienic Cladding | BK | 7000 | HG3 1GY |  |  | 7000
S/13W009/ | 67 |  | Ardere Solutions Limited | Firestopping | BK | 97225 | OL9 6HZ | 10000 | 87225 |  | 87225
S/13W009/ | 68 |  | Widd Signs (NW) Limited | Building Signage | BK | 17750 | WA6 4HY |  |  | 17750
S/13W009/ | 69 |  | Beech Landscape Developments Limited | Soft Landscaping | BK | 40000 | M31 4AD |  | 40000 |  | 40000
S/13W009/ | 70 |  | A1 Shutters Limited | Fire Curtain & Shutters | BK | 7500 | BL3 2NH |  | 7500 |  | 7500
S/13W009/ | 71 |  | Lancashire Tiling Company Limited | Ceramic Tiling | BK | 21500 | FY6 8JS |  |  | 21500
S/13W009/ | 72 |  | Arjo UK Limited | Changing Places Hoist | AW | 2950 | LU5 5XF |  |  | 2950
S/13W009/ | 73 |  | Pentel Contracts Limited | Blinds & Curtain Tracks | AW | 16000 | M27 6DB |  | 16000 |  | 16000
S/13W009/ | 74 |  | Jonathan Carey Design Limited | Bespoke Joinery | AW | 50000 | BD20 7BW |  |  | 50000
| 75 |  | FBS | FFE |  | 65000 | WA7 3DL |  | 13000 | 52000
32
|  | 40 | Hard Landscaping | CHARTRANGE | BK | 310000 | SK16 4NJ | 90000 | 220000 |  | 220000
|  | 39 | External Fencing | R&H | BK | 20000 | L5 9UU |  |  | 20000
|  |  | Vehicle Barriers | NEWGATE | AW | 15000 | NG24 2DE |  |  | 15000
|  | 47 | Builders Clean | TBC | BK | 25000 | TBC | 12500 | 12500
|  | 46 | Road Markings | L&R | BK | 2500 | CH65 4EL |  |  | 2500
|  | 55 | Internal wayfinding signage | WIDD | BK | TBC | TBC
|  |  | Gateman / Labourers / Cleaners |  |  | 105000 |  | 105000
|  |  | Direct purchased materials |  |  | 25000 |  |  | 25000
|  |  | MS staff |  |  | 600000 |  |  | 600000
49
|  | 52 | [5 empty] | 1054000 | 7945778 | 4503150 | 2588725
|  | 58 | [5 empty] | 7.806% | 58.84% | 33.35% | 19.17%
54
|  | 56 |  |  |  | 13502928 |  | 13502928
|  | 51 | [5 empty] | 0

## Local Spend (hidden)
Local Spend - Supporting Data
To be completed prior to order placement |  | To be completed as orders are placed
Work Package | Value | Company Name | Postcode | Subcontractor Company Address Tier Level
|  |  |  | 1 | 2 | 3 | 4
e.g Concrete frame | 5.85 | Heyrod | M14 |  |  | 20%
| 585% |  |  | 0% | 0% | 20% | 0%
|  |  |  | 1 | 2 | 3 | 4
Subcontractor Company Address Tier Level

## Local companies (hidden)
PLANT |  |  |  |  | MATERIALS
NAME OF SUBCONTRACTOR | WORK PACKAGE | NAME OF CORE SUPPLIERS | BRANCH POSTCODE | EXPECTED ORDER VALUE | NAME OF SUBCONTRACTOR | WORK PACKAGE | NAME OF CORE SUPPLIERS | BRANCH POSTCODE | EXPECTED ORDER VALUE
Heyrod

## Local Labour
Totals |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
| 0ct-21 |  | 2021-11-01 |  | 2021-12-01 |  | 2022-01-01 |  | 2022-02-01 |  | 2022-03-01 |  | 2022-04-01 |  | 2022-05-01 |  | 2022-06-01 |  | 2022-07-01 |  | 2022-08-01 |  | 2022-09-01 |  | 2022-10-01 |  | 2022-11-01 |  | 2022-12-01 |  | 2023-01-01 |  | 2023-02-01 |  | 2023-03-01 |  | 2023-04-01 |  | 2023-05-01 |  | 2023-06-01 |  | 2023-07-01 |  | 2023-08-01
TIER 4 UK or other | 0 | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0% | 0 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
TIER 3 NW | 0 | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0% | 0 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
TIER 2 GM | 0 | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0% | 0 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
TIER 1 Gorton | 0 | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0% | 0 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
| 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%