## Sheet1
PROJECT NO: | 5287 |  | ISSUE DATE: | 12 JAN 23
PROJECT TITLE: | LUCKY CAT, MANCHESTER
AREAS: | BASEMENT, GROUND FLOOR, MEZZANINE & FACADE
REQUEST FOR RESTORATION SCHEDULE
REVISION: A
STATUS
NOT CRITICAL
CRITICAL (Elements with an impact on the heritage statement
CRITICAL (Elements with no impact on heritage statement)
Item | Restoration Required | Photo | Location | Date Reqd
1 | Floor marble to be repaired/ re-installed where there is a missing tile or cracked marble |  | LHS Entrance | 2022-07-28
2 | Timber wall panels to be made good or repaired as close to original as possible, remove all tapes, markings and scratches |  | General | 2022-07-28
3 | Existing marble walls to be strip clean and repaired where chipped, scratched and/ or cracked |  | General | 2022-07-28
4 | Existing marble walls to be strip clean and repaired where chipped, scratched and/ or cracked |  | LHS Doorway | 2022-07-28
5 | Doormat to be replaced; All material on door panels and door gears to be inspected and made good where necessary |  | LHS Doorway | 2022-07-28
6 | Jamie Italian’s branding to be carefully removed on RHS entrance door; replace clear glass panel if necessary while maintaining all door gear and heritage element on panel |  | RHS Doorway | 2022-07-28
7 | Marble floor to be cleaned and make good as close to original as possible; remove any unused floor mounted floor boxes and close holes on floor where possible |  | Main Hall | 2022-07-28
8 | Unknown pipe; MC to inspect and check whether it can be removed to allow more room for new booth seat and close hole on floor after |  | Room next to RHS entrance under Mezzanine | 2022-07-28
9 | Remove timber panels in front of windows; MC to make good window frame and sill behind |  | Room next to RHS entrance under Mezzanine | 2022-07-28
10 | Unable to inspect heritage timber flooring below; MC to inspect and make good flooring to match as close as original as possible and ensure it is free of stains, scratches and repair if necessary |  | Room next to RHS entrance under Mezzanine | 2022-07-28
11 | MC to check feasibility to remove blackboard; clean & make good adjacent glass and timber feature panel to match original as much as possible; Remove timber panels in front of windows; MC to make good window frame and sill behind |  | Room next to RHS entrance under Mezzanine | 2022-07-28
12 | MC to clean, make good and repair heritage materials; install new tile to match existing where necessary |  | Archway into kitchen | 2022-07-28
13 | MC to remove timber panel in front of windows and make good windows and sill behind. |  | PDR 3 | 2022-07-28
14 | MC to carefully remove panel (behind heritage door) between PDRs without damaging heritage timber wall panelling |  | PDR 3 | 2022-07-28
15 | MC to remove all tapes and markings, clean and make good, as close to original as possible heritage fireplace, timber floor finishes and timber wall panels |  | PDR 3 | 2022-07-28
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption