## Sheet1
The Island Site, Manchester
Schedule of External Elevation Materials
Planning Condition 3 from Planning Permission 130553/FO/2021
Rev.00 - 20/10/21
Item No. | Material Typology | Material Description | Location on Building Elevations | Sample, Specification or Details Proposed | Date for Submission to Manchester City Council | Date for Incorporating into the Finished Works
1 | Upper Level Brick façade | Brick type (for inclusion within Precast panel) | L2 - L10 | Sample | 2022-03-11 | 2023-08-01
2 | Window system | Window with anodic PPC finish to frame, cills, flashings and fins. | L2 - L10 | Sample | 2022-09-01 | 2023-08-01
3 | Window system | Anodic PPC metal perforated panel. | L2 - L10 | Sample | 2022-09-01 | 2023-08-01
4 | Upper Level Façade Precast panels | Precast brickwork façade inc. window with anodic PPC finish to frame, cills, flashings and fins. | L2 - L10 | Details proposed - Sample Full Single Panel | 2022-11-01 | 2023-08-01
5 | Lower Floor Cladding | Feature metal cladding with profile detailing | GF - L1 | Sample | 2022-10-01 | 2023-08-01
6 | Lower Floor Glazing | Capped curtain walling system, anodic PPC finish | GF - L1 | Sample | 2022-10-01 | 2023-08-01
7 | Lower Floor Louvre | Anodic PPC finish louvre | GF | Sample | 2022-10-01 | 2023-08-01
8 | Plant screen | Anodic PPC finish perforated panel cladding - façade | L10 | Sample | 2022-10-01 | 2023-08-01
9 | Plant screen | Grey composite panel - within plant zone and building line | L10 | Sample | 2022-10-01 | 2023-08-01
10 | Roof terrace balustrade | Anodic PPC metal perforated panel. | L10 | Sample | 2022-10-01 | 2023-08-01
Notes:
The submission of detail for each material will be accompanied by elevational drawings identifying the location each material is to be used.
Samples and specifications of all materials to include jointing and fixing details and a strategy for quality control management.
Works above ground deemed to commence Dec-22.
Revisions: | (Latest revisions highlighted red)
0 | Initial issue for submission to MCC