## Sheet1
PROJECT NO: | 5287 |  | ISSUE DATE: | 12 JAN 23
PROJECT TITLE: | LUCKY CAT, MANCHESTER
AREAS: | BASEMENT, GROUND FLOOR, MEZZANINE & FACADE
REQUEST FOR RESTORATION SCHEDULE
REVISION: A
STATUS
NOT CRITICAL
CRITICAL (Elements with an impact on the heritage statement
CRITICAL (Elements with no impact on heritage statement)
Item | Restoration Required | Photo | Location | Date Reqd
16 | MC to remove all tapes and markings, clean and make good, as close to original as possible heritage fireplace, timber floor finishes and timber wall panels |  | PDR 2 | 2022-07-28
17 | MC to clean and make good all risers, treads, step nosings, railings and marble walls as close to original as possible. All cracked and/ or chipped marble to be repaired |  | LHS Stairwell to Mezzanine | 2022-07-28
18 | MC to clean and make good heritage timber flooring and wall panelling as much as possible to match original |  | LHS Mezzanine | 2022-07-28
19 | MC to inspect whether exposed wire can be removed and close and make good any floor holes after |  | LHS Mezzanine | 2022-07-28
20 | MC to clean and make good all timber panels as close to original as possible |  | Doorway to BOH corridors | 2022-07-28
21 | MC to clean and make good all timber panels, floor finish, fire place, close hole on panel, remove black board and finish as close to original as possible |  | Central Mezzanine | 2022-07-28
22 | MC to clean and make good all timber panels, fix lift door panel and inspect if the lift can be operable |  | RHS Mezzanine | 2022-07-28
23 | MC to clean, repair and make good all timber panels, floor finish, treads, tread nosings, risers, radiator (and tiling around) and railing as close to original as possible |  | RHS Stairwell to Mezzanine | 2022-07-28
24 | MC to clean and make good all risers, treads, step nosings, railings and marble walls as close to original as possible. All cracked and/ or chipped marble to be repaired |  | LHS Stairwell to Basement | 2022-07-28
25 | MC to clean and make good internal finishes on ceiling, floor and wall in vault room; MC to inspect if light strip detail above deposit boxes are functioning, re-lamp per lighting consultant’s specifications |  | Basement Vault Room | 2022-07-28
26 | Missing loo in WC #1 |  | Basement WCs | 2022-07-28
27 | Pendant to be removed, retain existing wiring & fixing and connect to PL-02 |  | Basement Vault Room | 2022-07-28
28 | Foot rail in front of ground floor bar panels to be removed and install new foot rail in brass, MT-01 |  | Ground Floor Bar | 2022-07-28
29 | Existing brass skirtings are loose; MC to ensure all skirting to be secured, cleaned and made good |  | Mezzanine Balustrade | 2022-07-28
30 | Drywalls to be repaired and re-painted in new paint colour |  | Mezzaline drywalls | 2022-07-28
31 | Existing pendant to be removed; Retain all wiring, fixings and install new ceiling fitting |  | PDR 2 | 2022-07-28
32 | Existing pendant to be removed; Retain all wiring, fixings and install new ceiling fitting |  | PDR 3 | 2022-07-28
33 | All existing framed artwork to be removed, wall behind to be made good as close to original as possible |  | PDRs | 2022-07-28
34 | Remove existing flags and allow for new flags |  | On facade above both entrances facing King Street | 2022-07-28
35 | Remove existing flags and allow for new flags |  | On niches facing King Street | 2022-07-28
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption