## Sheet1
PROJECT NO: | 5287 |  | ISSUE DATE: | 31 AUG 22’
PROJECT TITLE: | LUCKY CAT, MANCHESTER
AREAS: | BASEMENT, GROUND FLOOR, MEZZANINE & FACADE
REQUEST FOR RESTORATION SCHEDULE
REVISION: A
STATUS
NOT CRITICAL
CRITICAL (Elements with an impact on the heritage statement
CRITICAL (Elements with no impact on heritage statement)
Item | Restoration Required | Photo | Location | Date Reqd
1 | Floor marble to be repaired/ re-installed where there is a missing tile or cracked marble |  | LHS Entrance | 2022-07-28
2 | Timber wall panels to be made good or repaired as close to original as possible, remove all tapes, markings and scratches |  | General | 2022-07-28
3 | Existing marble walls to be strip clean and repaired where chipped, scratched and/ or cracked |  | General | 2022-07-28
4 | Existing marble walls to be strip clean and repaired where chipped, scratched and/ or cracked |  | LHS Doorway | 2022-07-28
5 | Doormat to be replaced; All material on door panels and door gears to be inspected and made good where necessary |  | LHS Doorway | 2022-07-28
6 | Jamie Italian’s branding to be carefully removed on RHS entrance door; replace clear glass panel if necessary while maintaining all door gear and heritage element on panel |  | RHS Doorway | 2022-07-28
7 | Marble floor to be cleaned and make good as close to original as possible; remove any unused floor mounted floor boxes and close holes on floor where possible |  | Main Hall | 2022-07-28
8 | Unknown pipe; MC to inspect and check whether it can be removed to allow more room for new booth seat and close hole on floor after |  | Room next to RHS entrance under Mezzanine | 2022-07-28
9 | Remove timber panels in front of windows; MC to make good window frame and sill behind |  | Room next to RHS entrance under Mezzanine | 2022-07-28
10 | Unable to inspect heritage timber flooring below; MC to inspect and make good flooring to match as close as original as possible and ensure it is free of stains, scratches and repair if necessary |  | Room next to RHS entrance under Mezzanine | 2022-07-28
11 | MC to check feasibility to remove blackboard; clean & make good adjacent glass and timber feature panel to match original as much as possible; Remove timber panels in front of windows; MC to make good window frame and sill behind |  | Room next to RHS entrance under Mezzanine | 2022-07-28
12 | MC to clean, make good and repair heritage materials; install new tile to match existing where necessary |  | Archway into kitchen | 2022-07-28
13 | MC to remove timber panel in front of windows and make good windows and sill behind. |  | PDR 3 | 2022-07-28
14 | MC to carefully remove panel (behind heritage door) between PDRs without damaging heritage timber wall panelling |  | PDR 3 | 2022-07-28
15 | MC to remove all tapes and markings, clean and make good, as close to original as possible heritage fireplace, timber floor finishes and timber wall panels |  | PDR 3 | 2022-07-28
16 | MC to remove all tapes and markings, clean and make good, as close to original as possible heritage fireplace, timber floor finishes and timber wall panels |  | PDR 2 | 2022-07-28
17 | MC to clean and make good all risers, treads, step nosings, railings and marble walls as close to original as possible. All cracked and/ or chipped marble to be repaired |  | LHS Stairwell to Mezzanine | 2022-07-28
18 | MC to clean and make good heritage timber flooring and wall panelling as much as possible to match original |  | LHS Mezzanine | 2022-07-28
19 | MC to inspect whether exposed wire can be removed and close and make good any floor holes after |  | LHS Mezzanine | 2022-07-28
20 | MC to clean and make good all timber panels as close to original as possible |  | Doorway to BOH corridors | 2022-07-28
21 | MC to clean and make good all timber panels, floor finish, fire place, close hole on panel, remove black board and finish as close to original as possible |  | Central Mezzanine | 2022-07-28
22 | MC to clean and make good all timber panels, fix lift door panel and inspect if the lift can be operable |  | RHS Mezzanine | 2022-07-28
23 | MC to clean, repair and make good all timber panels, floor finish, treads, tread nosings, risers, radiator (and tiling around) and railing as close to original as possible |  | RHS Stairwell to Mezzanine | 2022-07-28
24 | MC to clean and make good all risers, treads, step nosings, railings and marble walls as close to original as possible. All cracked and/ or chipped marble to be repaired |  | LHS Stairwell to Basement | 2022-07-28
25 | MC to clean and make good internal finishes on ceiling, floor and wall in vault room; MC to inspect if light strip detail above deposit boxes are functioning, re-lamp per lighting consultant’s specifications |  | Basement Vault Room | 2022-07-28
26 | Missing loo in WC #1 |  | Basement WCs | 2022-07-28
27 | Pendant to be removed, retain existing wiring & fixing and connect to PL-02 |  | Basement Vault Room | 2022-07-28
28 | Foot rail in front of ground floor bar panels to be removed and install new foot rail in brass, MT-01 |  | Ground Floor Bar | 2022-07-28
29 | Existing brass skirtings are loose; MC to ensure all skirting to be secured, cleaned and made good |  | Mezzanine Balustrade | 2022-07-28
30 | Drywalls to be repaired and re-painted in new paint colour |  | Mezzaline drywalls | 2022-07-28
31 | Existing pendant to be removed; Retain all wiring, fixings and install new ceiling fitting |  | PDR 2 | 2022-07-28
32 | Existing pendant to be removed; Retain all wiring, fixings and install new ceiling fitting |  | PDR 3 | 2022-07-28
33 | All existing framed artwork to be removed, wall behind to be made good as close to original as possible |  | PDRs | 2022-07-28
34 | Remove existing flags and allow for new flags |  | On facade above both entrances facing King Street | 2022-07-28
35 | Remove existing flags and allow for new flags |  | On niches facing King Street | 2022-07-28
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption
Caption