## Enter Template Title
QUALITY INSPECTION AND TEST PLAN
| Contract Number |  | Contract Name |  |  | Issuing Company Name |  |  | Prepared By: Mountain Earth |  | Reviewed By: Heritage Architect / Structural Engineer |  |  | Reviewed By: Mountain Earth Project Quality Manager |  |  | Accepted By: Mountain Earth Project Manager |  |  | Accepted By: Client / LPA
| TBA |  | THOMAS STREET |  |  | MOUNTAIN EARTH |  |  | Sign: |  | Sign: |  |  | Sign: |  |  | Sign: |  |  | Sign:
| QITP Number |  |  | TS/QMP/QITP/7KS/001 |  | Revision No. | P01
| QITP Title |  |  | 7 KELVIN STREET WORKS |  |  |  |  | Date: |  | Date: |  |  | Date: |  |  | Date: |  |  | Date:
| QITP Scope |  |  | Structural Stabilisation and Conservation Refurbishment
REFERENCES
| Standards & Procedures | [5 empty] | Regulations, Specifications & Drawings | [5 empty] | Design Changes
| List all relevant standards and procedures | [5 empty] | List all relevant specifications and drawings | [5 empty] | List changes to the specified requirements suc h as RFIs or Site Instructions
| Structural standards designed to BS EN 1991-1997 suite of Eurocodes I | [5 empty] | Design Consultant onstruction drawing set (yet to be produced) and specifications.
| Quality Risk & Opportunity Register for works being undertaken | [11 empty] | External Specialist Involvement
Specialist Subcontractors yet to be appointed
QUALITY INSPECTION AND TEST PLAN
Codes:
| I - Inspection |  | Formal inspection of works |  |  |  | S - Surveillance |  | Ongoing informal review of works in progress | [5 empty] | DM | Design Manager |  |  | LAB | UKAS Laboratory
| T - Test |  | Defined test carried out by a competent person |  |  |  | R - Review |  | Review of documentation (e.g. test certificates) | [5 empty] | PaM | Package Manager |  |  | BC | Building Control
| W - Witness |  | Witness of a test or inspection carried out by others |  |  |  | H - Hold Point |  | Works cannot proceed until inspection or test carried out successfully | [5 empty] | E | Engineer |  |  | TWC | Temporary Works
| Sub - Submit |  | Submission of a document | [11 empty] | QM | Quality Manager |  |  | S | Supervisor
| C - Check |  | Check against a specified requirement |  |  |  | E.g. W20 |  | Required sample % to be witnessed
SECONDARY CONTROL
PRIMARY CONTROL
Inspection / Test Number |  | Work being carried out |  |  | Relevant Documents (Specification / Procedure) |  |  | How do we know if it is right | [5 empty] | Relative Programme Activity | Where do we record the result |  | Handover Record (Y/N) | Inspection Details
[8 empty] | What are we checking |  | When / How often do we check | What answer should we get if it is right | [6 empty] | Subcontractor |  | Mountain Earth |  | Client | LPA
[18 empty] | Code | Inspector | Code | Inspector
Section 1 - Pre Construction
1.1 |  | Issue of construction drawings |  |  | Insert Contract clause that requires all drawings to be at "For Construction" Status before use |  |  | 1. Check against Drawing Register that drawings are issued at "For Construction" Status 2. Check Red Line drawings for changes |  | Before site works start | Drawings at "For Construction" Status |  |  |  | Drawing Register |  | N |  |  | R H | DT |  | R H
1.2 |  | Scaffolding Works Detailed Designs for modifying and adapting existing |  |  | Temporary Works Outlne design Subcontractor's detailed design drawings, calculations and RAMS |  |  | Review of Temporary Works Design for compliance against Temporary Works Brief |  | Before site works start | TWC Approved Drawing and Signed Temporary Works Design Check Certificate |  |  |  | TW Design Check Certificate |  | N | R H | TWC | R H | TWC |  | R H
1.3 |  | Permanent Works Detailed Designs |  |  | Structural Engineer's specification. |  |  | Review of Permanent Works Design for compliance against Structural Engineers Specification and in accordance with LPA/SLHA requirements |  | Before site works start | Approved drawings and details and methodology of installation |  |  |  | Drawing Register and Approvals, and RAMS approval |  | N | R H | TWC | R H | TWC |  | R H
1.4 |  | Movement and Vibration Monitoring |  |  | Structural Engineer's specification. |  |  | Check that the monitoring stratgey is developed in full detail and approved to implement |  | Before site works start | Approved drawings, trigger levels, monitoring and communcation, and action stratgey |  |  |  | M&V Monitoring log sheets |  | N | R H | E | R H | E / QM |  | R H
1.5 |  | Scaffolding Works Detailed Designs for supporting demolition works ineterfacing with the 7KS strucutre |  |  | Temporary Works Outlne design Subcontractor's detailed design drawings, calculations and RAMS |  |  | Review of Temporary Works Design for compliance against Temporary Works Brief |  | Before site works start | TWC Approved Drawing and Signed Temporary Works Design Check Certificate |  |  |  | TW Design Check Certificate |  | N | R H | TWC | R H | TWC |  | R H
1.6 |  | Detailed schedule of repairs and specification for all of the repair works to the internal and external fabric (including repointing, works to brickwork and works to roof) to include and a method statement for those works; |  |  | condition 4 130474 |  |  | to be developed |  | to be developed | to be developed |  |  |  | to be developed |  | to be developed | to be developed | to be developed | to be developed | to be developed | to be developed | R H
1.7 |  | Following further survey work, details of repair works to timbers and damproofing (with the assumption that there will be minimal intervention and as much original timber as possible is retained); |  |  | condition 4 130474 |  |  | to be developed |  | to be developed | to be developed |  |  |  | to be developed |  | to be developed | to be developed | to be developed | to be developed | to be developed | to be developed | R H
1.8 |  | A detailed audit of all internal and external features of historic and industrial interes that and details of how these will be reused, refurbished or reinstated; |  |  | condition 4 130474 |  |  | to be developed |  | to be developed | to be developed |  |  |  | to be developed |  | to be developed | to be developed | to be developed | to be developed | to be developed | to be developed | R H
1.9 |  | Works to the existing windows (with the assumption that all existing timber windows are retained as far as possible); |  |  | condition 4 130474 |  |  | to be developed |  | to be developed | to be developed |  |  |  | to be developed |  | to be developed | to be developed | to be developed | to be developed | to be developed | to be developed | R H
2 |  | Details of works required to acoustically insulate the apartments to include retention of exposed timbers to underside of floors; |  |  | condition 4 130474 |  |  | to be developed |  | to be developed | to be developed |  |  |  | to be developed |  | to be developed | to be developed | to be developed | to be developed | to be developed | to be developed | R H
2.1 |  | Details of new rooflights; |  |  | condition 4 130474 |  |  | to be developed |  | to be developed | to be developed |  |  |  | to be developed |  | to be developed | to be developed | to be developed | to be developed | to be developed | to be developed | R H
2.2 |  | Detailed method statement for brick cleaning (internally and externally); |  |  | condition 4 130474 |  |  | to be developed |  | to be developed | to be developed |  |  |  | to be developed |  | to be developed | to be developed | to be developed | to be developed | to be developed | to be developed | R H
2.3 |  | Details of the proposed roof insulation; |  |  | condition 4 130474 |  |  | to be developed |  | to be developed | to be developed |  |  |  | to be developed |  | to be developed | to be developed | to be developed | to be developed | to be developed | to be developed | R H
2.4 |  | Detailed proposals of works to retain timber linings; |  |  | condition 4 130474 |  |  | to be developed |  | to be developed | to be developed |  |  |  | to be developed |  | to be developed | to be developed | to be developed | to be developed | to be developed | to be developed | R H
2.5 |  | Details of M&E including a Strategy setting out design parameters detailing locations for ducting within rooms and details of conduits on exposed walls; |  |  | condition 4 130474 |  |  | to be developed |  | to be developed | to be developed |  |  |  | to be developed |  | to be developed | to be developed | to be developed | to be developed | to be developed | to be developed | R H
2.6 |  | A Strategy for the location and detailing of all building services including electrics and plumbing, telecommunications, fire/security alarms, door intercom from the main entrance to each apartment, communal tv/satellite connections and aerials CCTV cameras (and associated cabling and equipment) and internal mail boxes; and |  |  | condition 4 130474 |  |  | to be developed |  | to be developed | to be developed |  |  |  | to be developed |  | to be developed | to be developed | to be developed | to be developed | to be developed | to be developed | R H
2.7 |  | A shadow gap detail which would provide a clear expression of new and original building fabric; |  |  | condition 4 130474 |  |  | to be developed |  | to be developed | to be developed |  |  |  | to be developed |  | to be developed | to be developed | to be developed | to be developed | to be developed | to be developed | R H
2.8 |  | Programme of Issue of Samples |  |  | condition 5 130474 |  |  | to be developed |  | to be developed | to be developed |  |  |  | to be developed |  | to be developed | to be developed | to be developed | to be developed | to be developed | to be developed | R H
2.9 |  | Programme of Detailed Works for 7KS |  |  | condition 4 130475/LO/2021 and comments from LPA |  |  | to be developed |  | to be developed | to be developed |  |  |  | to be developed |  | to be developed | to be developed | to be developed | to be developed | to be developed | to be developed | R H
Section 2 - Materials/Technical Submittals/Samples/Benchmarks Acceptance
2.1 |  | Selection of UKAS Accredited Test House |  |  | Insert relevant clause from the contract / specification |  |  | Document Check that correct certification held for scope of testing to be carried out |  | Prior to appointment | UKAS Accreditation covering scope of works |  |  |  | UKAS Schedule |  | N | Sub | LAB | R H | QM
2.2 |  | Approval of Permanent Materials |  |  | Insert relevant clause from the contract / specification |  |  | Review of product documentation to verify compliance with the specification |  | Prior to placing order | Compliant Material |  |  |  | Technical Submission |  | Y | Sub |  | R H | E
2.3 |  | Certification of Specific Permanent Materials |  |  | Insert spec clauses relevant to the materials required for the activity |  |  | Document review of Product Certification from UKAS body or equivalent |  | Prior to incorporating materials into the Works | Note here spec requirements (e.g. gradings, certificates required) |  |  |  | Compliance Certification |  | Y | Sub |  | R H | E/QM/ME
2.4 |  | Ensure materials delivered to site conform to order detail, grade, quantity, condition |  |  | Insert relevant clause from the contract / specification |  |  | Visual Inspection and Delivery ticket check |  | Each delivery | Correct material (as described on delivery note and as ordered), Free from damage and accompanied by appropriate certification |  |  |  | Delivery Notes / Certificates of Conformity |  | N | C | F | R | F
2.5 |  | Material Storage |  |  | Insert relevant clause from the contract / specification |  |  | Check that suitable storage area available |  | Before materials delivered to site | Suitable storage area, protected from damage and inclement weather |  |  |  | No Record |  | N/A | C | F | C | F / E
Section 3 - Off Site Works/ Mock-ups / Product Delivery
3.1
Section 4 - Construction
4.1 |  | Protection of works |  |  | ISO 9001 Preservation of Product |  |  | Check that completed work by others has been adequately protected |  | Before starting works | Suitable and sufficient protection in place. All operatives aware of other works |  |  |  | No Record |  | N/A | C | F
4.2 |  | Access systems (scaffolds and proprietary Formwork access) |  |  | Safety Standards Temporary Works Procedure |  |  | Access platforms to be signed off by competent person before being accessed |  | Before the platform is put to any use | Sign off by registered scaffolder or Temporary Works Co-ordinator or Supervisor |  |  |  | Scaffold certificate Permit as per temporary works procedure |  | N | I H | F | C H | TWC / E / F
4.xx |  | Final Inspection |  |  | Insert relevant clause from the contract / specification |  |  | Inspection with Subcontractor and client of completed works |  | On completion of activity or section of works | All works complete and outstanding works list compiled |  |  |  | Outstanding Works List compiled |  | N | I | SSR | I | SSR | I
4.xx |  | Protection of works |  |  | ISO 9001 Preservation of Product |  |  | Check that works carried out under this ITP are protected and that protection of others work is still in place |  | On completion of activity or section of works | Suitable and sufficient protection in place |  |  |  | No Record |  | N/A | C | F/E
Section 5 - Close out and Handover
5.1 |  | Close out of process, product and material nonconformities |  |  | Insert relevant clause from the contract / specification |  |  | Review against nonconformity register |  | On completion of activity or section of works | All nonconformities closed out |  |  |  | Closed nonconformities |  | Y | C | SSR | C | QM
5.2 |  | Close out of Outstanding Works |  |  | Insert relevant clause from the contract / specification |  |  | Review of outstanding works list |  | On completion of activity or section of works | All outstanding works items completed |  |  |  | Outstanding Works list closed out |  | Y | C | SSR | C | QM / E
5.3 |  | Red Line / As Built drawings |  |  | Insert relevant clause from the contract / specification |  |  | Check that red line / As Built Drawings are complete |  | On completion of activity or section of works | All red line / As Built Drawings complete and submitted |  |  |  | Red Line / As Built Drawings |  | Y | Sub | SSR | R | E / QM | R
5.4 |  | Records submitted |  |  | Insert relevant clause from the contract / specification |  |  | Check that required records complete and submitted to client |  | On completion of activity or section of works | All relevant records complete and submitted |  |  |  | Record pack approved by Client |  | Y | Sub | SSR | R | E / QM | R
5.5 |  | Certification |  |  | Insert relevant clause from the contract / specification |  |  | Submission and approval of certification |  | On completion of activity or section of works | Certificate submitted and accepted by Client |  |  |  | Certificate |  | Y |  |  | Sub | QM / SSR | R
5.6 |  | O&M Manuals and H&S File |  |  | Insert relevant clause from the contract / specification |  |  | All required documentation available and complete |  | On completion of activity or section of works | Documentation included in relevant section of manuals / files |  |  |  | O&M Manual / H&S Files |  | Y | Sub | SSR | R | E | R
SECTION 3 - QUALITY INSPECTION AND TEST PLAN CLOSEOUT
| The works covered by this Quality Inspection and Test Plan have been undertaken and completed in accordance with this Quality Inspection and Test Plan and associated method statements,procedures,specifications,drawings,design changes and site instructions. The supporting Quality Documentation outlined in this plan has been submitted and checked as complete. | [5 empty] | Subcontractors Representative |  | Sign: |  |  | Mountain Earth Representative |  | Sign: |  |  |  | Client Representative |  | Sign:
[9 empty] | Date |  |  |  |  | Date | [5 empty] | Date