## Sheet1
Habitat proposals | Broad timing for installation completion | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2040 | 2045 | 2050 | 2055
Urban tree planting | Winter 2025 / 2026 | These will be installed as per the approved landscape plans and planting plans | Record tree species Check canopy Check for adverse impact on tree health by human activities and there is no current regular pruning regime. Check / record height and spread. Record if natural ecological niches for vertebrates and invertebrates are present. Check percentage of canopy oversail | Record tree species Check canopy Check for adverse impact on tree health by human activities and there is no current regular pruning regime. Check / record height and spread. Record if natural ecological niches for vertebrates and invertebrates are present. Check percentage of canopy oversail | Record tree species Check canopy Check for adverse impact on tree health by human activities and there is no current regular pruning regime. Check / record height and spread. Record if natural ecological niches for vertebrates and invertebrates are present. Check percentage of canopy oversail | Record tree species Check canopy Check for adverse impact on tree health by human activities and there is no current regular pruning regime. Check / record height and spread. Record if natural ecological niches for vertebrates and invertebrates are present. Check percentage of canopy oversail | Carryout tasks as per 2030 if required | Carryout tasks as per 2030 if required | Carryout tasks as per 2030 if required | Carryout tasks as per 2030 if required | Carryout tasks as per 2030 if required | Monitor and implement any contingency measures | Monitor and implement any contingency measures | Monitor and implement any contingency measures | Monitor and implement any contingency measures | Target condition reached
Other neutral grassland | Winter 2025 / 2027 | Create bare soils with aspects, remove rich top soils and leave nutrient poor soils on the surface. Create areas of disturbance to seed into. Sowing in late summer/autumn (late August – October) or spring (April – May). Seeds surface sown at rate of 20kg/ha and firmed in using a roller. | Control annual weeds. For the first year of growth, cut to 5cm in May, then cut every 2 months or when sward reaches approximately 15cm. Stop cutting by August to allow wildflowers to seed. Final cut to 5cm will be in October. Remove all arisings from the area, dispose of in designated areas such as a compost heap. Remove encroaching scrub and bracken manually using hand tools. Annually create areas of bare ground or ‘scrapes’ covering 1% to 5% of total habitat area by manually scraping away vegetation with hand tools. These scrapes should be located in sunny areas such as south facing embankments. Annually monitor | From the second year onwards, cut to 5cm in March or April, then make a second cut to 5cm in October.Remove all arisings from the area, dispose of in designated areas such as a compost heap. Remove encroaching scrub and bracken manually using hand tools. Annually create areas of bare ground or ‘scrapes’ covering 1% to 5% of total habitat area by manually scraping away vegetation with hand tools. These scrapes should be located in sunny areas such as south facing embankments. Annually monitor | From the third year onwards, designate some areas to receive a cut to 5cm during August in order to produce a more varied habitat that will encourage different species of wildflower. Remove all arisings from the area, dispose of in designated areas such as a compost heap. Remove encroaching scrub and bracken manually using hand tools. Annually create areas of bare ground or ‘scrapes’ covering 1% to 5% of total habitat area by manually scraping away vegetation with hand tools. These scrapes should be located in sunny areas. Undertake quadrat sampling to identify the habitat type that is establishing and then number of species per m2 and in comparison to the mix type. Estimate percentage of bare ground, bramble and bracken cover. Identify the presence of any non-native invasive species. such as south facing embankments. Annually monitor. Undertake quadrat sampling to identify the habitat type that is establishing and then number of species per m2 and in comparison to the mix type. Estimate percentage of bare ground, bramble and bracken cover. Identify the presence of any non-native invasive species. | From the third year onwards, designate some areas to receive a cut to 5cm during August in order to produce a more varied habitat that will encourage different species of wildflower. Remove all arisings from the area, dispose of in designated areas such as a compost heap. Remove encroaching scrub and bracken manually using hand tools. Annually create areas of bare ground or ‘scrapes’ covering 1% to 5% of total habitat area by manually scraping away vegetation with hand tools. These scrapes should be located in sunny areas. Undertake quadrat sampling to identify the habitat type that is establishing and then number of species per m2 and in comparison to the mix type. Estimate percentage of bare ground, bramble and bracken cover. Identify the presence of any non-native invasive species. such as south facing embankments. Annually monitor. Undertake quadrat sampling to identify the habitat type that is establishing and then number of species per m2 and in comparison to the mix type. Estimate percentage of bare ground, bramble and bracken cover. Identify the presence of any non-native invasive species. | Target condition reached | Carryout tasks as per 2029 if required | Carryout tasks as per 2029 if required | Carryout tasks as per 2029 if required | Carryout tasks as per 2029 if required | Carryout tasks as per 2029 if required | Monitor and implement any contingency measures | Monitor and implement any contingency measures | Monitor and implement any contingency measures | Monitor and implement any contingency measures