## COOP Live
CO-OP LIVE
Biodiversity Management Plan 2025
|  |  | Spring |  |  | Summer |  |  |  | Autumn |  | Winter
TASK | Resource | Budget required | March | April | May | June | July | August | September | October | November | December | January | February
Short amenity grass
Overseed amenity grass with low growing wildflower species to diversify the sward (as directed by Niche) | additional |  |  | x | x |  |  |  |  | x | x
Raise height of cut to maximum height tolerable (for aesthetics) depending on the location | contract |  | x | x | x | x | x | x | x | x | x
Transition short grass to long grass where grass meets hedging or tree lines | contract |  |  | x
Scalp grass down to the soil in various locations in spring, particularly sunny aspects to create habitat for invertebrates such as ground nesting bees (Niche to advise on locations) | contract |  | x
Avoid using any fertilisers at all on short grass to maximise sward diversity and minimise nutrient impacts on site flora (also to reduce greenhouse gas emissions) | contract
Top dress areas of verge and grass banks with sand to reduce soil fertility and improve for wildflowers (recycled or waste sand from CFA) - as directed by Niche | additional
Plant flowering bulbs into turf areas including: daffodils, crocus, snakes head fritiliary | additional
Long grass areas
Areas of long grass to be cut on a three year rotation. All arisings to be piled up into habitat mounds on site and allowed to breakdown over winter with option to remove in the spring. | contract | [7 empty] | x
Mow paths for access (for maintenace and to encourage leisure) | contract |  |  | x | x | x | x | x | x
Regular litter removal to reduce hazards for wildlife | contract |  | x | x | x | x | x | x | x | x | x | x | x | x
Create patches of bare soil throughout long grass areas (strim to the ground) - dig over in some places | contract |  | x
Control non-native invasive species using manual methods | contract |  |  | x |  | x |  | x
Control extent of weeds including dock species and creeping thistle. Ragwort should NOT be removed. | contract |  |  |  | x |  | x |  | x
Add plug plants each year targeting pollinators inluding butterfly host plants (as directed by Niche) | additional |  |  | x
Select areas for alternative cutting use strimmers, brush cutters or scythes | contract |  |  | x |  | x |  | x
Wildflower areas
Cut and remove vegetation at least once per year in late summer after flowers have set seed. Twice per year if early flowering spring species are present. | contract |  | x | [5 empty] | x
Scarify and overseed with appropriate seed mix (as directed by Niche) - in autumn or spring | additional |  | x | [6 empty] | x
Scarify and sow yellow rattle into all wildflower areas in November | additional | [9 empty] | x
Strip small areas of bare soil for invertebrates | contract |  | x
Planting enhancements to support species of conservation concern (specific wildflower species as directed by Niche) | additional |  | x
Add plug plants each year targeting pollinators inluding butterfly host plants (as directed by Niche) | additional |  | x | x
Use local recyled sands to improve soil conditions of wildflower areas. | additional |  |  |  | x | x
Create deadwood and habitat piles for invertebrates | contract |  | x | x | x | x | x | x | x | x | x | x | x | x
Add bee posts and sand planters for front of house areas | additional
Ponds
Create a series of small wildlife ponds and ditches in back of house areas | additional |  | x |  | x |  | x |  | x
Plant with a variety of native marginal, aquatic and terrestrial flora (as specified by Niche) | additional |  |  |  |  | x
Add aggregate, rocks and boulders to pond margins to create refuges for wildlife | additional | [11 empty] | x | x
Hedges
Implement a three year rotational pruning programme allowing sections to remain uncut. Ensure different species are included in the rotation including beech, holly, yew, hawthorn, field maple, elder. | contract | [9 empty] | x | x | x | x
Allow vegetation to establish at the base of hedges in back of house areas (cease spraying) | contract
Replace dead plants with a variety of native hedge species including: hawthorn, blackthorn, field maple, hazel, holly, guelder rose, dog rose, damson, | additional | [9 empty] | x | x | x | x
Check progress of saplings every year and where planting has failed, replace in the following season. | contract | [8 empty] | x | x | x | x | x
Coppice hazel plants on 7 year rotation to produce timber for habitat creation such as deadhedging | additional
Allow hedges to grow out and upwards where feasible | contract
Retain all clippings from hedge pruning to create habitat piles and/or mulch, do not compost | contract
Regularly remove litter from the base of hedges including deeper areas in the winter to prevent ongoing annual build up of non-degradable litter pollution | contract
Scrub (nettles, bramble, self set trees)
Encourage the establishment of scrub areas on site including areas of nettles, brambles and self set trees. | contract |  | x |  | x |  | x
Rotational cut back and clear on a 5 year cycle to support regeneration and allow for deep litter removal | additional
Existing scrub areas require thorough litter scavenge in winter months when vegetation is minimal | contract | [9 empty] | x | x | x | x
Orchard Creation
Plant micro orchards where large amenity grass areas exists | additional |  | x | [5 empty] | x
Stake, tie and protect | additional
Mulch | additional |  | x | [5 empty] | x
Irrigate until establsihed | additional
Underplant meadow with flowering plants and bulbs | additional
Install seating | additional
Mow paths between trees for access | additional
Woodland tree belt (between arena and carpark)
Monitor for pest and diseases | contract |  | x
Leave dead trees as standing or fallen deadwood if they die and fall within the woodland. | contract |  | x
Coppice hazel on rotation and use timber to create deadwood features across site (as directed by Niche) | additional
Thin woodland to provide gaps for sunlight to reach the understory, prioritising coppicing of hazel. No more than 10% of canopy | additional | [9 empty] | x | x | x | x
Ringbark selected trees to create standing deadwood. | additional | [9 empty] | x | x | x | x
Create habitat piles with brash and timber. Leave some scattered throughout woodland. | additional | [9 empty] | x | x | x | x
Compliment understory with flowering woodland species. Include: Foxglove Digitalis purpurea, Wood Anemone Anemone nemorosa, Red Campion Silene dioica etc. Planted in early spring or early autumn | additional |  |  | x | x
Plant native woodland flowering bulbs including snowdrops, bluebells, winter aconite, wild garlic, | additional | [9 empty] | x
Install bird boxes for different species (as per direction by Niche) | additional | [9 empty] | x | x | x | x
Install bat boxes (as per direction by Niche) | additional | [9 empty] | x | x | x | x
Plant native bulb species including: bluebells, snowdrops, winter aconite, wood anemone, | additional | [9 empty] | x
Individual trees and stands of trees
Allow rings of long grass / vegetation to develop underneath individual trees and stands of trees. | contract |  |  | x
Scarify and overseed with native wildflower species | additional |  |  | x | [5 empty] | x
Plant additional trees prioritising native fruiting species such as rowan, crab apple and wild cherry | additional | [9 empty] | x | x | x | x
Alternatively plant up tree pits with ornamental planting scheme for pollinators | additional |  |  | x
Ornamental shrubs and flower beds
Develop shrub beds with new species and planting designs | additional
Plant (early spring early autumn) and monitor flowering species throughout the year to ascertain the best mix for other shrub beds to provide colour year round | additional |  |  | x | [5 empty] | x
Add additional habitat components including rocks, logs, habitat structures | additional
Leave ornamental grasses uncut (appropriate to species) over winter for aesthetic structure and invertebrate habitat | contract |  | x | [6 empty] | x | x | x | x | x
Use any cuttings to mulch bed (in ornamental fashion) and create habitat refuge structures | contract | [8 empty] | x | x | x
Leave some flower seed heads and stems standing through the winter for invertebrate habitat and bird food | contract |  | x | [6 empty] | x | x | x | x | x
Allow shrubs including ornamental hedges to flower before pruning. | contract |  | x |  |  |  |  | x | x | x | x | x | x | x
Avoid pruning shrubs with fruits or berries. Leaving this for wildlife in winter months. | contract |  | x |  |  |  |  | x | x | x | x | x | x | x
Manage sensitively for biodiversity allowing organisms such as fungi to fruit (mushrooms) without disturbance - Do not remove mushrooms in beds. | contract |  | x | [6 empty] | x | x | x | x | x
Plant flowering bulbs including: muscari, alliums, crocus and other species which support pollinators | additional
Carpark / hardstanding areas | additional
Create wildflower perimeter in front of hedge using waste/recycled aggregate | additional
Use gabion cages to create retaining habitat wall | additional
Integrate seating and planters in central reservation areas | additional
Add invertebrate structures such as bee posts and sand planters for ground nesting bees and other invertebrates | additional
Curate and install biodiversity signage | additional
Install bat towers within rear hedgerow | additional
Living Wall
Diversify planting to support wildlife particularly insects | contract
Determine feasiblity of habitat structures retrofitted to the wall | additional
Biological Recording programme / Ecological surveying
Set up a biological recording project for the site and engage stakeholders using iNaturalist | additional |  | x | x | x | x | x | x | x | x | x | x
Acoustic bird survey x 2- spring and winter - Using remote recording devices | additional |  |  | x | [8 empty] | x
Undetake series of invertebrate surveys including moth trapping | additional |  |  |  | x | x | x | x | x | x
Acoustic bat survey - using remove recording devices | additional | [5 empty] | x
Comission formal habitat survey for full extent of site (include BNG assessment) | additional
Comission protected species surveys to identify sensitve habitats and species | additional
Engagement Opportunitites
RSPB Big Garden Bird Watch | additional | [11 empty] | x
Big Butterfly Count - Staff sessions | additional | [5 empty] | x | x
Wildflower walks | additional |  |  |  | x | x | x | x | x
City Nature Challenge | additional |  |  | x
Butterfly Transects | additional |  |  | x | x | x | x | x | x | x
Bumblebee Transects | additional |  |  | x | x | x | x | x | x | x
Wildflower seed collection | additional | [8 empty] | x
Wildflower Posy Workshop | additional | [5 empty] | x | x | x
Daffodil Posy harvesting | additional |  | x | x | x
Introduction to iNaturalist | additional |  |  |  |  | x | x | x | x
Moth Mornings | additional |  |  |  |  | x | x | x | x
Bee walks | additional |  |  |  | x | x | x | x | x
Conservation Actions + New Habitat Creation
Install swift boxes and calling system - fixed to buildings or in tower form | additional | [9 empty] | x | x | x | x
Install Peregrine Nest Box on top of venue | additional | [9 empty] | x | x | x | x
Install more bird nest boxes each year - sparrows, swifts, swallows, starlings (as directed by Niche) | additional | [9 empty] | x | x | x | x
Clean and maintain bird nest boxes | additional | [9 empty] | x | x | x | x
Install bat towers or bat barns in back of house areas (canel side and rear of carpark) | additional | [9 empty] | x | x | x | x
Create new patches of wildflowers across the site in varied soil conditions and aspects | additional | [8 empty] | x
Utilise waste aggregates particularly sands to create sand mounds in sunny back of house areas including rear of carpark infront of hedgerow | additional |  |  |  | x | x
Use brash and branches to start creating deadhedges across site | additional |  | x |  | x |  | x |  | x |  | x |  | x
Plant new micro orchards around site (avoid areas prone to waterlogging) | additional |  | x | [7 empty] | x | x | x | x
Plant 30 new plant species per annum (native and cultivated) to support key invertebrate species and groups i.e. butterflies (as directed by Niche) - wildflowers, bulbs, shrubs and trees. | additional |  | x |  | x
Team training and development
Monthly biodiversity workshop or time spent with the team (Niche) | contract |  | x | x | x | x | x | x | x | x | x | x | x | x
Local site visits to RHS Garden Bridgewater etc. Spring, Summer, Autumn, Winter | contract |  |  | x |  |  |  | x |  | x |  |  | x
Quarterly plant ID challenge | contract |  |  | x |  |  |  | x |  | x |  |  | x
iNaturalist biological recording sessions | contract |  |  | x | x | x | x | x | x | x

## Summary (hidden)
Number of activities
| Complete | Past Due | Future Due | Total
0
0
0
0
0
0
0
0
0
0
0
0
0
Total | 0 | 0 | 0 | 0
| 0% | 0% | 0%

## Change Log (hidden)
Workstream | Activity | Action | Justification
Addition
Removal
Amendment