## Sheet1
Wythenshawe Park Multi Sports Hub User Relocation Plan
Existing Sports Facility User | Current usage | Requires Relocation (Y/N) | Relocation plan | Duration
Simply Cycling | Tues, Wed & Fri 9-12/ Sat 1-3 | Y | Relocation of sessions to Timperly, Longford Park and some sessions remaining at Wythenshawe Park bike trails. | Throughout construction (70 weeks) 9/6/2026 to 11/10/2027
NACRO | Various across the week | N | Can still be delivered from the park/ learn to ride area or led rides around thr park. | Throughout construction (70 weeks) 9/6/2026 to 11/10/2028
British Cycling/Pedal Party | various Mar-Oct (monthly) | N | Can still be delivered from the park/ learn to ride area or led rides around the Park. | Throughout construction (70 weeks) 9/6/2026 to 11/10/2029
Manchester Harriers | Tuesday and Thurday 6-8 | Y | Additonal off site training confirmed for Manchester Enterprise academy. Some sessions will continue from the park. | Throughout construction (70 weeks) 9/6/2026 to 11/10/2030
Sale Harriers | Monday- Thursday 7-9 | N | Utilising the wider park and other off site athletic venues at Longford Park, Manchester Regional Athletics Arena, and Crossford Park. | Throughout construction (70 weeks) 9/6/2026 to 11/10/2031
Winston Runners | Tues/ Thurs/ Sat | N | Utilise the wider park and other off site venues across the city with trails suibale for running. | Throughout construction (70 weeks) 9/6/2026 to 11/10/2032
Second Chance Cycling | Tue 10-12 | N | Selection of cycle routes available within park | Throughout construction (70 weeks) 9/6/2026 to 11/10/2033
Park Run | Sat 9am | N | This will not be affected and the run will continue within the wider site. | Throughout construction (70 weeks) 9/6/2026 to 11/10/2034
Wythenshawe Community Run | Sundays | N | This will not be affected and the run will continue within the wider site. | Throughout construction (70 weeks) 9/6/2026 to 11/10/2035
Baseball | March-October | N | Works to be undertaken outside of the Baseball season | Refer to construction phasing plan