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1. Introduction and Purpose
This Construction Management Plan has been prepared by Etec Contract Services Ltd in accordance with the planning condition attached to the planning permission for Wythenshawe Park Sports Hub. It draws upon the Construction Environmental Management Plan (CEMP) prepared by Etec (Ref: Rev 001, 21st September 2025) and the Arboricultural Method Statement (AMS) prepared by Arbtech Consulting Ltd (Ref: Arbtech AMS 01 Rev A, dated 26/09/2025), in accordance with BS5837:2012.
This document is submitted to Manchester City Council as Local Planning Authority (LPA) for written approval prior to the commencement of construction works. All construction activities shall be carried out strictly in accordance with this approved plan.
Etec Contract Services Ltd is registered with the Considerate Constructors Scheme (CCS) and is committed to being a considerate contractor, being aware of the needs of park visitors, neighbours and the environment throughout the works.
This plan has been prepared having regard to the requirements of Manchester City Council and addresses the following key areas: phasing and quantification of vehicular activity; vehicle routing within the site and on adjacent highway; contractor parking arrangements; a detailed Traffic Management Plan; a dilapidation survey commitment; parking management during construction; and a pedestrian and cycle management plan. Any requirements for licensing, hoarding and temporary traffic management will be agreed with the Council's Highways Applications and Network Resilience teams via Contact Manchester (Tel. 0161 234 5004 / highwaylicences@manchester.gov.uk).
2. Key Objectives
1. Protect retained trees and vegetation throughout the development in accordance with BS5837:2012 and the Arbtech AMS
1. Mitigate environmental and ecological risks including bats, breeding birds, and Baguley Brook
1. Ensure legal compliance (Wildlife & Countryside Act 1981, COSHH Regulations, BS5837:2012, BS3998:2010)
1. Define site protocols for environmentally responsible operations
1. Outline roles and responsibilities for environmental protection
1. Minimise impact on park users outside the redline site boundary
1. Comply with Manchester City Council's requirements as Local Planning Authority
1. Provide confirmation of parking arrangements and cycle link continuity during construction
3. Project Description and Site Information
3.1 Project Details
	Project
	Wythenshawe Park Sports Hub

	Contract No.
	J2976

	Address
	Wythenshawe Park, Wythenshawe Road, Manchester, M23 9RQ

	What3Words
	jumpy.salt.custom

	Client
	Alliance Leisure Services Ltd

	Principal Contractor
	Etec Contract Services Ltd

	Environmental Manager
	Arbtech (Claire Swinburn)

	Principal Designer
	Abacus (Ed Offer)

	GEFA
	1,445 m²

	GIFA
	1,365 m²

	Document
	Construction Management Plan – Rev 02

	Date
	May 2026


3.2 Building Description
The proposed development is a single-storey Sports Hub building comprising café, community rooms, GP and clinical rooms (10 no.), bike workshop, wet and dry changing facilities, accessible WCs, plant room and staff accommodation. Foundation type: mass concrete (GEN 3) strip and pad foundations to a minimum depth of 1,000 mm below existing ground level.
3.3 Site Context and Existing Conditions
The site is located within Wythenshawe Park to the south of Greater Manchester. The park lies within a residential area with housing estates to the north, south and west; the nearest residential property is approximately 450 m away. The park receives hundreds of visitors per day arriving by foot, bike and car.
The following features are present on or adjacent to the site (refer to Existing Site Plan 118165-NPS-ZZ-00-D-A-0801 Rev. P09):
1. Existing athletics track and changing building to the south/east will be closed during the works as park of the work is the track to be re-surfaced. These fall inside the red line boundary of the site.
1. Existing car park to the north
1. Existing mature trees and hedgerows of Categories A, B, C and U (per Arbtech AMS)
1. Existing woodland areas to the north, west and south
1. Baguley Brook running along the southern site boundary – sensitive watercourse. Although construction works are not anticipated to take place in proximity to the brook, its presence is noted as an environmental constraint. Silt fencing and spill kit provisions will be maintained as a precaution in accordance with Section 10.3 of this plan
1. Existing pump-track and learn-to-ride area – to be retained and remain in use throughout the works
1. Existing pedestrian footpaths crossing and adjacent to the site
1. Existing gate access points for maintenance and public use
1. Existing weightlifting and changing building subject to demolition – confirmed bat roost present (BERS, May 2025)
1. Foul water main sewer crossing the site with a 5 m easement either side of centreline (United Utilities)
1. Site levels generally flat, ranging from approximately 31.1 m to 33.0 m AOD
4. Key Project Parties
The key project parties and their contact details are set out below:
	Role
	Environmental Manager
	Principal Designer
	Principal Contractor

	Organisation
	Arbtech
	Abacus
	Etec Contract Services Ltd

	Address
	New Broad Street House, New Broad St, London EC2M 1NH
	4th Floor Cotton House, Queen Street, Manchester M2 5HS
	Suite 7, Elmhurst, 98/106 High Rd, South Woodford, London E18 2QH

	Contact
	Claire Swinburn
	Ed Offer
	Lee Jones

	Telephone
	01244 661170
	0845 365 1350
	07581 469044



Client – Alliance Leisure Services Ltd: Contact To Be Agreed | T: TBC
MCRactive Facility Strategy & Capital Projects Lead – Manchester City Council: Louise Harding | C/O House of Sport, Etihad Campus, Gate 13, Rowsley Street, Manchester, M11 3FF
NOTE: The client in the contract is Alliance Leisure Services Ltd. Louise Harding’s role is as MCRactive Facility Strategy & Capital Projects Lead for Manchester City Council. Both parties to confirm contractual client designation prior to finalising this document.
5. Environmental Constraints and Risk Register
The following constraints and risks have been identified from the site conditions, CEMP (Etec, Rev 001), Arbtech AMS and ecological surveys. Control measures shall be implemented and maintained throughout the works.
	Feature / Constraint
	Risk
	Control Measure

	Retained Trees
	Damage from machinery or materials
	Heras-type protective fencing to BS5837:2012, exclusion zones, signage: ‘Tree Protection Area – Keep Out’

	Root Protection Areas (RPAs)
	Compaction or root damage
	No entry without Project Arboriculturist approval; no excavation unless stated in AMS; cellular confinement systems, scaffold boards or matting for temporary access

	Protected Species – Bats
	Disturbance to confirmed roost (10 emergences recorded, BERS 8 May 2025)
	No works to maintenance unit until Natural England licence obtained; 3 surveys required; seasonal constraints and ECoW supervision; 2km BRD search via Greater Manchester LRC

	Protected Species – Breeding Birds
	Harm/disturbance to active nests
	Pre-works nesting check by qualified ecologist during breeding season (March–August); 5–10m buffer zones around active nests; no works in buffer until ecologist confirms clear

	Baguley Brook (southern boundary)
	Runoff, sedimentation or contamination
	Although construction works are not anticipated near the brook, a precautionary 10m exclusion buffer will be maintained; temporary silt fencing along boundary retained; spill kits adjacent to all fuel/chemical storage; daily site manager inspections of boundary

	Watercourse / Pollution
	Contamination from spills / concrete washout
	Bunded storage areas; designated washout zones away from watercourse; spill kits on site; emergency containment procedures in place

	Residential Properties (nearest ~450m)
	Dust and noise pollution
	Dust suppression (misting/damping), wheel wash, covered skips, wind-direction monitoring; noise restricted to permitted hours; acoustic barriers along residential boundary

	Asbestos (existing buildings)
	Exposure during demolition
	Pre-demolition asbestos survey before works to Weightlifting/Changing Room building; licensed removal contractor; consignment notes; toolbox talks to all operatives

	Existing Athletics Track, Learn-to-Ride and Park Users
	Disruption / safety risk to public
	Site hoarding/fencing to separate construction from public; banksman at access gates; maintained pedestrian and cycle routes; signage throughout


6. Scope of Construction Works
The construction scope is based on the Proposed Ground Floor Plan (118165-NPS-ZZ-00-D-A-0300 Rev. P17), Foundation Plan (QPM-DR-S-001 Rev. T03) and Site Set Up – Construction Phase drawing (Etec). Key construction activities include:
1. Establishment of site compound, hoarding and welfare facilities (as shown on Site Set Up drawing)
1. Bulk earthworks and site preparation
1. Foundation construction: mass concrete (GEN 3) strip foundations (600 mm wide) and pad foundations (600x600 mm to 1,400x1,400 mm) at minimum 1,000 mm below existing ground level, to Building Control inspector’s approval
1. Ground-bearing concrete floor slab (minimum C35 grade)
1. Superstructure construction (steel frame per subcontract tender package)
1. Roofing works
1. External envelope – walls (brick/blockwork), windows and doors
1. Internal fit-out: café, community rooms, GP/clinical rooms (10 no.), bike workshop, wet and dry changing facilities, accessible WCs, plant room, staff accommodation and ancillary spaces
1. Mechanical and electrical services installation (refer to MEP drawings)
1. External works: access to pitches, bike hub area, landscaping, drainage and statutory service connections
1. Landscaping and tree planting in accordance with BS4428, the AMS and BNG requirements (including wildflower meadows south of Baguley Brook)
7. Site Set Up – Construction Phase
Refer to Site Set Up – Construction Phase drawing (Etec). The site compound layout is as follows:
1. Canteen, drying room, WC block, smoking shelter – welfare facilities to the northwest of the construction zone
1. Site office and meeting room
1. Contractor parking area
1. Storage containers – two no., located centrally within the compound area, outside all RPAs and fenced zones
1. Skip / waste separation area – designated waste compound within the hoarded zone, positioned for HGV collection access
Access and vehicle routing:
1. Main Gate: northern access from Wythenshawe Road – primary entry
1. Etec Site Entrance Gate: segregated contractor access into the compound and construction zone
1. Pitch Contractors Site Entrance Gate: separate access for pitch-related contractor vehicles
1. Heavy Vehicle Route: defined haul route running along the eastern boundary, separated from park users
1. Hoarding/fencing forms the full perimeter of the construction zone
1. Existing pump-track and learn-to-ride area to the south to be retained and protected throughout construction, with maintained public access
8. Arboricultural Protection – Construction Phase
8.1 Tree Protection Fencing
Tree protection fencing installed during the demolition phase will be maintained throughout the construction phase. All fencing to BS5837:2012 using Heras-type fencing, with ‘Tree Protection Area – Keep Out’ signage maintained.
8.2 Root Protection Areas (RPAs)
1. No entry into RPAs without prior written approval from the Project Arboriculturist
1. No excavation within RPAs unless specified in the AMS
1. Excavations near trees supervised by Arboriculturist – hand tools or air spade only
1. No plant, storage, fires or vehicles within RPAs
1. Cellular confinement systems, scaffold boards or matting for any approved temporary access
8.3 Sequencing of Tree-Related Works
1. Verify all tree protection fencing intact from demolition phase; replace/repair as required
1. Construction plant to observe tree protection exclusion zones at all times
1. Concrete washout and material storage areas maintained outside all RPAs and fenced zones
1. Final arboricultural inspection on completion of construction
1. Removal of fencing
1. Landscaping, replacement planting and wildflower meadow installation
1. Minimum 5-year maintenance period for all new trees
9. Ecological Protection – Construction Phase
9.1 Bat Roost – Post Demolition
Following completion of demolition of the roost-bearing structure in accordance with the Natural England licence, bat mitigation and compensation measures (as detailed in the licence) will be implemented during the construction phase. The ECoW will confirm compliance with licence conditions throughout.
9.2 Breeding Birds
1. Pre-works nesting bird check by a suitably qualified ecologist before any vegetation clearance during the breeding season (March–August)
1. 5–10 m buffer zones around any active nests; no works until ecologist confirms nest is no longer in use
1. Ecological checks enforced if construction works must proceed during the breeding season
1. Toolbox talks on legal protections and escalation procedure for all operatives
10. Construction Phase Controls
10.1 Machinery Access
1. No plant within RPAs without approved ground protection and Arboriculturist supervision
1. Storage areas located outside all RPAs and fenced zones
1. Excavation near trees: supervised by Arboriculturist; hand tools or air spade only
10.2 Concrete Washout and Spill Management
1. Designated concrete washout areas directly into concrete skips, located minimum 15 m from Baguley Brook
1. Spill kits on site adjacent to all refuelling and chemical storage areas
1. All spills to be contained and reported immediately to the Site Manager and Environment Agency if watercourse is at risk
10.3 Watercourse Protection – Baguley Brook
Whilst construction works are not anticipated to take place in direct proximity to Baguley Brook, the following precautionary measures will be maintained throughout the construction phase given the brook’s proximity to the southern site boundary:
1. A precautionary 10 m exclusion buffer from Baguley Brook will be observed for all plant, materials and excavations should any works approach the southern boundary
1. Temporary silt fencing maintained along the southern site boundary as a precautionary measure
1. No discharge or concrete washout within 15 m of Baguley Brook
1. Site manager to perform periodic inspections of the buffer zone and silt fencing
1. Emergency procedures in place to contain and report any pollution events to the Environment Agency (0800 807060)
10.4 Foundation Works
1. All proposed foundations to be taken to competent ground level at minimum 1,000 mm below existing ground level, to Building Control inspector’s approval
1. Engineer to be notified immediately of any variations to reported ground conditions or if foundation depths substantially exceed minimum depths
1. All obstructions, old foundations and disused sewers to be removed for the extent of foundation works and backfilled to engineer’s approval
1. No vibratory works within the United Utilities 5 m sewer easement without prior agreement
11. Noise and Vibration Control
11.1 Working Hours
1. Monday to Friday: 08:00 – 18:00
1. Saturday: 08:00 – 13:00
1. Sundays and Bank Holidays: No works
11.2 Noise Mitigation
1. All plant and equipment maintained in good working order with silencers and acoustic covers
1. Temporary acoustic barriers or hoarding erected along the boundary facing residential properties
1. Powered mechanical plant switched off when not in active use
1. Toolbox talks to reinforce site-wide noise awareness
1. Compliance with BS5228 Parts 1 and 2
11.3 Vibration
1. Vibratory compaction plant selected and operated to minimise ground-borne vibration
1. No vibratory works within the United Utilities 5 m sewer easement without prior agreement
1. Vibration monitoring adjacent to sensitive receptors if percussive or high-vibration activities are proposed
12. Dust Control
1. Water suppression (misting, damping down) during dry periods
1. Wheel wash facilities at all site egress points
1. Covered skips and material stockpiles
1. Roads and hard standings swept daily as a minimum
1. Monitoring of wind direction to reduce drift toward residential areas and Baguley Brook
1. Compliance with IAQM Guidance on the Assessment of Dust from Demolition and Construction (2014)
13. Waste Management – Construction Phase
13.1 Waste Hierarchy and Objectives
The waste hierarchy will be applied throughout: Reduce, Reuse, Recycle, Recover, Dispose.
1. Prevent unnecessary waste generation through take-off reviews and efficient material ordering
1. Use of prefabricated components to reduce site waste
1. Returnable packaging and supplier take-back schemes where available
1. Maximise reuse, recycling and material recovery
1. Ensure legal and responsible disposal of non-recyclable waste
13.2 Segregation and Storage
Waste will be segregated at source in the dedicated skip/waste separation area (refer to Site Set Up drawing):
1. Inert waste (concrete, bricks) – segregated skip
1. Non-hazardous waste (timber, packaging) – segregated skip
1. Hazardous waste (contaminated soils) – handled by licensed contractor with consignment notes
1. Clearly labelled skips provided for each waste stream; all operatives briefed via toolbox talks
1. All waste carriers licensed with the Environment Agency; WTN or Consignment Note for every load leaving site
1. Site Waste Management Log maintained and audited weekly by Site Manager
1. Waste volumes and recycling rates reported to Manchester City Council as part of environmental monitoring
14. Parking and Traffic Management
14.1 Contractor Parking During Construction
A designated contractor parking area is provided within the site compound as shown on the Site Set Up – Construction Phase drawing. No construction vehicles are to park on the public highway or obstruct park access routes. All deliveries to be pre-booked and managed to avoid congestion.
14.2 Park Visitor Parking During Construction
The existing car park to the north of the site is anticipated to remain available to park visitors throughout the construction works. Etec will liaise with Manchester City Council and Alliance Leisure prior to commencement to confirm parking arrangements and to agree a robust management system to maintain adequate visitor parking throughout the programme. Any temporary displacement of car parking will be subject to prior agreement with Manchester City Council.
14.3 Vehicular Phasing and Activity
The approximate vehicular movements for the main construction phases are as follows:
	Phase
	Approximate HGV Movements / Week
	Notes

	Groundworks / Foundations
	15–20 two-way
	Concrete deliveries, spoil removal

	Steel Frame
	5–10 two-way
	Structural steel, plant

	Superstructure / Envelope
	10–15 two-way
	Brickwork, roofing materials

	Fit-out / MEP
	5–10 two-way
	Services, finishes, equipment

	External Works / Landscaping
	5–10 two-way
	Drainage, planting, hard landscaping


All HGVs to use the defined heavy vehicle route as shown on the Site Set Up drawing. Swept-path assessments for refuse lorry and fire truck / ambulance access have been undertaken (refer to drawings QPMDRC910 Rev T03 and QPMDRC912 Rev T03).
14.4 Pedestrian and Cycle Management
Existing pedestrian footpaths crossing and adjacent to the site will be maintained or suitable alternative routes provided throughout the works. The existing cycle links through and around Wythenshawe Park will remain open. The learn-to-ride area will remain in operation throughout the works and will be physically separated from the construction zone by hoarding/fencing. A pedestrian and cycle management plan will be agreed with Manchester City Council prior to commencement and updated as the programme develops. Signed diversionary routes will be provided where any path is temporarily closed. Please see schedule below in regards to active clubs.

[image: ]

15. Sheeting of Construction Vehicles
1. All vehicles leaving site carrying construction materials, spoil or waste to be sheeted or covered before leaving the site
1. Vehicles to pass through wheel wash facilities at site egress before entering the public highway
1. Site access road swept and inspected daily as a minimum
1. Any spillages onto the public highway to be cleared immediately
1. Contractor to maintain a vehicle check register to ensure compliance
16. Landscaping and Restoration
1. All landscaping works to follow BS4428 and the AMS recommendations
1. Replacement planting to compensate for any tree removals, in accordance with the approved landscaping design
1. Wildflower meadows to the south of Baguley Brook to be established in line with Biodiversity Net Gain (BNG) requirements
1. Minimum 5-year maintenance period for all new trees
1. Final landscaping to be confirmed to the satisfaction of the Project Arboriculturist and Manchester City Council
17. Labour Resourcing and Social Value
Etec Contract Services Ltd is committed to creating a cleaner, greener, fairer and more prosperous borough. The following local employment and supply chain initiatives will be delivered:
17.1 Site-Based Local Employment (Full Time)
1. 1 no. Project Manager
1. 1 no. Site Manager
1. 1 no. Commercial Surveyor
1. 2 no. Site Labourers
1. 1 no. Traffic / Logistics Manager
17.2 Local Subcontract Tender Packages
The following packages will be tendered to local businesses in or around the Wythenshawe / Manchester area:
1. Ground Works
1. Steel Frame
1. External Windows and Doors
1. General Building / Brickwork
1. Roofing
1. Drylining
1. Painting
1. Carpentry / Joinery
1. Flooring
1. Landscaping
18. Roles, Responsibilities and Site Management
	Role
	Organisation
	Responsibility

	Site Manager
	Etec Contract Services Ltd
	Overall environmental compliance, day-to-day implementation of this plan, complaint handling, daily inspections

	Project Manager
	Etec Contract Services Ltd
	Programme management, liaison with Manchester City Council and LPA

	Commercial Surveyor
	Etec Contract Services Ltd
	Waste transfer documentation, subcontractor compliance

	Traffic / Logistics Manager
	Etec Contract Services Ltd
	Vehicle management, delivery scheduling, banksman coordination

	Project Arboriculturist
	Arbtech
	Oversee all tree protection measures, supervise high-risk works within or near RPAs, arboricultural inspections at key stages

	Ecological Clerk of Works (ECoW)
	Arbtech
	Ecological advice and on-site checks, nesting bird surveys, bat roost licence compliance, escalation procedure

	Environmental Manager
	Arbtech (Claire Swinburn)
	Environmental oversight and compliance monitoring

	Principal Designer
	Abacus (Ed Offer)
	CDM coordination, design-stage environmental requirements

	All Operatives
	All subcontractors
	Adhere to site environmental rules, attend inductions and toolbox talks, report any ecological or environmental findings immediately


18.1 Inductions and Toolbox Talks
All operatives will receive a site induction covering environmental protection prior to commencing work. Toolbox talks will be delivered on:
1. Tree protection and fencing requirements
1. Wildlife legislation (bats, nesting birds, Wildlife & Countryside Act 1981)
1. Spill response procedures
1. Watercourse protection and Baguley Brook buffer protocols
1. Dust suppression methods and neighbour/park user awareness
1. Noise mitigation responsibilities and working hours
1. Waste handling and segregation protocols
19. Monitoring, Supervision and Reporting
1. Arboricultural inspections at key stages: before construction, during critical works (excavations near trees), and on completion
1. Inspection reports logged and made available for audit
1. Non-compliance recorded and rectified immediately
1. Site Manager to conduct weekly checks on waste segregation, storage and housekeeping
Daily inspection checklist to include:
1. Tree fencing and ground protection integrity
1. Baguley Brook 10 m buffer compliance (precautionary)
1. Dust generation areas and suppression measures
1. Noise levels near residential boundaries
1. Wheel wash operation and road sweeping
1. Waste segregation and skip labelling
1. Any ecological findings
Complaints from park users, neighbours or Manchester City Council to be logged, investigated and responded to within 24 hours. A copy of this approved plan to be kept on site at all times.
20. Emergency Contact Details
	Role / Organisation
	Contact Name
	Contact Number

	Client – Alliance Leisure Services Ltd
	To Be Agreed
	T: TBC

	MCRactive Facility Strategy & Capital Projects Lead – Manchester City Council
	Louise Harding
	C/O House of Sport, Etihad Campus, Gate 13, Rowsley Street, Manchester, M11 3FF

	Environmental Manager – Arbtech
	Claire Swinburn
	01244 661170

	Principal Designer – Abacus
	Ed Offer
	0845 365 1350

	Principal Contractor – Etec Contract Services Ltd
	Lee Jones
	07581 469044

	Site Manager – Etec (24hr site number)
	TBC prior to commencement
	TBC

	Project Arboriculturist / ECoW – Arbtech
	Alan Thompson
	07703 676216

	United Utilities (sewer / water emergency)
	—
	0345 672 3723

	Environment Agency (pollution incidents)
	—
	0800 807060 (24hr)

	Health and Safety Executive
	—
	0300 003 1647

	Manchester City Council – Planning / LPA
	Steve McCombie
	0161 234 4607

	Emergency Services
	—
	999


A dedicated site telephone number will be established and communicated to Manchester City Council, park management and local residents prior to commencement, displayed prominently at the site entrance and monitored during all working hours.
21. Considerate Constructors Scheme
1. Etec Contract Services Ltd is registered with the Considerate Constructors Scheme (CCS) – CCS charter to be displayed on site hoarding
1. Regular CCS audits throughout the construction phase
1. Dedicated community contact number and regular communication with park management and residents
1. Compliance with the CCS Code of Considerate Practice in all aspects of the works
Appendix A – Reference Drawings
	Drawing Title
	Drawing Number / Revision

	Proposed Ground Floor Plan
	118165-NPS-ZZ-00-D-A-0300 Rev P17

	Existing Site Plan
	118165-NPS-ZZ-00-D-A-0801 Rev P09

	Site Location Plan
	118165-NPS-ZZ-00-D-A-0802 Rev P06

	Foundation Plan
	QPM-DR-S-001 Rev T03

	Vehicle Swept Path – Refuse Lorry
	QPMDRC910 Rev T03

	Vehicle Swept Path – Fire Truck and Ambulance
	QPMDRC912 Rev T03

	Site Set Up – Demolition Phase
	Etec / Wythenshawe Park Rev 01

	Site Set Up – Construction Phase
	Etec / Wythenshawe Park Rev 01


Appendix B – Reference Documents
	Reference Document
	Reference Number / Date

	Arboricultural Method Statement (AMS) – Arbtech Consulting Ltd
	Arbtech AMS 01 Rev A, 26/09/2025

	Bat Emergence and Re-entry Survey (BERS)
	8th May 2025

	Construction Environmental Management Plan (CEMP) – Etec
	Rev 001, 21st September 2025

	BS5837:2012 – Trees in Relation to Design, Demolition and Construction
	British Standard

	BS3998:2010 – Tree Work Recommendations
	British Standard

	BS4428 – Code of Practice for General Landscape Operations
	British Standard

	Wildlife & Countryside Act 1981 (as amended)
	Legislation

	Control of Substances Hazardous to Health (COSHH) Regulations 2002
	Legislation

	IAQM Guidance on Dust from Demolition and Construction (2014)
	Guidance

	BS5228 Parts 1 & 2 – Noise and Vibration Control on Construction Sites
	British Standard
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Existing Sports Facility User Current usage  Requires Relocation (Y/N) Relocation plan Duration

Simply Cycling  Tues, Wed & Fri  9-12/ Sat 1-3  Y Relocation of sessions to Timperly, Longford Park and some 

sessions remaining at Wythenshawe Park bike trails.

Throughout construction  (70 weeks)

9/6/2026 to 11/10/2027

NACRO Various across the week N Can still be delivered from the park/ learn to ride area or led 

rides around thr park.

Throughout construction  (70 weeks)

9/6/2026 to 11/10/2028

British Cycling/Pedal Party various Mar-Oct (monthly) N Can still be delivered from the park/ learn to ride area or led 

rides around the Park.

Throughout construction  (70 weeks)

9/6/2026 to 11/10/2029

Manchester Harriers Tuesday and Thurday 6-8  Y Additonal off site training confirmed for Manchester 

Enterprise academy. Some sessions will continue from the 

park. 

Throughout construction  (70 weeks)

9/6/2026 to 11/10/2030

Sale Harriers Monday- Thursday 7-9 N Utilising the wider park and other off site athletic venues at 

Longford Park, Manchester Regional Athletics Arena, and 

Crossford Park.

Throughout construction  (70 weeks)

9/6/2026 to 11/10/2031

Winston Runners Tues/ Thurs/ Sat N Utilise the wider park and other off site venues across the city with trails suibale for running. Throughout construction  (70 weeks)

9/6/2026 to 11/10/2032

Second Chance Cycling  Tue 10-12 N Selection of cycle routes available within park Throughout construction  (70 weeks)

9/6/2026 to 11/10/2033

Park Run Sat 9am  N This will not be affected and the run will continue within the 

wider site. 

Throughout construction  (70 weeks)

9/6/2026 to 11/10/2034

Wythenshawe Community Run Sundays N This will not be affected and the run will continue within the 

wider site. 

Throughout construction  (70 weeks)

9/6/2026 to 11/10/2035

Baseball March-October N Works to be undertaken outside of the Baseball season Refer to construction phasing plan


