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Planning Tracker	

	Project Name:

	Cross Lane, Gorton

	Job No:

	3809
	Local Authority:
	Manchester City Council

	Client:
	Southway Housing Trust
	Date of grant of Permission:
	20/09/2023

	Contractor:
	R&M Property Group
	Planning Permission Reference:
	136203/FO/2023

	
	
	Tracker Last Issued:
	17/04/2026



►► See relevant approval notices and refer to these documents for precise wording of the conditions ◄◄

	Action Required
	No Action Required
	Discharged

	Pre-Occupation
	
	


		
Cond 3, 4, 5, 6, 8, 10, 11 CDN/24/0362 | Application to discharge conditions 3 (Materials), 4 (Construction Management Plan), 5 (Highway Works), 6 (Waste Management), 8 (Drainage), 10 (Noise Impact Statement) and 11 (EV Charging) attached to planning permission 136203/FO/2023 | Land At Junction Of Cross Lane, Chapman Street And Roxburgh Manchester

Cond 4, 5, 8, 9 CDN/24/0736 | Discharge of conditions 4 (Construction Environment Management Plan), 5 (Highway works), 8 (Drainage) and 9 (Drainage Maintenance Scheme) from planning approval reference 136203/FO/2023 | Land At Junction Of Cross Lane, Chapman Street And Roxburgh Street Manchester

NMA Application (Fence Lines) 141911/NMC/2025 | Non-material amendment to planning permission reference 136203/FO/2023 to allow for the reconfiguration of rear gardens / fence lines to provide individual private spaces for residents | Land At Junction Of Cross Lane, Chapman Street And Roxburgh Street Manchester

Cond 13, 14, 15 CDN/25/0283 | Discharge of condition nos. 13 ( Landscaping), 14 (Bicycle storage),15 (Biodiversity enhancements) attached to planning permission reference 136203/FO/2023. | Land At Junction Of Cross Lane, Chapman Street And Roxburgh Manchester

NMA Application (Plot 8 Parking) 143892/NMC/2025 | Non Material Change to planning permission 136203/FO/2023 to allow removal of plot 8 parking space and addition of one space to main central parking block, plot 8 parking space replaced with grass | Land At Junction Of Cross Lane, Chapman Street & Roxburgh Street Manchester

Cond 10, 19, 24 CDN/26/0070 | Discharge of Conditions 10 (Noise), 19 (SBD) and 24 (External Equipment) attached to Planning Permission referenced 136203/FO/2023. | Land At Junction Of Cross Lane, Chapman Street And Roxburgh Manchester M18 8WA

	Condition No 1: Commencement
	Date
	Action By

	1.1
	The development must be begun not later than the expiration of three years beginning with the date of this permission.

	
	


   
	Condition No 2: Drawing Numbers
	Date
	Action By

	2.1
	The development hereby approved shall be carried out in accordance with the following drawings and documents:

100- Site Location Plan- received 25th May 2023
102 Rev B- Site Clearance Plan- received 25th May 2023
105 Rev J- Proposed Site Plan - received 14th July 2023
107 Rev C- Proposed Boundary Treatment- received 14th July 2023
115 Rev A- Proposed Floor Plan and Elevations 1 bed 2 person cottage flat-received 25th May 2023
120 - Proposed Floorplans and Elevations 2 bed 3 person house- received 25th May 2023
Affordable Housing Statement-received 8th February 2023
Design and Access Statement- received 8th February 2023

	
	

	2.2
	NMA Application Approved:

SPECIFIED PLANS 
The development hereby approved shall be carried out in accordance with the following drawings and documents:
a. Drawing - Site Plan 04 Feb 2025 105 L PROPOSED
b. Drawing - Proposed 15 Jan 2025 107 D BOUNDARY TREATMENT PLAN

	11.02.25
	MCC

	2.3
	NMA Application Approved:

The development hereby approved shall be carried out in accordance with the following drawings and documents: 

100- Site Location Plan- received 25th May 2023
102 Rev B- Site Clearance Plan- received 25th May 2023 
105 Rev M- Proposed Site Plan - received 3rd September 2025 
107 Rev E- Proposed Boundary Treatment- received 3rd September 2025 110 Rev D- Street Elevations-received 3rd September 2025 
115 Rev A- Proposed Floor Plan and Elevations 1 bed 2 person cottage flat-received 25th May 2023 
120 - Proposed Floorplans and Elevations 2 bed 3 person house- received 25th May 2023
Affordable Housing Statement-received 8th February 2023 Design and Access Statement- received 8th February 2023

	01.10.25
	MCC


   
	[bookmark: _Hlk159311503]Condition No 3: Materials
	Date
	Action By

	3.1
	Before the commencement of above ground construction works, samples and specifications of all materials to be used on all external elevations of the development have been submitted to and approved in writing by the City Council as local planning authority. The development shall be fully implemented in accordance with the approved details, which shall be maintained in situ thereafter.

	
	RM

	3.2
	File submitted:

3809_3810_BTP_Cross Lane & Varey Street Materials Tracker 18.04.24

	18.04.24
	BTP

	3.3
	The following materials as submitted and shown on the materials tracker received 3rd of May 2024 are considered acceptable and condition 3 can be discharged in full.

External Main Facing Materials Bricks
· Manchester Bricks Main facing brick: Salford Smooth Red (right hand smooth brick) 
Feature brick: 
· Calderwood Claret (left hand textured brick) 
Roof 
· Sandtoft Calderdale Edge Tile (Concrete)- Grey 
Windows 
· PVC RAL7016 - Grey 
Fascia and Soffits 
· Black Composite GRP 
External Doors PVC Casement Window & Swing Door Profile: 
· Anthracite grey grained foil external on smooth white base & smooth white internalGRP faced, external black finish with grey RAL7016 frame
Rainwater Goods 
· Black PVC
Entrance Canopy 
· Glass and Stainless-steel brackets 
External Materials 
· Car Parking Black Tarmac 
· Access Path Concrete 
· Fencing C/B Timber Fence

	25.07.24
	MCC


   
	[bookmark: _Hlk159311510]Condition No 4: Construction Management Plan
	Date
	Action By

	4.1
	Prior to the commencement of the development hereby approved, a detailed construction management plan outlining working practices during development shall be submitted to and approved in writing by the local planning authority, which for the avoidance of doubt should include:

· Display of an emergency contact number; 
· Details of wheel washing; 
· Compound locations where relevant;
· Location, removal and recycling of waste;
· Routing strategy and swept path analysis;
· Parking of construction vehicles and staff;
· Sheeting over of construction vehicles.
· Parking of construction vehicles and staff;
· Dust suppression measures.

Development shall be carried out in accordance with the approved construction management plan upon commencement of authorised works.

	
	RM

	4.2
	File submitted:

Cross Lane and Varey St - Construction Environmental Management Plan

	18.04.24
	BTP

	[bookmark: _Hlk172886989]4.3
	Insufficient information has been provided to enable discharge of condition 4 Construction Management. This condition is therefore refused for lack of the following information: The applicant should be advised to make contact with the council's Highway Network Management teams by email highwaynetworkmanagement@manchester.gov.uk
highwaylicences@manchester.gov.uk

to discuss the following: 

· Pedestrian and traffic management plans are required to show: 
· Effect on vehicular and pedestrian movement
· Are there any temporary road/footway closures or diversions, including Section 50, required to facilitate the development? 
· Are works to the back of kerb or right on the kerb edge? 
· Any requirements for licensing, hoarding / scaffolding, skips.
· Are new utility connections, i.e new electricity supply, required? if so, where will these be coming from

	25.07.24
	MCC

	4.4
	Files submitted:

· CPP Cross Lane Varey St DRAFT Rev 02
· Cross Lane and Varey St Construction Environmental Management Plan

	31.07.24
	BTP

	4.5
	The Construction, demolition and management plan and construction phase plan by R and M property group received 8th August 2024 have been assessed and are sufficient to enable the discharge condition 4.

	19/11/24
	MCC



	[bookmark: _Hlk159311527]Condition No 5: Highways Works
	Date
	Action By

	5.1
	Before the commencement of above ground construction works, details of highways works to Cross Lane that are required as part of the implementation of the development, for the avoidance of doubt, including:
Footway reinstatement on Cross Lane and installation of dropped kerbs for driveway access from Cross Lane shall be submitted to and approved in writing by the City Council as local planning authority. 

The development shall not be occupied until the works have been constructed in accordance with the approved details, which shall be maintained in situ at all times thereafter.

	
	SCP

	5.2
	Drawings submitted:

SCP-230871-S278-0000-001 - Rev A - S278 General Arrangement
SCP-230871-S278-0200-001 - Rev A - S278 Site Clearance
SCP-230871-S278-0700-001 - Rev A - S278 Surface Finishes and Kerbing
SCP-230871-S278-1200-001 - Rev A - S278 Signing and Lining
SCP-230871-S278-4000-001 - Rev A - S278 Standard Details

	18.04.24
	BTP

	[bookmark: _Hlk172887066]5.3
	Condition 5 cannot be discharged for the following reason: 

A Section 278 application for highways works has not yet been received. This should be undertaken through the Manchester City Council Highways Statutory Approvals team so that a process can be determined and taken forward. 

The following link provides access: https://www.manchester.gov.uk/directory_record/451887/permission_to_work_on_the_h ighways_-_section_278_agreement

	25.07.24
	MCC

	5.4
	Files submitted:

SCP-230871-S278-0000-001 - Rev A - S278 General Arrangement
SCP-230871-S278-0200-001 - Rev A - S278 Site Clearance
SCP-230871-S278-0700-001 - Rev A - S278 Surface Finishes and Kerbing
SCP-230871-S278-1200-001 - Rev A - S278 Signing and Lining
SCP-230871-S278-4000-001 - Rev A - S278 Standard Details

	31.07.24
	BTP

	5.5
	The information submitted by SCP relating to general arrangement, signing and lining, standard details, surface finishes and kerbing and site clearance shall be finalised through the section 278 agreement however is sufficient to discharge condition 5 Highway works

	19/11/24
	MCC



	[bookmark: _Hlk159311646]Condition No 6: Waste Storage and Collection
	Date
	Action By

	6.1
	a) Notwithstanding the details as shown on 'Drawing- Site Plan- 105 Rev J', stamped as received by the City Council as Local Planning Authority on 8th February 2023, before the development commences a scheme for the storage and disposal of refuse shall be submitted to and approved in writing by the City Council as local planning authority.

New developments shall have refuse storage space for segregated waste collection and recycling. Internal and external storage areas are required.

b) The details of the approved scheme shall be implemented as part of the development and shall remain in situ whilst the use or development is in operation.

	
	BTP

	6.2
	Drawing submitted:

CL-BTP-00-SP-DR-A-3809_208 - Waste Collection Plan

	18.04.24
	BTP

	6.3
	Waste Management can be discharged on the basis of the submitted Waste Collection Plan ref 208 received 3rd May 2024. The approved details shall be in place so long as the associated development is occupied.

	25.07.24
	MCC



	Condition No 7: Car Parking
	Date
	Action By

	7.1
	Before the occupation of the development, car parking areas shown on 'Drawing- Site Plan- 105 Rev J, as received by the City Council as Local Planning Authority on 14th July 2023, shall be surfaced and made available for use. The car parking spaces shall be maintained in situ prior to the occupation of the authorised houses and remain in situ thereafter.

	
	

	7.2
	NMA Application Approved:

The area previously identified as the in-curtilage parking space to Plot 8, which is now designated as soft landscaping as shown on drawing 105 Rev M (Proposed Site Plan), shall not be used for the parking of motor vehicles at any time while the housing development approved under planning reference 136203/FO/2023 remains in existence.

	01.10.25
	MCC



	Condition No 8: Drainage Works
	Date
	Action By

	8.1
	No development shall take place until surface water drainage works have been implemented in accordance with Non-Statutory Technical Standards for Sustainable Drainage Systems (March 2015) or any subsequent replacements national standards and details that have been submitted to and approved in writing by the Local Planning Authority.

	
	SCP

	8.2
	Drawing submitted:

SCP-230871-S106-0500-001 - Rev A - S106 Drainage Layout

	18.04.24
	BTP

	8.3
	There has been insufficient information submitted to discharge condition 8 Drainage The information required is: 

The applicant must present a consistent package to discharge the condition (including all layouts and calculations). The layout and calculations must be jointly updated to account for any edits required. When preparing a resubmission, the applicant must ensure that the drainage layout and hydraulic calculations correspond, and that they can be cross referenced for checks. This includes layout annotations and schedule printouts. The condition cannot therefore be discharged at this time

	25.07.24
	MCC

	8.4
	Files submitted:

· SCP-230871-S106-0500-001 - Rev D - S106 Drainage Layout (Cross Lane)
· SCP-230871-S106-0500-040 - Rev B - Flow Control Detail (Sheet 1)
· SCP-230871-S106-0500-041 - Rev B - Flow Control Details (Sheet 2)
· 230871 - Cross Lane - Rev B - OMM (Combined)
· 2024.07.26 - SW Calcs (Cross Lane)

	31.07.24
	BTP

	8.5
	The following information: 

· Storm Sewer Design submitted by Micro Drainage, received 8th August 2024 
· SCP Drainage Operations and Maintenance manual -Doc Ref: LC/230871/OMM REV B received 8th August 2024 
· SCP Drainage Flow Control Details SCP-230871-S106-0500-041 Rev B received 8th August 2024
· SCP Drainage Layout received 8th August 2024 
· Email from SCP Design re management received 1st November 2024

is sufficient to discharge condition 8 as long as implemented in accordance with the approved documentation.

	19/11/24
	MCC



	Condition No 9: Drainage Maintenance scheme
	Date
	Action By

	9.1
	No development hereby permitted shall be occupied until details of the implementation, maintenance and management of the sustainable drainage scheme have been submitted to and approved by the local planning authority. The scheme shall be implemented and thereafter managed and maintained in accordance with the approved details.

	
	

	9.2
	Files submitted

· 230871 - Cross Lane - Rev B - OMM (Combined)
	31.07.24
	BTP

	9.3
	The information submitted by SCP Drainage Operations and Maintenance manual -Doc Ref: LC/230871/OMM REV B dated July 2024 is sufficient to discharge condition 9 as long as implemented in accordance with the approved documentation.

	19/11/24
	MCC

	9.4
	DOC files submitted:
· 06715188-040225 Part 2 Approved
· Photo 1 - 4VC-32030
· Photo 2 - 4VC-32030
· S106 Inspection Notice for Cross Lane - Connection status Satisfactory  14-08-2026
· SCP-230871-S106-0500-001 - Rev C - S106 Drainage Layout
· SCP-230871-S106-0500-040 - Rev A - Flow Control Details (Sheet 1)
· SCP-230871-S106-0500-041 - Rev A - Flow Control Details (Sheet 2)
· SCP-230871-S106-0500-050 - Rev A - Typical Drainage Construction Details (Sheet 1)
	17.08.26
	BTP



	[bookmark: _Hlk159311879]Condition No 10: Noise and overheating Mitigation
	Date
	Action By

	10.1
	a) Before the development commences a scheme for acoustically insulating the proposed residential accommodation against noise from Cross Lane shall be submitted to and approved in writing by the City Council as local planning authority. There may be other actual or potential sources of noise which require consideration on or near the site, including any local commercial/industrial premises.

The potential for overheating shall also be assessed and the noise insulation scheme shall take this into account. The approved noise insulation and ventilation scheme shall be completed before any of the dwelling units are occupied.

Noise survey data shall include measurements taken during a rush-hour period and night time to determine the appropriate sound insulation measures necessary.

b) Prior to first occupation of the residential units, a verification report shall be required to validate that the work undertaken throughout the development conforms to the recommendations and requirements in the approved acoustic consultant's report. The report shall also undertake post completion testing to confirm that the internal noise criteria have been met. Any instances of non-conformity with the recommendations in the report shall be detailed along with any measures required to ensure compliance with the internal noise criteria.

	
	

	10.2
	File submitted:

· Z57053 Cross Lane, Varey Street, Manchester NIA Report

	18.04.24
	BTP

	10.3
	Part a) of this condition can be discharged based upon the submitted documentation Construction, Demolition & Environmental Management Plan received on the 3rd of May 2024

	25.07.5.24
	MCC

	10.4
	File submitted:

· Z57053 Cross Lane and Varey Street Manchester - Noise Monitoring 22012026

	23.01.26
	BTP

	10.5
	The information submitted to support the discharge of Part b) Condition 10 Acoustic Insulation attached to previously approved ref 136203/FO/2023 in the form of the revised Azymuth Acoustics assessment reference Z57053.4 dated 02.04.26 has been assessed and additional information is still required to enable full discharge of this condition.

Therefore, Part b) of this condition cannot be discharged at this present time.

	17.04.26
	MCC

	10.6
	DOC files submitted:
· EC - Builders Declaration
· Z57053 Cross Lane - Varey Street, Manchester Part O Letter_12-06-26AH
	17.08.26
	BTP



	[bookmark: _Hlk159312116]Condition No 11: EV Charging
	Date
	Action By

	11.1
	Prior to commencement of the development, a scheme for electric vehicle charging shall be submitted to and approved in writing by the City Council as local planning authority.

a) Prior to occupation of the development any agreed mitigation measures shall be implemented and verified as such in writing by the City Council as local planning authority and shall remain in situ whilst the use or development is in operation.

	
	

	11.2
	Drawing submitted:

CL-BTP-00-SP-DR-A-3809_209 - EV Charging Plan

	18.04.24
	BTP

	11.3
	Vehicle charging point can be considered fully discharged based upon the submitted vehicle charging point plan ref 209 submitted 3rd of May 2024. The approved scheme shall be implemented and maintained for use so long as the development is occupied.

	25.07.24
	MCC



	Condition No 12: Boundary Treatment
	Date
	Action By

	12.1
	Prior to the first occupation of the development the Boundary Treatment shall be implemented in accordance with the approved plans 'Drawing- Proposed- Boundary Treatment, numbered 107 Rev C, stamped as received by the City Council as Local Planning Authority on 8 February 2023. The approved details shall be retained in accordance with the details and maintained in situ thereafter.

	
	



	Condition No 13: Hard and soft Landscaping
	Date
	Action By

	13.1
	Prior to occupation, details of a hard and soft landscaping scheme shall be submitted to and approved in writing by the City Council as local planning authority and once approved shall be implemented not later than 12 months from the date the buildings are first occupied. If within a period of 5 years from the date of the planting of any tree or shrub, that tree or shrub or any tree or shrub planted in replacement for it, is removed, uprooted or destroyed or dies, or becomes, in the opinion of the local planning authority, seriously damaged or defective, another tree or shrub of the same species and size as that originally planted shall be planted at the same place.

	
	

	13.2
	File submitted:

· 7098.01C Cross Lane 1 to 200 Mar 25

	18.03.25
	BTP

	13.3
	The information submitted with the planting schedule 7098.01 Rev C has more than adequate native species to be planted, and as such if the landscaping scheme hereby agreed is implemented within 12 months from the date the buildings are first occupied then condition 13 will have been complied with.

	16.05.25
	MCC



	Condition No 14: Bicycle Storage
	Date
	Action By

	14.1
	Prior to first use, details of the specifications, elevations, siting and appearance of the secured cycle storage shall be submitted to and approved in writing by the City Council as local planning authority. The agreed details shall be fully implemented prior to the first use of development, retained and maintained thereafter.

	
	

	14.2
	File submitted:

· 3809_bike shed

	18.03.25
	BTP

	14.3
	The information submitted for the Shedstore Forest double door overlap wooden bike shed has been assessed and is considered acceptable, therefore subject to the implementation of these agreed details condition 14 can be fully discharged.

	16.05.25
	MCC



	Condition No 15: Biodiversity Enhancements
	Date
	Action By

	15.1
	Before the occupation of the authorised dwellinghouses, a scheme to encourage biodiversity within the application site shall be submitted to and approve in writing by the City Council as local planning authority, including the provision measures to encourage habitats for native species and bird and, if appropriate, bat species. The development shall be implemented in accordance with approved scheme prior to the occupation of the authorised properties and shall be maintained in situ thereafter.

	
	

	15.2 
	File submitted:

· 81-131-002 Rev 2 Biodiversity Enhancement Plan - Cross Lane Manchester

	18.03.25
	BTP

	15.3
	The information submitted on the Biodiversity Enhancement Plan ref 81-131-002 showing the location and detailing of the proposed bat and bird boxes dated 18th March 2025 are considered acceptable and therefore these agreed details should be implemented within the development prior to occupation to ensure compliance with condition 15.

	16.05.25
	MCC



	Condition No 16: Tree Works
	Date
	Action By

	16.1
	All tree work should be carried out by a competent contractor in accordance with British Standard BS 3998 "Recommendations for Tree Work".

	
	



	Condition No 17: Trees
	Date
	Action By

	17.1
	In this condition "retained tree" means an existing tree, shrub or hedge which is to be as shown as retained on the approved plans and particulars; and paragraphs (a) and (b) below shall have effect until the expiration of 5 years from the date of the occupation of the building for its permitted use.

a) No retained tree shall be cut down, uprooted or destroyed, nor shall any retained tree be topped or lopped other than in accordance with the approved plans and particulars, without the written approval of the local planning authority. Any topping or lopping approved shall be carried out in accordance with British Standard 5387 (Trees in relation to construction)
b) If any retained tree is removed, uprooted or destroyed or dies, another tree shall be planted at the same place and that tree shall be of such size and species, and shall be planted at such time, as may be specified in writing by the local planning authority.
c) The erection of fencing for the protection of any retained tree shall be undertaken in accordance with the approved plans and particulars before any equipment, machinery or materials are brought on to the site for the purposes of the development, and shall be maintained until all equipment, machinery and surplus materials have been removed from the site. Nothing shall be stored or placed in any area fenced in accordance with this condition and the ground levels within those areas shall not be altered, nor shall any excavation be made, without the written consent of the local planning authority.

	
	



	Condition No 18: Site Clearance
	Date
	Action By

	18.1
	No vegetation clearance shall take place during the optimum period for bird nesting (March- September inclusive) unless nesting birds have been shown to be absent, or, a method statement for the demolition including for the protection of any nesting birds is agreed in writing by the City Council, Local Planning Authority. Any method statement shall then be implemented for the duration of the demolition works.

	
	



	Condition No 19: Secure by Design
	Date
	Action By

	19.1
	Prior to occupation, details of the measures to be incorporated into the development (or phase thereof) to demonstrate how secure by design accreditation will be achieved have been submitted to and approved in writing by the City Council as local planning authority. The development shall only be carried out in accordance with these approved details at all times thereafter.

The development hereby approved shall not be occupied or used until the Council as local planning authority has acknowledged in writing that it has received written confirmation of a secured by design accreditation.

	
	

	19.2
	Files submitted:

· SBD-Certificate-Cross Lane

	23.01.26
	BTP

	19.3
	The information submitted 26/01/2026 to support the discharge of condition 19 Secured By Design in the form of the Gold award accreditation is considered sufficient to discharge condition 10 in full so long as the scheme as approved is implemented.

	17.04.26
	MCC



	Condition No 20: Affordable Housing
	Date
	Action By

	20.1
	Upon first the occupation of the authorised houses, the development shall be fully implemented in accordance with the following document 'Supporting Information- Affordable Housing Statement', stamped as received by the City Council as Local Planning Authority on 8 Feb 2023, which confirms the provision of a total of 5 residential units for Social Rent in relation to the Cross Lane / Chapman Street, Roxburgh Street site.

The approved details shall be retained in accordance with the requirements of the statement at all times thereafter.
	
	

	20.2
	Clarification sought regarding wording of condition.

	01.11.23
	BTP

	20.3
	As long as it is implemented as per the Affordable Housing Statement, the typo in condition 20 to say social instead of affordable would not over ride it.

	01.11.23
	BTP



	Condition No 21: Permitted Development Rights
	Date
	Action By

	21.1
	Notwithstanding the provisions of the Town and Country Planning (General
Permitted Development) Order 2015 (or any order revoking and re-enacting that Order with or without modification) no garages, extensions, additional fenestration, roof alterations, porches or outbuildings shall be erected other than those expressly authorised by this permission.

	
	



	Condition No 22: Use Class
	Date
	Action By

	22.1
	Notwithstanding the provisions of the Town and Country Planning (General
Permitted Development) Order 2015 (or any order revoking and re-enacting that Order with or without modification) no part of the residential units shall be used for any other purpose (including any other purpose in Class C3 of the Schedule to the Town and Country Planning (Use Classes) Order 1987 as amended by The Town and Country Planning (Use Classes) (Amendment) (England) Order 2015, or in any provision equivalent to that Class in any statutory instrument revoking and re-enacting that Order with or without modification) other than the purpose(s) of C3(a) not precluding occupation by two unrelated people sharing a property.

	
	



	Condition No 23: Dwelling Use
	Date
	Action By

	23.1
	Notwithstanding the provisions of the Town and Country Planning (General
Permitted Development) Order 2015 as amended by The Town and Country Planning (General Permitted Development) (Amendment) (England) Order 2010 (or any order revoking and re-enacting that Order with or without modification) the dwelling houses hereby approved shall be used only as private dwellings (which description shall not include serviced apartments/apart hotels or similar uses where sleeping accommodation (with or without other services) is provided by way of trade for money or
money's worth and occupied by the same person for less than ninety  consecutive nights) and for no other purpose (including any other purpose in Class C3(a) of the Schedule to the Town and Country Planning (Use Classes) Order 1987 as amended by The Town and Country Planning (Use Classes) (Amendment) (England) Order 2010, or in any provision equivalent to that Class in any statutory instrument revoking and re-enacting that Order with or without modification) other than the purpose(s) of C3(a).

	
	



	Condition No 24: Equipment Noise Impact
	Date
	Action By

	24.1
	a) Externally mounted ancillary plant, equipment and servicing shall be selected and/or acoustically treated in accordance with a scheme designed so as to achieve a rating level of 5dB (LAeq) below the typical background (LA90) level at the nearest noise sensitive location. Prior to commencement of the use hereby approved the scheme shall be submitted to and approved in writing by the City Council as local planning authority in order to secure a reduction in the level of noise emanating from the site. The scheme shall be implemented in full before the use commences or as otherwise agreed in writing by the City Council as local planning authority.

a) Prior to the operation of the scheme a verification report shall be submitted to and approved in writing by the City Council as local planning authority to validate that the work undertaken throughout the development conforms to the recommendations and requirements in the approved acoustic report. The report shall also undertake post completion testing to confirm that the noise criteria have been met. Any instances of nonconformity with the recommendations in the report shall be detailed along with any measures required to ensure compliance with the agreed noise criteria.

	
	

	24.2
	Files submitted:

· Ashley Hurst Installer Pack_14
· Ashley Hurst Installer Pack_16
· Ashley Hurst Installer Pack_18
· Ashley Hurst Installer Pack_20
· Ashley Hurst Installer Pack_22
· Ashley Hurst Installer Pack_24
· Ashley Hurst Installer Pack_26
· Ashley Hurst Installer Pack_28
· Z57053 Cross Lane and Varey Street Manchester - Noise Monitoring 22012026

	23.01.26
	BTP

	24.3
	Due to the lack of evidential technical data to support the discharge of condition 24 relating to external plant and machinery, the pictorial information submitted by email from the applicant 13.04.2026 has been assessed and is considered to be insufficent to discharge this condition at this present time. Additional information is required relating to the assessment of the air source heat pumps to enable a full assessment and discharge of this condition.

	17.04.26
	MCC

	24.4
	Files submitted:
· Ashley Hurst Installer Pack_14
· Ashley Hurst Installer Pack_16
· Ashley Hurst Installer Pack_18
· Ashley Hurst Installer Pack_20
· Ashley Hurst Installer Pack_22
· Ashley Hurst Installer Pack_24
· Ashley Hurst Installer Pack_26
· Ashley Hurst Installer Pack_28
	17.08.26
	BTP



	Condition No 25: Window obscurity
	Date
	Action By

	25.1
	Before first occupation the windows in the first floor to the rear (southern) elevation shall be obscure glazed to a specification of no less than level 5 of the Pilkington Glass Scale or such other alternative equivalent and shall remain so in perpetuity.
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