## LB Schedule
Location Number | Photo Reference | Photo evidence | Exsisting wall make-up | Reason for Demo/GMI comments | Drawing referance
Basement
No 3 | 83723 |  | Double skin Original brickwork. | Historic brick wall removed during construction works and rebuilt in blockwork to make safe without listed building consent. Wall was unsafe during in Construction, Re-built in 4" block laid flat. Propose blockwork wall to remain as will be plastered over. | 2027-SBA-01-01B-D-A-00209
No 19 | 84330 84351 |  | Double skin Original brickwork. | This wall is now to remain as it is to suit SB & WRD details. | 2027-SBA-01-01B-D-A-00209
Ground Floor
No 3 | 110301 110257 |  | Single skin original brickwork | Now that the soft strip has been competed it shows a mixture of historical brickwork, parts of the wall altered with a modern engineered brick and other areas with a lightweight block completed by the previous owner. Wall has not been removed, wall is determined as being unstable following mortar test results. (see Structural Engineers report) The wall will need re-built as per structural engineers design update (140mm Block) | 2027-SBA-01-00-D-A-00210 WRD strucutal report.
No 4 | 114637 114657 114646 114826 |  | Single skin original brickwork | Now that the soft strip has been competed it shows a mixture of historical brickwork, parts of the wall altered with a modern engineered brick and other areas with a lightweight block completed by the previous owner. Wall has not been removed, wall is determined as being unstable following mortar test results. (see Structural Engineers report) The wall will need re-built as per structural engineers design update (140mm Block) | 2027-SBA-01-00-D-A-00210 WRD strucutal report.
No 5 | 110457 110707 |  | Blockwork or brickwork | Now that the soft strip has been competed it shows a mixture of historical brickwork, parts of the wall altered with a modern engineered brick and other areas with a lightweight block completed by the previous owner. Wall has not been removed, wall is determined as being unstable following mortar test results. (see Structural Engineers report) The wall will need re-built as per structural engineers design update (140mm Block) | 2027-SBA-01-00-D-A-00210 WRD strucutal report.
No 6 | 113741 113752 |  | Single skin original brickwork | Now that the soft strip has been competed it shows a mixture of historical brickwork, parts of the wall altered with blockwork completed by the previous owner. Wall has not been removed, wall is determined as being unstable following mortar test results. (see Structural Engineers report) The wall will need re-built as per structural engineers design update (140mm Block) | 2027-SBA-01-00-D-A-00210 WRD strucutal report.
No 7 | 113857 113912 |  | Single skin original brickwork | Now that the soft strip has been competed it shows historical brickwork & timber wall plate within wall,Parts of the wall plate have been replaced with new grey common brick without LBC. Wall has not been removed, wall is determined as being unstable following mortar test results. (see Structural Engineers report) The wall will need re-built as per structural engineers design update. (140mm block) | 2027-SBA-01-00-D-A-00210 WRD strucutal report.
No 8 | 114058 143923 |  | Single skin original brickwork | Wall construction was either historical brick or blockwork, This has been removed without LBC due to it being unsafe during construction works. The wall will need to be re-built as per structural engineers design update. (140mm block) | 2027-SBA-01-00-D-A-00210 WRD strucutal report.
No 9 | 113735 |  | Single skin original brickwork | Wall construction was historical brickwork, This has been removed without LBC due to it being unsafe during construction works. The wall will need to be re-built as per structural engineers design update. This will be 215mm brickwork using reclaimed bricks from deconstruction of corridor walls. | 2027-SBA-01-00-D-A-00210 WRD strucutal report.
No 10 | 114448 |  | Single skin original brickwork | Now that the soft strip has been competed it shows a mixture of historical brickwork. Wall has not been removed, wall is determined as being unstable following mortar test results. (see Structural Engineers report) The wall will need re-built as per structural engineers design update (140mm Block). this wall will now be deconstructed and re-built using 215mm reclaimed brickwork from the demolition of the corridor walls at ground and 1st floor levels. | 2027-SBA-01-00-D-A-00210 WRD strucutal report.
Level 1
No 3 | 144929 144913 |  | Single skin original brickwork | Historic brick wall altered during construction works and rebuilt in blockwork due to instability without LBC. Wall was unsafe during in Construction, Re-built in 140mm block. | 2027-SBA-01-01-D-A-00211 WRD strucutal report.
No 4 | 145444 145520 145455 145522 145500 |  | Single skin original brickwork | Now that the soft strip has been competed it shows a mixture of historical brickwork, parts of the wall altered with a modern engineered brick and other areas with a lightweight block completed by the previous owner. Wall has not been removed, wall is determined as being unstable following mortar test results. (see Structural Engineers report) The wall will need re-built as per structural engineers design update (140mm Block) | 2027-SBA-01-01-D-A-00211 WRD strucutal report.
No 5 | 145408 |  | Blockwork or brickwork | Wall construction was either historical brick or blockwork, This has been removed without LBC due to it being unsafe during construction works. The wall will need to be re-built as per structural engineers design update. (140mm block) | 2027-SBA-01-01-D-A-00211 WRD strucutal report.
No 6 | 144743 144755 |  | Single skin original brickwork | Now that the soft strip has been competed it shows a mixture of historical brickwork, parts of the wall altered with a modern brick completed by the previous owner. Parts of the wall had a timber wall plate with areas replaced with new grey common brick without LBC. Wall has not been removed, wall is determined as being unstable following mortar test results. (see Structural Engineers report) The wall will need re-built as per structural engineers design update (140mm Block) | 2027-SBA-01-01-D-A-00211 WRD strucutal report.
No 7 | 144913 144929 144905 144948 |  | Single skin original brickwork | Now that the soft strip has been competed it shows a mixture of historical brickwork, parts of the wall altered with a modern engineered brick and other areas with a lightweight block completed by the previous owner. Wall has not been removed, wall is determined as being unstable following mortar test results. (see Structural Engineers report) The wall will need re-built as per structural engineers design update (140mm Block) | 2027-SBA-01-01-D-A-00211 WRD strucutal report.
No 8 | 144657 |  | Blockwork or brickwork | Wall construction was either historical brick or blockwork, This has been removed without LBC due to it being unsafe during construction works. The wall will need to be re-built as per structural engineers design update. (140mm block). | 2027-SBA-01-01-D-A-00211 WRD strucutal report.
Level 2
No 3 | 84908 84932 84922 |  | Single skin original brickwork | Now that the soft strip has been competed it shows a mixture of historical brickwork, parts of the wall altered with a modern engineered brick and other areas with a lightweight block completed by the previous owner. This wall still has plaster on the wall. Wall has not been removed, wall is determined as being unstable following mortar test results. (see Structural Engineers report) The wall will need re-built as per structural engineers design update (140mm Block).the 2nd floor corridor will now be re-constructed in 100mm reclaimed bricks. | 2027-SBA-01-02-D-A-00212 WRD strucutal report.
No 4 | 84602 84532 84447 84503 |  | Single skin original brickwork | Now that the soft strip has been competed it shows a mixture of historical brickwork, parts of the wall altered with a modern engineered brick and other areas with a lightweight block completed by the previous owner. This wall still has plaster on the wall. Wall has not been removed, wall is determined as being unstable following mortar test results. (see Structural Engineers report) The wall will need re-built as per structural engineers design update (140mm Block).the 2nd floor corridor will now be re-constructed from re-claimed bricks 100mm wide | 2027-SBA-01-02-D-A-00212 WRD strucutal report.
No 6 | 84259 84309 |  | Single skin original brickwork | Now that the soft strip has been competed it shows a mixture of historical brickwork, parts of the wall altered with a modern engineered brick and other areas with a lightweight block completed by the previous owner. This wall still has areas of plaster on the wall. Wall has not been removed, wall is determined as being unstable following mortar test results. (see Structural Engineers report) The wall will need re-built as per structural engineers design update (140mm Block).the 2nd floor corridor will now be re-constructed from re-claimed bricks 100mm wide
No 7 | 84908 84932 84922 |  | Single skin original brickwork | Now that the soft strip has been competed it shows a mixture of historical brickwork, parts of the wall altered with a modern engineered brick and other areas with a lightweight block completed by the previous owner. This wall still has areas of plaster on the wall. Wall has not been removed, wall is determined as being unstable following mortar test results. (see Structural Engineers report) The wall will need re-built as per structural engineers design update (140mm Block). the 2nd floor corridor will now be re-constructed from reclaimed bricks 100mm wide.
No 16 | 84709 84750 84650 84702 |  | Single skin original brickwork | Now that the soft strip has been competed it shows a mixture of historical brickwork. This wall still has plaster on the wall. Wall has not been removed, wall is determined as being unstable following mortar test results. (see Structural Engineers report) The wall will need re-built as per structural engineers design update (140mm Block). this wall will now remain as existing and not removed as it is non-loadbearing.