## Project Information
Site Waste Management Plan
Project Information
Issue Date 3/1/2023 | 2026-09-09
Project Reference |  | NW201
Project Name / Title |  | MSV Moss Side Compound Site 3
Geographical location |  | Raby Street Moss Side
Postcode |  | M14 4SL
Project Start Date |  | 2027-02-22
Project End Date |  | 2030-02-28
Project Value / Cost |  | 55000000
Description of Project |  | The affordable housing scheme of 205 apartments and 7 houses for social rent and rent to buy. The project is to be constructed on a currently vacant site which is located between Princess Road/Barnhill St and Raby St/Moss Lane East. Site Three is a parcel of land at the intersection of Raby Street and Westwood Street which will house the Welfare and Office compound for the planned development.
Gross Internal Floor area (m2) |  | TBC
Total Site Area (m2) |  | 0.13 hectares
Classification |  | Site Welfare Compound for new Social Housing project on Site 1.
Project Use Class |  | Site Welfare Compound for new Social Housing project on Site 1.
Project Type / Work Stream |  | Temporary site compound with modular cabin structures
Construction Type |  | Modular welfare, office and storage cabins and containers
Client |  | Mosscare St Vincent
Emma Litchfield
Position |  | Development Manager
Contact number |  | 07867 418810
email address |  | Emma.Litchfield@msvhousing.co.uk
Principal contractor |  | Caddick Construction
Contract / Order number |  | NW
Person responsible |  | Joe Rawlinson
Responsibility |  | Project Director
Position |  | Project Director
Contact number |  | 07868 037 138
email address |  | JoeRawlinson@caddick.co.uk
Site Waste Manager
Person Responsible |  | Pat Farnan
Responsibility |  | Project Management Team
Company |  | Caddick Construction North West
Position |  | Project Management Team
Contact number |  | 07435 988841
email address |  | patrickfarnan@caddick.co.uk
SWMP Author |  | Pat Farnan
Company |  | Caddick Construction
Contact number |  | 07435 988841
email address |  | patrickfarnan@caddick.co.uk
Location & Storage of the plan
An electronic copy of the SWMP will be made available on site for the duration of the project
Declaration
All Waste produced on the site 3 is dealt with in accordance with the waste duty of care. All materials will be handled efficiently and managed appropriately.

## Waste Minimisation
Waste Minimisation Plan
Waste Minimisation target; 80% by tonnage diverted from landfill
Type | Waste Minimisation decision taken | By whom | Intended results
Reduced Level / overburden | Utilise suitable stored material as fill, utilise any on site reclaimed crushed 6f2 or tarmac arisings. Work to LK reclamation Strategy | CCL / Subcontractors | Minimise import of hardcore to be used
Demolition arisings/crush from existing car park or structures | The site is largely vacant with stone and tarmac areas. Where possible stone will be reused and vegetation strip will be minimised in accordance with the BNG strategy | CCL / Subcontractors | Reduce import requirement
Construction waste removal | Area allocated to segregate waste material types | CCL / Subcontractors | The waste waste material generated will be sent to be reprocessed at the transfer station operated by Kenny Waste
Concrete waste (for temporary cabin foundations and other miscellaneous concrete) | Wagons wash out in wash out skip/pit | CCL / Subcontractors | Water to be filtered, concrete waste to be sent to reprocessing by Kenny Waste
Waste Management | Waste material storage | CCL / Subcontractors | Reuse of larger elements of waste material where applicable. Other waste to go to Kenny Waste Transfer Facility
Contact recycling companies | Materials sent to agency’s or companies who recycle | CCL / Subcontractors | Minimise building products sent to land fill
Over ordering of construction materials | Reduce %age waste factor . Modular buildings used for compound with minimal extra material and waste generated by elements of site fitout | Subcontractors | Minimise new material products set to land fill
General and Canteen Waste generated by day to day site compound activities | Waste separated at source into separate waste bins in accordance with CCL Minimum Standards. Waste paper and card collected weekly, Canteen waste separated and removed to transfer station by Kenny Waste. Separate waste bins for cans and batteries | Subcontractors | Waste to be separated at source for recycling, Canteen and food waste minimised. Effective waste management in welfare facilities
Hazardous waste | Hazardous waste is not expected however if encountered will be disposed of in accordance with relevant procedures | CCL | No hazardous waste anticipated. This will be monitored and recorded
Limited site space for segregation and storage The Welfare compound on site 3 has limited space allows for limited on site separation or storage. As a result this operation is largely undertaken by our waste management partner off site at their facility. The following describes the process: Each skip or load that enters the facility removed from Caddick Construction is weighed on a fully calibrated weighbridge and captured on reports. The waste from each skip is tipped and compliance officers complete a visual inspection of each individual load and reports each waste stream by percentage. These percentages are then inputted into our waste management reporting system which then calculates the density/volume of each waste stream for each individual skip/tip. These waste reports will be available for Caddick Construction via an online portal. The waste reports can demonstrate exactly where any reductions in waste can be made by reporting on a full breakdown of each waste stream. This will allow Caddick Construction to identify potential waste streams that could have potentially been re-used onsite. CCL waste management partner will support Caddick Construction in this analysis by conducting site audits and perform toolbox talk to communicate the waste strategy which also helps to create a visual mindset within the site team to reduce waste. The waste ( Canteen waste, separated waste streams and general unseparated waste) that is collected from this project will be taken to a state of the art Material Reclamation Facility (MRF). Separation and identification at our facility is the key to successfully diverting the maximum amount of waste from landfill. Not all waste can be recycled, for certain types there simply isn’t a commercially viable solution available to us. Any waste that cannot be recycled is sent for incineration as Refuse Derived Fuel (RDF). |  | CCL / Waste Management Partner | Maximise the amount of reused or recycled waste and minimise waste to landfill
All other waste is directed to state of the art processing lines where it is separated by machine and ultimately by hand. The processing line gives us the capability to identify products that can be recycled as plastics, paper, cardboard, bottles and cans. These secondary recovered commodities form an important role in the manufacture of new packaging, ensuring that the use of virgin materials is kept to an absolute minimum. Not all waste can be recycled, for certain types there simply isn’t a commercially viable solution available to us. Any waste that cannot be recycled is sent for incineration as Refuse Derived Fuel (RDF). CCL will also be provided with Waste Destination Figures broken down into Waste Categories. From this you will be shown recycling figures broken down into: • Recycled restoration/remediation aggregates • Recycled and sent for further reprocessing • Recycled/Reprocessed to the WRAP protocol • Waste to Energy • Landfill

## Waste Tracker
Waste Tracker
The waste data is monitored monthly against the estimated values. The waste web portal also allows any other monitoring periods to be used.
Waste Stream | EWC CODE | Estimated Waste | [5 empty] | Waste Stream | EWC CODE |  | ACTUAL
|  | Total Tonnage | Reduce | Reuse | Recycle | Recover | Landfill |  |  | % of Estimated | Total Tonnage | Reduce | Reuse | Recycle | Recover | Landfill
Co Mingled and Fine Granular Material | 17 09 04 | 1 | 0.2 | 0.65 | 0 | 0.15 | 0 | Co Mingled and Fine Granular Material | 17 09 04 | 0% |  | 0 | 0 | 0 | 0 | 0
Mixed Dense Materials | 17 09 04 | 2 | 1.6 | 0.4 | 0 | 0 | 0 | Mixed Dense Materials | 17 09 04 | 0% |  | 0 | 0 | 0 | 0 | 0
Mixed Wood | 17 09 04 | 1 | 0 | 0.05 | 0.9 | 0.05 | 0 | Mixed Wood | 17 09 04 | 0% |  | 0 | 0 | 0 | 0 | 0
Tiles/Ceramics and Glass | 17 09 04 | 1 | 0.85 | 0.15 | 0 | 0 | 0 | Tiles/Ceramics and Glass | 17 09 04 | 0% |  | 0 | 0 | 0 | 0 | 0
Packaging & Polystyrene | 17 09 04 | 2 | 0 | 0 | 0.5 | 1.5 | 0 | Packaging & Polystyrene | 17 09 04 | 0% |  | 0 | 0 | 0 | 0 | 0
Rigid Plastic and Films | 17 09 04 | 2 | 0 | 0 | 0.6 | 1.4 | 0 | Rigid Plastic and Films | 17 09 04 | 0% |  | 0 | 0 | 0 | 0 | 0
Plasterboard & Gypsum Products | 17 09 04 | 3 | 0.15 | 0.15 | 2.7 | 0 | 0 | Plasterboard & Gypsum Products | 17 09 04 | 0% |  | 0 | 0 | 0 | 0 | 0
Carpet Tiles / Soft Floor Coverings | 17 09 04 | 1 | 0 | 0 | 0 | 0.5 | 0.5 | Carpet Tiles / Soft Floor Coverings | 17 09 04 | 0% |  | 0 | 0 | 0 | 0 | 0
Green Waste | 20 02 01 | 1 | 0 | 0.05 | 0.95 | 0 | 0 | Green Waste | 20 02 01 | 0% |  | 0 | 0 | 0 | 0 | 0
Furniture / Household | 17 09 04 | 1 | 0 | 0 | 0.25 | 0.5 | 0.25 | Furniture / Household | 17 09 04 | 0% |  | 0 | 0 | 0 | 0 | 0
Mixed Metals | 17 09 04 | 1 | 0 | 0 | 1 | 0 | 0 | Mixed Metals | 17 09 04 | 0% |  | 0 | 0 | 0 | 0 | 0
Non Recyclable Mixed Waste | 17 09 04 | 2 | 0 | 0 | 0 | ` | 0.04 | Non Recyclable Mixed Waste | 17 09 04 | 0% |  | 0 | 0 | 0 | 0 | 0
Canteen / Office / Adhoc | 17 09 04 | 5 | 0 | 0 | 0 | 4.9 | 0.1 | Canteen / Office / Adhoc | 17 09 04 | 0% |  | 0 | 0 | 0 | 0 | 0
Mixed Municipal Waste | 20 03 01 | 15 | 0 | 0 | 0 | 0.9 | 1 | Mixed Municipal Waste | 20 03 01 | 0% |  | 0 | 0 | 0 | 0 | 0
Hazardous Waste / Hazardous Packaging Waste | 15 01 | 1 | 0 | 0 | 0.3 | 0.7 | 0 | Hazardous Waste / Hazardous Packaging Waste | 15 01 | 0% |  | 0 | 0 | 0 | 0 | 0
Electrical Equipment | 17 09 04 | 0.1 | 0 | 0 | 0.03 | 0.07 | 0 | Electrical Equipment | 17 09 04 | 0% |  | 0 | 0 | 0 | 0 | 0
Plasterboard | 17 08 02 | 0.5 | 0.025 | 0.025 | 0.45 | 0 | 0 | Plasterboard | 17 08 02 | 0% |  | 0 | 0 | 0 | 0 | 0
Wood from Construction | 17 02 01 | 1 | 0 | 0.05 | 0.9 | 0.05 | 0 | Wood from Construction | 17 02 01 | 0% |  | 0 | 0 | 0 | 0 | 0
Mixed Inert / Brick / Concrete | 17 01 07 | 10 | 8 | 2 | 0 | 0 | 0 | Mixed Inert / Brick / Concrete | 17 01 07 | 0% |  | 0 | 0 | 0 | 0 | 0
Metals | 17 04 07 | 2 | 0 | 0 | 2 | 0 | 0 | Metals | 17 04 07 | 0% |  | 0 | 0 | 0 | 0 | 0
Non Compliant / Other | N/A | 3 | 0 | 0 | 0.9 | 0.6 | 1.5 | Non Compliant / Other | N/A | 0% |  | 0 | 0 | 0 | 0 | 0
Estimates |  | 55.6 | 10.825 | 3.525 | 11.48 | 11.32 | 3.39 | ACTUAL |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Muck Away
Totals Report

## Review
Review
The plan is to be monitored as a minimum every 6 months and the full review is to be completed within 3 months of site completion.
Total estimated quantity of waste | 55.6 | Tonnes
Total actual quantity of waste | 0 | Tonnes
M2 Waste generated | 0 | M2
Total landfilled | 0 | Tonnes
Total diverted from landfill | 0 | Tonnes
Recycled | #DIV/0! | %
Floor Area | 14200 | M2
quantity / M2 Internal Floor area | 0 | T/100m2
I confirm that the plan has been monitored on a regular basis to ensure that the work has progressed according to the plan.
Signed
Print name
Organisation
Position
Date
Comments on any deviation from the plan
Lessons learnt to be applied to future projects of this type